## Slide 1: 3GPP’s steps for IMT2020 In light of revised Rel-16 schedule
3GPP PCG #42_15
28th March 2019
Geneva, Switzerland

## Slide 2: Introduction
3GPP TSGs decided to move out the Release 16 freeze date by 3 months
ITU IMT[M.2020] schedule assumed to remain unchanged
This shortens the time available for the different steps that 3GPP TSGs and OPs need to take for IMT[M.2020] input
These slides present a proposal for these steps
  Timeline is very tight, but just about doable
PCG#42 is invited to review the proposal
  In particular, OPs should review whether they can perform their respective steps with the given time constraints

## Slide 3: Summary
A) Submission of RIT/SRIT proposal
  No changes necessary, 3GPP’s submission schedule and plans are unchanged
B) 3GPP contribution for ITU-R M.[IMT-2020]
  Specific measures are needed to ensure timely delivery of 3GPP specs for inclusion to ITU-R M.[IMT-2020]:
    For all RAN core and spectrum specs: June/2020 specs (RAN#88) will be used towards ITU-R
      It is assumed that all OPs will be able to complete transposition of June/2020 specs by WP5D#36 (7 – 14 October 2020; deadline: 30 September 2020).
    For RAN4 performance specs: September/2020 specs (RAN#89) will be used towards ITU-R
      Expedited MCC action needed to ensure rapid availability of RAN4 performance specs after RAN#89
      Expedited transposition needed for RAN4 performance specs to have them available by SG5 (23 – 24 November 2020; deadline: 16 November 2020
      At least ETSI and ATIS transposition will be available, other OPs on a best effort basis  OPs to discuss and confirm availability of their transpositions
   3GPP’s delivery of specs complete for IMT-2020
Details presented on the following slides

## Slide 4: Overall schedule
2019
Q2
Q3
Q4
Q1
2020
Q1
Q2
Q3
Q4
2021
Q1
Q2
Rel-17 package approval
Rel-16 RAN1 freeze
“Late drop”
Rel-15 late drop ASN.1
Rel-15 late drop freeze
Rel-16 freeze
Rel-16 ASN.1 freeze
Rel-16 RAN4
performance completion
A) Final RIT/SRIT submission:
5D#32
July/2019
B) 3GPP specs contributed to IMT2020 recommendation:
5D#36
October/2020
RAN#83
RAN#84
RAN#85
RAN#86
RAN#87
RAN#88
RAN#90
ITU-R
WP5D#32
ITU-R
WP5D#36
RAN#89

## Slide 5: A) Submission of 3GPP’s RIT/SRIT proposal (step 3 of ITU-R process)
Source: doc IMT-2020/2 Rev1 (attached to RP-170044)
Source: doc RP-172098
To be finalized in RAN#84 for submission to WP5D#32:
  Description Templates
  Compliance Templates
  Self-Evaluation
Source: RP-172098 & Rep ITU-R M.2411 (att. to RP-171559)

## Slide 6: B) 3GPP contribution for ITU-R M.[IMT-2020] (step 8 of ITU-R process)
Source: doc IMT-2020/2 Rev1 (attached to RP-170044)
The original 3GPP plans need to be reviewed to match the updated 3GPP Rel-16 timeline approved in Dec’18 (RAN#82)
Specific indications/milestones from ITU-R WP5D are not available yet
  It is expected they would be available in conjunction with the information on the process and use of GCS, references and certifications (anticipated to be finalized by WP5D#34 in Feb’20, and expected to be similar to the IMT-Advanced process in doc IMT-ADV/24Rev3)
The schedule proposed in the next slide is based on the process and timing applied in earlier ITU recommendations. This has to be cross-checked with ITU-R WP5D leadership

## Slide 7: B) Expected* milestones for M.[IMT-2020]
ITU-R WP5D#35 (24 June – 1 July 2020; deadline: 17 June 2020, 16:00 hours UTC):
  3GPP (as “RIT/SRIT Proponent”) delivers Form A to ITU-R
  3GPP (as “GCS Proponent”) delivers to ITU-R:
    Overview
    Titles and Synopsis of the GCS
    the GCS
    Certification B
Date TBD:
  OPs (as Transposing Organizations) deliver transposition references & Certifications C to ITU-R (to enable the BR to produce the complete draft Rec in time for WP5D#36)
ITU-R WP5D#36 (7 – 14 October 2020; deadline: 30 September 2020, 16:00 hours UTC):
  ITU-R WP5D reviews and agrees the completed draft new Rec. ITU-R M.[IMT-2020.SPECS] and forwards it to SG5 (23 – 24 November 2020; deadline: 16 November 2020)
* on the basis of the process and timing applied earlier. To be cross-checked with ITU-R WP5D leadership

## Slide 8: B) Proposed 3GPP schedule M.[IMT-2020] completion (step 8 of ITU-R process)
RAN#87 (Mar 2020 – Rel16 stage-3 freeze)
  Decision of the set of Specs to be submitted to ITU-R (Rel15 & Rel16)
  Approval of the contribution toward ITU-R WP5D#35 (deadline: 17 Jun’20) encompassing:
    Overview
    titles and synopsis of the GCS
    the GCS (Rel15 & Rel16)
  Approval of a contribution to ITU-R WP5D#35 on the details of the 3GPP process (similar doc RP-110856 submitted to ITU-R WP5D#11 in Jul’11)
  OPs coordinated action toward the submission to ITU-R WP5D#35 of:
    Form A
    Certifications B

## Slide 9
RAN#88 (15-18 Jun 2020 – Rel-16 ASN.1 freeze)
  Approval of the updated version of the GCS to be sent to ITU-R WP5D#36 (from RAN#89) and to be used by OPs as basis for transposition (with the exception of RAN4 performance specs)
  OPs coordinated action toward the submission to ITU-R of the transposition references (transposed standards not available yet) for these specs (all RAN core and spectrum specs) by 16 Nov ‘20 (SG5 deadline**)
RAN#89 (14-17 Sept 2020 – Rel16 RAN4 performance specs complete)
  Approval of RAN4 performance specs to be sent to ITU-R WP5D#36 (deadline: 30 Sept’20) as updated GCS, and to be transposed by OPs (by 16 Nov ‘20 – SG5 deadline**)
    Transposition of RAN4 performance specs from at least one OP shall be available for SG5 deadline
  OPs coordinated action toward the submission to ITU-R of Certifications C (when the OPs transposed standards are available), with all CRs approved in RAN#88*** and, for the selected RAN4 Specs, in RAN#89***
** It is anticipated that at least one set of transposed standards has to be fully available
*** in case ITU-R does not intend to update the GCS originally submitted to WP5D#35
B) Proposed 3GPP schedule M.[IMT-2020] completion (step 8 of ITU-R process) – contd…

## Slide 10: Annex
List of RAN4 performance specs
  UE
    TS38.101-4
    TS38.133 (this spec includes both RRM core and performance requirements)
  Base station
    TS38.104 (this spec includes both BS core and performance requirements)
    TS38.141-1 (this is BS test spec but typically these BS test cases are also completed as part of the performance work)
    TS38.141-2 (this is BS test spec but typically these BS test cases are also completed as part of the performance work)
OP responsible persons for transposition //needs checking
  ARIB arib-3gpp@arib.or.jp
  ATIS Steve Barclay SBARCLAY@atis.org , Farrokh Khatibi fkhatibi@qti.qualcomm.com
  CCSA ZHU Longming zhu.longming@zte.com.cn
  ETSI john.meredith@etsi.org
  TSDSI Jayeeta Saha jayeeta@tsdsi.org, A.K. Mittal akmittal@tsdsi.org, Bindoo Srivastava bindoo@tsdsi.org
  TTA Hyeyoung (Esthel) Lee hyeyoung@tta.or.kr
  TTC Masaomi SUMITA <sumita@s.ttc.or.jp>