## Slide 1
3GPP TSG RAN #77 RP-171523
Sapporo, JP, 11 – 14 Sep, 2017
RAN4 Chairman: Xutao Zhou
RAN4 Vice Chairman: Xizeng Dai
RAN4 Vice Chairman: Hiromasa Umeda
RAN4 Secretary: Kyoungseok Oh
Status Report RAN WG4 to TSG-RAN #77

## Slide 2: Meetings and Elections
Meetings held since the last plenary
No challenge received for sitting vice chairman in Aug meeting. Xizeng Dai and Hiromasa Umeda will continue their second term as RAN4 vice chairman
RAN4 NR ad-hoc #2 | 27 – 29 June 2017 | Qingdao, CN | ZTE
RAN4 MIMO OTA ad-hoc | 29 – 30 June 2017 | Qingdao, CN | ZTE
RAN4 #84 | 21 – 25 Aug 2017 | Berlin, DE | EF3
RAN #77 | 11 – 14 Sep 2017 | Sapporo, JP | JF3

## Slide 3: 2017 Statistics
Meeting | Date | Delegates registered/attendees | Documents requested/uploaded
RAN4 NR ad-hoc #2 | 27 – 29 June 2017 | 183/117 | 466/449
RAN4 #84 | 21 – 25 Sep 2017 | 261/192 | 2136/2063
Chart: 
| NR#1 | #82 | #82bis | #83 | NR #2 | #84 | #84bis | #85
RAN4 Delegates 2017 | 94 | 218 | 224 | 240 | 117 | 192
Chart: 
| NR#1 | #82 | #82bis | #83 | NR #2 | #84 | #84bis | #85
RAN4 Submitted Contributions 2017 | 292 | 1879 | 1560 | 1826 | 449 | 2063

## Slide 4: WI/SI to be completed
Rel-14 WI
  Radiated requirements for the verification of multi-antenna reception performance of UEs
  eMBMS enhancement for LTE
  Enhanced LAA for LTE
  Uplink capacity enhancement for LTE
  LTE-based V2X Services
  4 RX antenna ports with CA for LTE DL
  Enhanced CRS and SU-MIMO interference mitigation performance requirements for LTE
Rel-15 WI
  450MHz E-UTRA FDD Band for LTE PPDR and PMR/PAMR in Europe
  E-UTRA 700MHz in Europe for Broadband-PPDR
  FDD operating band in the L-band for LTE
  TDD operating band in the L-band for LTE
  LTE Extended 1.5 GHz SDL band (1427 – 1518 MHz) and LTE Carrier Aggregation (2DL/1UL) with Band 20
  US 600 MHz Band for LTE
  Addition of band 28 and 40 to LTE MTC Cat.0
  Performance requirements of interference cancellation receiver for LTE BS

## Slide 5: WI/SI to be extended
Rel-14 Core WI extended to March 2018
  LTE UE TRP and TRS and UTRA Hand Phantom related UE TRP and TRS Requirements
Rel-14 Performance WI extended to Dec 2017
  Enhancement on Full-Dimension (FD) MIMO for LTE

## Slide 6: Spectrum related WI/SI status
Name ( new WIs approved in RAN#73 and WIs revised finish dates by red font) | Start_Date | Finish_Date | Status Report or WID | Completion
Rel-15 WI |  | Performance WI |  | Core/Perf
450MHz E-UTRA FDD Band for LTE PPDR and PMR/PAMR in Europe | 12/2016 | 09/2017 | RP-171710 | 100/100 %
E-UTRA 700MHz in Europe for Broadband-PPDR | 12/2016 | 09/2017 | RP-171712 | 100/NA %
FDD operating band in the L-band for LTE | 12/2016 | 09/2017 | RP-171837 | 100/100 %
LTE Extended 1.5 GHz SDL band (1427 – 1518 MHz) and LTE Carrier Aggregation (2DL/1UL) with Band 20 | 12/2016 | 09/2017 | RP-171989 | 100/100 %
TDD operating band in the L-band for LTE | 12/2016 | 09/2017 | RP-171746 | 100/100 %
Add UE Power Class 2 to band 41 intra-band contiguous LTE carrier aggregation | 12/2016 | 12/2017 | RP-171707 | 90/0 %
Add Power Class 1 UE to B3/B20/B28 | 09/2016 | 09/2017 | RP-171756 | 100/NA %
US 600 MHz Band for LTE | 03/2017 | 09/2017 | RP-171632 | 100/100 %
V2X new band combinations for LTE | 03/2017 | 06/2018 | RP-171610 | 40/0 %
450MHz Band for LTE in region 3 | 03/2017 | 12/2017 | RP-171569 | 80/0 %
LAA/eLAA for the CBRS 3.5GHz band in US | 03/2017 | 12/2017 | RP-171996 | 50/50 %
Introduction of new band support for 4Rx antenna ports for LTE for Rel-15 | 06/2017 | 06/2018 | RP-171747 | 99/0 %
Addition of band 28 and 40 to LTE MTC Cat.0 | 06/2017 | 09/2017 | RP-171760 | 100/NA %
LTE Advanced high power UE (power class 2) for Rel-15 | 06/2017 | 06/2018 | RP-171754 | 10/NA %
New LTE band for 3.3-3.4 GHz for Africa | 06/2017 | 06/2018 | RP-171758 | 10/0 %
Rel-15 Basket CA WI |  |  |  | 
LTE Advanced intra-band Carrier Aggregation Rel-15 for xDL/yUL including contiguous and non-contiguous spectrum | 06/2017 | 06/2018 | RP-171623 | 25/25 %
LTE Advanced inter-band CA Rel-15 for 2DL/1UL | 06/2017 | 06/2018 | RP-171990 | 
LTE Advanced inter-band CA Rel-15 for 3DL/1UL | 06/2017 | 06/2018 | RP-171748 | 20/20 %
LTE Advanced inter-band CA Rel-15 for 4DL/1UL | 06/2017 | 06/2018 | RP-171624 | 54/54 %
LTE Advanced inter-band CA Rel-15 for 5DL/1UL | 06/2017 | 06/2018 | RP-171573 | 20/20 %
LTE Advanced inter-band CA Rel-15 for 2DL/2UL | 06/2017 | 06/2018 | RP-171750 | 20/20 %
LTE Advanced inter-band CA Rel-15 for xDL/2UL with x=3,4,5 | 06/2017 | 06/2018 | RP-171609 | 20/0 %

## Slide 7: Non-spectrum related WI/SI status RAN4 led items Rel-14
Name (revised finish dates by red font) | Start_Date | Finish_Date | Status Report | Completion
Rel-14 WI |  | Performance WI |  | Core/Perf
LTE UE TRP and TRS and UTRA Hand Phantom related UE TRP and TRS Requirements | 12/2012 | 03/2018 | RP-171585 | 85/NA %
Radiated requirements for the verification of multi-antenna reception performance of UEs | 03/2016 | 09/2017 | RP-171834 | 100/NA %
Enhanced CRS and SU-MIMO interference mitigation performance requirements for LTE | 09/2016 | 09/2017 | RP-171830 | NA/100 %
4 RX antenna ports with CA for LTE DL | 09/2016 | 09/2017 | RP-171873 | 100/100 %
Rel-15 WI |  |  |  | 
Further Enhancement of Base Station (BS) RF and EMC requirements for Active Antenna System (AAS) | 03/2016 | 06/2018 | RP-171744 | 70/20 %
Performance requirements of interference cancellation receiver for LTE BS | 06/2017 | 09/2017 | RP-171786 | NA/100 %
UE requirements for network-based CRS interference mitigation for LTE | 06/2017 | 06/2018 | RP-171586 | NA/15 %
LTE CRS Interference Mitigation Performance Requirements for Single RX Chain UEs | 06/2017 | 06/2018 | RP-171832 | NA/20 %
Rel-15 SI |  |  |  | 
Study on LTE DL 8Rx antenna ports | 06/2017 | 12/2017 | RP-171752 | 35%
Study on test methods for New Radio | 03/2017 | 03/2018 | RP-171827 | 15%

## Slide 8: Status of other WG led WI/SIs impacting RAN4
Name (revised finish dates by red font) | Start_Date | Finish_Date | Status Report | Completion
Rel-14 WI |  | Performance WI |  | Core/Perf
Enhanced LAA for LTE | 12/2015 | 09/2017 | RP-171856 | 100/100 %
Uplink capacity enhancement for LTE | 03/2016 | 09/2017 | RP-171702 | 100/100 %
Further enhanced MTC for LTE | 06/2016 | 12/2017 | RP-171930 | 100/60 %
NB-IoT enhancement | 06/2016 | 12/2017 | RP-171735 | 100/50 %
LTE-based V2X Services | 06/2016 | 09/2017 | RP-171617 | 100/100 %
eMBMS enhancements for LTE | 09/2016 | 09/2017 | RP-171811 | 100/100 %
Enhancements on Full-Dimension (FD) MIMO for LTE | 03/2016 | 12/2017 | RP-171788 | 100/70 %
Rel-15 WI |  |  |  | 
Shortened TTI and processing time for LTE | 09/2016 | 03/2018 | RP-171620 | 75/0 %
Even further enhanced MTC for LTC | 03/2017 | 12/2018 | RP-171929 | 20/0 %
Further NB-IoT enhancements | 03/2017 | 12/2018 | RP-171736 | 15/0 %
Enhancements to LTE operation in unlicensed spectrum | 03/2017 | 12/2018 | RP-171622 | 30/0 %
High capacity stationary wireless link for LTE | 03/2017 | 06/2018 | RP-171737 | 60/0 %
Cellular V2X Phase 2 | 03/2017 | 12/2018 | RP-171739 | 30/0 %
Further enhancements to Coordinated Multi-Point (CoMP) Operation for LTE | 03/2017 | 03/2018 | RP-171817 | 90/0 %
Ultra Reliable Low Latency Communication for LTE | 03/2017 | 12/2018 | RP-171627 | 0/0 %
Signaling reduction to enable light connection for LTE | 03/2017 | 12/2018 | RP-171741 | 79/0 %
UE Positioning Accuracy Enhancements for LTE | 03/2017 | 06/2018 | RP-171734 | 20/0 %
Enhancing CA Utilization | 03/2017 | 12/2018 | RP-171859 | 22/0 %

## Slide 9: LTE Items
Handling of LTE TRP and TRS
  LTE TRP and TRS WI is proposed to be extended to March 2018
  Large gap between operators proposal and UE vendors proposal on the TRP/TRS performance is observed in the last RAN4 meeting.
  It is challenging to address the above gaps using meeting time. More offline discussion is expected to address the different opinion.
Add Band 4, Band 14 and 71 to list of operating bands for Cat M1, M2, NB1 and NB2 applicability
  New WI proposal on adding new bands to support Cat M1, M2, NB1 and NB2 is proposed in RP-171572. Further discussion on the WID is expected in RAN #77.
  Draft CRs for 36.101 have been endorsed in RAN4 #84. Companies is going to submit the company CRs in RAN#77 after above new WI is approved
  Companies also proposed to close the WI in RAN #77 after approval of company CRs.

## Slide 10: NR Items
Meeting arrangement for NR in Q4
  Three parallel sessions for NR are arranged in June NR ad-hoc #2 and Aug #84 meeting
  Total 28 TUs are used in Aug #84 meeting
  RAN4 is planning to have Nov Ad-hoc for NR on 30th Oct – 2nd Nov
NR WID update
  New proposals on NR bands and NR-LTE band combinations have been reviewed in previous RAN4 meetings. RAN4 endorsed the lists of new proposals in R4-1707566. NR WID is supposed to be updated correspondingly.
  RAN4 agreed the WF for handling general TR in R4-1708837. Three TRs will be generated to capture the band/band combination agnostic aspects. NR WID is supposed to be updated correspondingly.

## Slide 11: RAN WG4 Work plan

## Slide 12: new WI/SI proposals
New Proposals for LTE (Led by RAN4)
  WI: Multi-node testing for License-Assisted Access (LAA) (RP-171727)
  WI: Lower Complexity Higher Order MIMO for LTE (RP-171787)
  WI: Addition of Bands for Cat M1, M2, NB1 and NB2 applicability (RP-171572)
  SI: Study on Advanced Receivers LTE V2X (RP-171833)
  Spectrum related
      Extended-Band12 new E-UTRA Band (RP-171575)
      New band for PS-LTE in Korea (RP-171908)
  New Proposal for NR (Led by RAN4)
    SI: Study on vehicle UE for NR (Rp-171803)

## Slide 13: RAN4 capacity
  To meet the NR timeline, in Q3, three parallel sessions are arranged as below as below
  In Q4, RAN4 is planning to arrange the meeting as same as Q3. Therefore, it is proposed to revise the capacity as
    Total TU for LTE (13 for RF and 13 for RD) is 26 TUs, i.e., 36 TUs -> 26 TUs for LTE
    Increase total TU for NR to 28 TUs, i.e., 18 TUs -> 28 TUs for NR
  Based on above meeting arrangement and RAN4 capacity, there is no additional TU available for new LTE/NR proposals.

## Slide 14: RAN WG4 Schedule
Meeting | Date | Location | Host
RAN4 NR #3 ad-hoc | 18 – 21 Sep 2017 | Nagoya, JP | JF3
RAN4 #84bis | 9 - 13 Oct 2017 | Dubrovnik, HR | EF3
RAN4 NR #4 ad-hoc | 30 Oct -2 Nov 2017 | TBD | ZTE

## Slide 15: Thanks to
Vice chairmen Xizeng Dai and Hiromasa Umeda for preparation and session chairing
Kyoungseok Oh and Igor Minaev for efficient secretary support
Evening AH chairs:
  Richard Kybett, Muhammad Kazmi, Jiantao Xue, Qiming Li, Yang Tang, Haijie Qiu, Thorsten Hertel, Valentin Gheorghiu
Delegates for enthusiastic contributions
ZTE and EF3 for meeting hosting