## Slide 1: Way forward for handling URLLC for LTE feature
Nokia, Nokia Shanghai Bell
3GPP TSG RAN #79
19 – 22 March, 2018, Chennai, India
Agenda Item: 10.2.4
RP-180489

## Slide 2: Background
According to the current WI schedule, the work on URLLC for LTE in the RAN WGs has only one quarter left
The progress in the RAN WGs so far has been rather limited (especially in RAN1)
  only 20% in RAN1
The completion of the WI with its current scope and the Rel-15 timescale seems impossible
  Not wanting to repeat the unreasonable working conditions seen recently in other items, RAN should give a clear message that WGs are not expected to make extreme efforts on this WI

## Slide 3: Alternatives for URLLC for LTE handling
Alt.1: Postpone the core completion of URLLC for LTE WI to a reasonable completion date, e.g. RAN#83 (Mar. 2019)
  By implication, reliability enhancements within low latency bounds for LTE would become a Rel-16 feature
  This would keep the whole feature together as a single marketable entity in one release
Alt. 2: Restrict the Rel-15 URLLC focus down to a self-consistent subset of functionality that can realistically be completed by June
  This would provide at least some completed enhanced reliability functionalities in Rel-15
  If desired, a new follow-up WI could be considered in Rel-16 to work on further URLLC enhancements
  Details on the following slides

## Slide 4: Alt. 2 details: (1) Restricted URLLC focus in Rel-15
To support enhanced reliability within low latency bounds in Rel-15 the following is to be specified by June:
PCFICH reliability: Semi-static configuration of PCFICH duration to avoid PCFICH reliability impacting the overall DL reliability (RAN2 led)
Blind repetition for scheduled DL-SCH operation (RAN1 led)
  Finalise details of RAN1 agreement to support blind PDSCH repetition.
  Using legacy DCI, (S/E)PDCCH, (S)PUCCH, HARQ-Ack operation
PDCP data duplication (RAN2)
For the solutions above, introduce any necessary UE and base station core requirements [RAN4]

## Slide 5
The following shall not be addressed in the current WI:
DL control channel enhancements
  Including compact DCI, higher ALs, PDCCH candidate combining (in time, frequency &/ candidate level) as well as false alarm studies
MCS / CSI / CQI enhancements
  Including CSI target BLERs, lower MCS and new URLLC CQI tables
UL control enhancements
  Including PUCCH repetition, TPC and power boosting
UL-SCH enhancements
  Including TPC enhancements and UL preemption techniques
More granular time reference value to a UE from an eNB
Alt. 2 details: (2) Exclusions from WI scope

## Slide 6: Conclusion: Proposed Way Forward
RAN#79 should choose one of the following alternatives for the future work on the URLLC for LTE feature:
    Alt.1: Postpone the core completion of URLLC for LTE WI to a reasonable completion date, e.g. RAN#83 (Mar. 2019)
    Alt. 2: Restrict the Rel-15 URLLC focus down to a self-consistent subset of functionality that can realistically be completed by June
      Agree the details on Slides 4 and 5