## Slide 1: FS_SCIPTO Status Update
Eric Siow
Intel
FS_CSIPTO Rapporteur
3GPP TSG-SA WG1 Meeting #64
San Francisco, CA, USA, 11 – 15 November 2013
Remember: present only slides 3, 6, 7
Notes: 1

## Slide 2: FS_CSIPTO Status
Is this a new WI? No
This WI has been approved at SP#61
  Approved WID is in tdoc SP-130417
Notes: 1

## Slide 3: C_SIPTO Progress
Progress made at this meeting
  TR Skeleton, Introduction and Scope agreed
  CSIPTO for IMS & Non-IMS use cases agreed
  On-Demand & Always-On Dual PDN Connection use cases agreed
Work/Study Item Completion: 15%
Draft TR 22.828 Completion: 15%
Controversial issues
  None
Notes: 1

## Slide 4: FS_CSIPTO Meeting Time
Number of slots assigned at this meeting
  sum of plenary and drafting slots: 2
Number of slots requested for next meeting
  sum of plenary and drafting slots: 4
Number of Drafting session participants: 40
Notes: 1

## Slide 5: FS_CSIPTO Completion Date
Target completion date in WID: 06/2014 SP#64
Current target completion date: 06/2014 SP#64
Will target completion date be met? No
If not, change target completion date to:
  12/2014 SP#66
Expected date to send TR 22.828 to SA plenary:
  For information: SA1#66 (05/2014)
  For approval: SA1#68 (11/2014)
Notes: 1

## Slide 6: FS_CSIPTO Planning/Progress
Topics to focus on at SA1#65 (Jan 2014):
  Address identified FFS items: Impact to APN AMBR; Definitions for “suboptimal “ and “more optimized” PDN connections
Planning for subsequent meetings
  SA1#66 (May 2014)
    Use cases with potential requirements
  SA1#67 (Aug 2014)
    Compile general requirements and TR
  SA1#68 (Nov 2014)
    Complete TR
Notes: 1

## Slide 7: Work plan between meetings
Email discussion
  New contributions
  FFS items
  Tentative start date: 11/20/2013
Notes: 1

## Slide 8: FS_CSIPTO Progress Estimate
Estimated percentage completion:
  SA1#65 (Jan 2014): 25%
  SA1#66 (May 2014): 50%
  SA1#67 (Aug 2014): 75%
  SA1#68 (Nov 2014): 100%
Notes: 1

## Slide 9: FS_CSIPTO Agreed documents
List of agreed documents at this meeting:
S1-135025 | Rapporteur | TR Skeleton
S1-135026 | Rapporteur | TR Introduction
S1-135027 | Rapporteur | TR Scope
S1-135214 | Intel; Samsung, | CSIPTO for Non-IMS
S1-135215 | Intel; Samsung | CSIPTO for IMS
S1-135284 | Samsung, Intel, NEC, Acer, ITRI | CSIPTO Always-On Dual PDN Connection
S1-135216 | Samsung, Intel, NEC, Acer, ITRI | CSIPTO On-Demand Dual PDN Connection
Notes: 1