## Slide 1: MCPTT Status Update Mission Critical Push to Talk
David Cypher
US Department of Commerce
MCPTT Rapporteur
3GPP TSG-SA WG1 Meeting #66bis on MCPTT and GCSE
Dublin, Ireland, 15-17 July 2014
Remember: present only slides 3, 6, 7
Notes: 1

## Slide 2: MCPTT Status
Is this a new WI? <n>
This WI has been approved at SP#62
  Approved WID is in tdoc SP-130728
Notes: 1

## Slide 3: MCPTT Progress
Progress made at this meeting
  rework of definitions and their application
  addition of MCPTT Administrator capabilities
  general clean up
Work/Study Item Completion: 50 %
Draft TS 22.179 Completion: 50 %
Controversial issues
  Definitions
  On- and off-network requirements and organization
  Overall TS structure
  Expansion of WID / Consolidation of GCSE_LTE
Notes: 1

## Slide 4: MCPTT Meeting Time
Number of slots assigned at this meeting
  sum of plenary and drafting slots: 14
Number of slots requested for next meeting
  sum of plenary and drafting slots: 10
Notes: 1

## Slide 5: MCPTT Completion Date
Target completion date in WID: <09/2014> SP#65
Is current completion date the same as above? <n>
  If not, current target completion date: <12/2014> SP#66
Will target completion date be met? <n>
  If not, change target completion date to:
    <12/2014> SP#66
Expected date to send <TS> to SA plenary:
  For information: SA1#65 (09/2014)
  For approval: SA1#66 (12/2014)
Notes: 1

## Slide 6: MCPTT Planning/Progress
Topics to focus on at SA1#67 (Aug 2014):
  Revisions/resubmissions of contributions from SA1#66bis
  Informative text for every clause and subclause
  OMA and TCCA requirements
Planning for subsequent meetings
  SA1#68 (Nov 2014)
    Revisions / resubmissions of contributions from SA1#67
    OMA and TCCA requirements
    Final clean up
Notes: 1

## Slide 7: Work plan between meetings
Email discussion
  None planned
Notes: 1

## Slide 8: MCPTT Progress Estimate
Estimated percentage completion:
  SA1#68 (Nov 2014): <100%>
Notes: 1

## Slide 9: MCPTT Agreed documents
List of agreed documents at this meeting:
S1-142012 | US Department of Commerce | Split double requirement in Security 4.10
S1-142013 | Harris Corp., Motorola Solutions Inc., US DoC | Restatement of first requirement of section 5.2, Project 25
S1-142016 | Harris Corp., Motorola Solutions Inc., US DoC | Modification to an MCPTT Emergency Alert requirement, 4.6.1.3.1
S1-142018 | US Department of Commerce | Modification to first note in section 4.5.1.2
S1-142020 | Harris Corp., Motorola Solutions Inc., US DoC | Clarification on the use of Group Regroup and User Regroup
S1-142034 | Harris Corporation | TS22.179 v0.4.1 – Definition of MCPTT Administrator
S1-142086 | Home Office | Alignment of MCPTT Terminology Previously Agreed in S1-141544
S1-142087 | Home Office | Alignment of MCPTT Terminology Previously Agreed in S1-141544
S1-142088 | Home Office | Alignment of MCPTT Terminology Previously Agreed in S1-141544
S1-142099 | Alcatel-Lucent | MCPTT Scope
S1-142100 | Alcatel-Lucent | References for ProSe and GCSE specs
Notes: 1

## Slide 10: MCPTT Agreed documents
List of agreed documents at this meeting:
S1-142102 | Huawei, TD Tech | Introduction to dispatcher for MCPTT
S1-142110 | Alcatel-Lucent, Department of Commerce | Proposed restructuring to indicate applicability of requirements to on or off network usage
S1-142111 | Alcatel-Lucent | MCPTT Off-Network Definition
S1-142113 | US Department of Commerce | Collecting and uniquely labelling Variables
S1-142114 |  | 
S1-142116 | Motorola Solutions Inc. | Modifications to 4.3 General Group Call
S1-142118 | Home Office | Revision of the Selected MCPTT Group
S1-142120 | US Department of Commerce | Modification of a call monitoring (section 4.3.4) requirement
S1-142121 | Motorola Solutions | Modifications to 4.3.4 Call Monitoring
S1-142123 | Harris Corporation | TS22.179 v0.4.1 FFS item on the relationship between UE and User authorizations
S1-142124 | Harris Corporation | TS22.179 v0.4.1 FFS item on 1:1 Call Override Capabilities
Notes: 1

## Slide 11: MCPTT Agreed documents
List of agreed documents at this meeting:
S1-142126 | Harris Corporation | TS 22.179 v0.4.1 MCPTT Management Requirements #3
S1-142127 | Harris Corporation | TS 22.179 v0.4.1 MCPTT Management Requirements #4
S1-142128 | Home Office | Alignment of MCPTT Terminology Previously Agreed in S1-141544
S1-142129 | Huawei, TD-Tech | Modifications to Audio MCPTT Access time and Mouth-to-ear latency, 4.5.1
S1-142130 | Harris Corporation | TS22.179 v0.4.1 FFS Item on Late Call Entry Performance
S1-142131 | General Dynamics UK Ltd | References and Abbreviations for MCPTT Audio / Voice Quality
S1-142132 | French Ministry of Interior | Generic priority management
S1-142136 | Harris Corporation | MCPTT Management Requirements (5)
Notes: 1

## Slide 12: MCPTT Agreed documents
List of agreed documents at this meeting:
S1-142140 | Harris Corporation | Legacy Interworking Overview
S1-142141 | Harris Corp, Motorola Solutions Inc., US DoC | Restatement of first requirement of section 5.4, Legacy Land Mobile Radio
S1-142142 | General Dynamics UK Ltd | Clarify Private Call and Broadcast Group definitions
S1-142143 | Home Office | Additional Text for Talker ID Requirements
S1-142144 | BlackBerry UK Limited, Home Office | Clarification of location requirements in TS 22.179
S1-142145 | French Ministry of Interior | MCPTT Systems Interworking
S1-142146 | Home Office | MCPTT State Diagram
S1-142147 | Motorola Solutions Inc | Moving requirements from definitions to main body
S1-142148 | Alcatel-Lucent | Proposed restructuring the document for common, on network and off network requirements
S1-142149 | Motorola Solutions Inc | Modifications to Floor Control requirement, 4.2
S1-142150 | Home Office | Call Commencement Modes Consolidation of Requirements
S1-142151 | Motorola Solutions Inc | Modifications to 4.3.4 Call Monitoring
S1-142153 | Alcatel-Lucent | Definitions of off network
S1-142154 | Harris Corporation | MCPTT Management Requirements (2)
Notes: 1