## dinu
ID | UID | Name | Acronym | Level | Release | Resource | Start | Finish | Compl | Hyperlink | SR | WI_rapporteur_name | WI_rapporteur_Email | Notes | TS_TR
3GPP Work Plan v. Oct 10th, extract for SA1#68
1 | 0 | Release 14 Features | - | 1 | Rel-14 | SP,RP,CP,GP | 2014-12-12 08:00 | 2017-06-14 17:00 | 0% | - | - | - | - | - | -
2 | 0 | Release 14 Studies | - | 1 | Rel-14 | SP,RP,CP,GP | 2014-09-17 08:00 | 2015-12-11 17:00 | 10% | - | - | - | - | - | -
3 | 610032 | Study on need for Multiple Access Point Names | FS_MAPN | 1 | Rel-14 | S1 | 2013-09-12 08:00 | 2015-03-18 17:00 | 50% | SP-130416 | S1-143308 | Giesecke & Devrient | Ilario.macchi@gi-de.com | SP#65 moved to Rel-14. Completion 12/14=>03/15. Triggered by S1-133134 LS on GSMA Connected Living Programme Request for APN Storage in the SIM | 22.802
4 | 620071 | Study on Multimedia Broadcast Supplement for Public Warning System (PWS) | FS_MBSP | 1 | Rel-14 | S1 | 2013-12-11 08:00 | 2014-12-12 17:00 | 70% | SP-130599 | S1-143312 | Qualcomm | Eddy Hall (edhall@qti.qualcomm.com) | SP#65 completion 09/14=>12/14. Moved to Rel-14. TR 22.815v100 for Information. Study the case where a public safety agency needs to distribute on a large scale timely multimedia public safety information to the public. Linked to Rel-9 Feature PWS | 22.815
5 | 630018 | Study on service aspects for dealing with User Control over spoofed calls | FS_UC_SPOOF | 1 | Rel-14 | S1 | 2014-03-07 08:00 | 2014-12-12 17:00 | 70% | SP-140074 | S1-143314 | Sprint | Gregory.schumacher@sprint.com | SP#65 moved to Rel-14. TR 22.898v100 for Information. Linked to SA3 Rel-11 TR 33.838 PUCI and Rel-12 ongoing study TR 33.831 (FS_SPOOF) | 22.898
6 | 640060 | Study on User Location Reporting Support enhancements | FS_eULRS | 1 | Rel-14 | S1 | 2014-06-19 08:00 | 2015-06-17 17:00 | 30% | SP-140402 | S1-143315 | China Unicom | Zhuoyun Zhang ( zhangzy910@chinaunicom.cn) | SP#65 moved to Rel-14. Linked to Rel-12 SA2 TR 23.843 Study on Core Network Overload solutions (FS_CNO) and Rel-13 Feature Service Exposure and Enablement Support (SEES) | 22.899
7 | 640061 | Study on Control of Applications when Third party Servers encounter difficulties | FS_CATS | 1 | Rel-14 | S1 | 2014-06-19 08:00 | 2015-03-18 17:00 | 30% | SP-140246 | S1-143316 | KDDI | Eriko Yoshida (er-yoshida@kddi.com) | SP#65 completion 12/14=>03/15. Moved to Rel-14. Linked to Rel-13 Feature SEES and Rel-13 TR 22.806 (FS_ACDC) | 22.818
8 | 0 | Release 13 Features | - | 1 | Rel-13 | SP,RP,CP,GP | 2013-09-12 08:00 | 2015-12-25 17:00 | 25% | - | - | - | - | - | -
9 | 611000 | Stage 1 - ONLY Features | - | 1 | Rel-13 | SP | 2013-09-13 08:00 | 2015-12-23 17:00 | 100% | - | - | - | - | - | -
10 | 610030 | Service Exposure and Enablement Support | SEES | 1 | Rel-13 | S1 | 2013-09-12 08:00 | 2014-09-17 17:00 | 100% | SP-130505 | S1-143301 | KPN | toon.norp@tno.nl | SP#62 completion 06/14=>09/14. Linked to Rel-12 Study TR 22.888 (FS_MTCe) and to Features Rel-11 SIMTC & Rel-12 MTCe and MOSAP | Stage 1
11 | 610130 | TR on Stage 1 for Service Exposure and Enablement Support | SEES | 2 | Rel-13 | S1 | 2013-09-12 08:00 | 2014-06-18 17:00 | 100% | SP-130505 | S1-143301 | KPN | toon.norp@tno.nl | SP#64 completed. TR 22.853v200 for Approval. External requirements from oneM2M TR0001(oneM2M Use Case collection), TS0002 (M2M Requirements) | New TR 22.853
12 | 610230 | Stage 1 for Service Exposure and Enablement Support | SEES | 2 | Rel-13 | S1 | 2013-09-12 08:00 | 2014-09-17 17:00 | 100% | SP-130505 | S1-143301 | KPN | toon.norp@tno.nl | SP#65 completed | 22.101, 22.115, 22.368, TBD
13 | 620063 | Service Requirements Maintenance for Machine-Type Communications (MTC) | SRMMTC | 1 | Rel-13 | S1 | 2013-12-13 08:00 | 2014-09-17 17:00 | 100% | SP-130600 | - | KPN | toon.norp@tno.nl | SP#65 completed. Linked to Rel-13 SEES, Rel-12 Support for Interworking with M2M Service Enablement (MTCe-SIMSE), Service Requirement Maintenance (MTCe-SRM). Decide which MTC reqs with no Stage 2 should be removed/maintained in Rel-13. | 22.368
14 | 630015 | Isolated E-UTRAN Operation for Public Safety | IOPS | 1 | Rel-13 | S1 | 2014-03-07 08:00 | 2014-09-17 17:00 | 100% | SP 140232 | S1-143304 | General Dynamics | paul.piggin@gd-broadband.com | SP#65 completed. TS 22.346v100 for 1-step Approval. Triggered by Rel-13 TR 22.897 (FS_IOPS) | New TS 22.346
15 | 640042 | Service Requirements Maintenance for Group Communication System Enablers for LTE | SRM_GCSE_LTE | 1 | Rel-13 | S1 | 2014-06-18 08:00 | 2014-09-17 17:00 | 100% | SP-140228 | S1-143307 | Nokia Networks | Juergen.Merkel@nsn.com | SP#65 completed. Some Rel-12 service reqs have no Stage 2/3 implementation | 22.468
16 | 640044 | Co-ordinated packet data network gateway (P-GW) change for SIPTO | CSIPTO | 1 | Rel-13 | S1 | 2014-06-18 08:00 | 2014-09-16 17:00 | 100% | SP-140509 | S1-143306 | Intel | Eric.siow@intel.com | SP#65 completed. Updated WID SP-140235=>SP-140509. Triggered by Rel-13 Study TR 22.828 (FS_CSIPTO) | 22.101
17 | 640052 | Application specific Congestion control for Data Communication | ACDC | 1 | Rel-13 | S1 | 2014-06-18 08:00 | 2014-09-17 17:00 | 100% | SP-140234 | S1-143305 | NTT DOCOMO | Atsushi Minokuchi (minokuchi@nttdocomo.co.jp) | SP#65 completed. Triggered by Rel-13 Study TR 22.806 | 22.011
18 | 650018 | Enhanced Calling Information Presentation | ECIP | 1 | Rel-13 | S1 | 2014-09-15 08:00 | 2014-09-16 17:00 | 100% | SP-140513 | S1-143311 | China Mobile | LI Xiaofan (lixiaofan@chinamobile.com | SP#65 approved WID & completed. Triggered by Rel-13 TR 22.810. Linked to Multimedia Telephony Service for IMS (UID_7038), Customized Alerting Tone (CAT) UID_370028, Customized Ringing Signal (CRS) UID_380067 | 22.182 (CAT), 22.183 (CRS)
19 | 650019 | Flexible Mobile Service Steering | FMSS | 1 | Rel-13 | S1 | 2014-09-15 08:00 | 2014-09-17 17:00 | 100% | SP-140638 | S1-143310 | China Mobile | Lu Lu (lulu@chinamobile.com) | SP#65 WID approved & completed. Triggered by Rel-13 TR 22.808 (FS_FMSS) | 22.101
20 | 650020 | GERAN UTRAN Sharing Enhancements | GUSH | 1 | Rel-13 | S1 | 2014-09-19 08:00 | 2014-12-12 17:00 | 0% | SP-140637 | SP-140515 | Telefónica | chris.friel@telefonica.com | SP#65 exception in SP-140515. Triggered by TR 22.852 (FS_RSE and FS_GUSH) | 22.101
21 | 620999 | SA1/SA2 Features | - | 1 | Rel-13 | SP,RP,CP,GP | 2013-12-16 08:00 | 2015-12-25 17:00 | 0% | - | - | - | - | - | -
22 | 570029 | User Plane Congestion management | UPCON | 1 | Rel-13 | S1,S2,C3,C4 | 2012-02-02 08:00 | 2015-03-18 17:00 | 68% | SP-140631 | - | KDDI | Eriko Yoshida (er-yoshida@kddi.com) | SP#65 updated WID SP-140153=>SP-140631 (BBII & BBIII stopped). Triggered by Rel-12 TR 22.805 Study on User Plane Congestion management (FS_UPCON) | Stage 1/2/3
23 | 570129 | Stage 1 for User Plane Congestion management | UPCON | 2 | Rel-13 | S1 | 2012-02-02 08:00 | 2013-03-06 17:00 | 100% | SP-140631 | - | KDDI | Eriko Yoshida (er-yoshida@kddi.com) | SP#63 moved to Rel-13 updated WID SP-120890=>SP-140153. SP#59 completed. Convert TR 22.805 clause 6 consolidated requirements to normative requirements in 22.101 | 22.101
24 | 580057 | TR on Stage 2 for User Plane Congestion management | UPCON | 2 | Rel-13 | S2 | 2012-12-12 08:00 | 2015-03-18 17:00 | 87% | SP-140631 | - | Allot | Alla Goldner (agoldner@allot.com) | SP#65 updated WID SP-140153=>SP-140631. TR 23.705v100 for Information | new TR 23.705
25 | 580058 | Deleted - Stage 2 for User Plane Congestion management | UPCON | 2 | Rel-13 | S2 | 2012-12-19 08:00 | 2013-12-11 17:00 | 100% | SP-140631 | - | NEC | andreas.maeder@neclab.eu | SP#62 stopped at 0% completion | TBD
26 | 630019 | BB1: RAN Downlink Traffic Differentiation, Congestion Detection and Reporting | UPCON-DOTCON | 2 | Rel-13 | S2 | 2014-03-07 08:00 | 2015-03-13 17:00 | 17% | SP-140631 | - | Allot | Alla Goldner (agoldner@allot.com) | SP#65 updated WID SP-140153=>SP-140631. Includes: RAN Congestion Detection: , RAN Traffic Differentiation, RAN Congestion Reporting, CN Congestion Mitigation mechanisms, Dynamic Policy Control | -
27 | 630119 | Stage 2 for RAN Downlink Traffic Differentiation, Congestion Detection and Reporting | UPCON-DOTCON | 3 | Rel-13 | S2 | 2014-03-07 08:00 | 2014-12-12 17:00 | 60% | SP-140434 | - | Allot | Alla Goldner (agoldner@allot.com) | SP#65 updated WID SP-140153=>S2-142850 (added impacted specs) | 23.060, 23.203, 23.401
28 | 650007 | CT aspects of User Plane Congestion Management for BB1 | UPCON-DOTCON-CT | 3 | Rel-13 | C3,C4 | 2014-03-18 08:00 | 2015-03-13 17:00 | 0% | CP-140734 | - | Huawei | Xia Haitao (xiahaitao@huawei.com) | Stage 3 | Stage 3
29 | 650107 | CT3 part of CT aspects of User Plane Congestion Management for BB1 | UPCON-DOTCON-CT | 4 | Rel-13 | C3 | 2014-03-18 08:00 | 2015-03-13 17:00 | 0% | CP-140734 | - | Huawei | Xia Haitao (xiahaitao@huawei.com) | - | 29.201, 29.212, 29.213, 29.214, 29.215, 29.219, New TS 29.217 (PCC over Np)
30 | 650207 | CT4 part of CT aspects of User Plane Congestion Management for BB1 | UPCON-DOTCON-CT | 4 | Rel-13 | C4 | 2014-03-18 08:00 | 2015-03-13 17:00 | 0% | CP-140734 | - | Huawei | Xia Haitao (xiahaitao@huawei.com) | - | 23.003, 29.303, New TS 29.405 (UPCON over Nq)
31 | 630020 | Deleted - BB2: Application and Content Prioritization | UPCON-CON | 2 | Rel-13 | S2 | 2014-03-07 08:00 | 2014-09-17 17:00 | 100% | SP-140631 | - | Allot | Alla Goldner (agoldner@allot.com) | SP#65 updated WID SP-140153=>SP-140631 (BBII & BBIII stopped). Includes: Content specific UP prioritization (Video), Application specific UP prioritization | TBD
32 | 630021 | Deleted - BB3: Uplink traffic and attended/unattended traffic | UPCON-TRAF | 2 | Rel-13 | S2 | 2014-03-07 08:00 | 2014-09-17 17:00 | 100% | SP-140631 | - | Allot | Alla Goldner (agoldner@allot.com) | SP#65 updated WID SP-140153=>SP-140631 (BBII & BBIII stopped). Includes: Uplink Congestion Management, Un/Attended UE Information | TBD
33 | 600045 | RAN Sharing Enhancements | RSE | 1 | Rel-13 | S1,R3 | 2013-06-19 08:00 | 2015-06-16 17:00 | 39% | SP-130330 | - | NEC | joerg.swetina@neclab.eu | Triggered by Rel-12 TR 22.852 Study on RAN Sharing Enhancements (FS_RSE) | -
34 | 600145 | Stage 1 for RAN Sharing Enhancements | RSE | 2 | Rel-13 | S1 | 2013-06-19 08:00 | 2013-12-11 17:00 | 100% | SP-130330 | - | NEC | joerg.swetina@neclab.eu | SP#62 completed | 22.101
35 | 650021 | RAN aspects of RAN Sharing Enhancements for LTE | RSE-RAN_LTE | 2 | Rel-13 | R3 | 2014-09-12 08:00 | 2015-06-16 17:00 | 0% | RP-141671 | - | NEC | Siva.Vakeesar@emea.nec.com | Triggered by TR 36.856 Study on RAN aspects of RAN Sharing Enhancements for LTE (FS_RSE-RAN_LTE) & SA1 22.101 Stage 1 | LTE
36 | 650121 | Core part: RAN aspects of RAN Sharing Enhancements for LTE | RSE-RAN_LTE-Core | 3 | Rel-13 | R3 | 2014-09-12 08:00 | 2015-06-16 17:00 | 0% | RP-141671 | - | NEC | Siva.Vakeesar@emea.nec.com | - | 36.300, 36.413, 36.423
37 | 620064 | Mission Critical Push To Talk over LTE | MCPTT | 1 | Rel-13 | S1,S2 | 2013-12-11 08:00 | 2015-06-17 17:00 | 26% | SP-140435 | - | NIST | david.cypher@nist.gov | SP#65 updated WID SP-140276=>SP-140435. Complements Rel-12 FS_ProSe/ProSe and GCSE_LTE. External requirements: FIRSTNET (US), UK Home Office, OMA, TCCA (TETRA and Critical Communications Association) | Stage 1/2
38 | 620164 | Stage 1 for Mission Critical Push To Talk over LTE | MCPTT | 2 | Rel-13 | S1 | 2013-12-11 08:00 | 2014-12-12 17:00 | 75% | SP-140435 | SP-140502 | NIST | david.cypher@nist.gov | SP#65 completion 09/14=>12/14. Exception in SP-140502. TS 22.179v100 for Information. | New TS 22.179
39 | 640142 | TR on Stage 2 for Mission Critical Push To Talk over LTE | MCPTT | 2 | Rel-13 | S2 | 2014-06-18 08:00 | 2015-06-17 17:00 | 2% | SP-140435 | - | U.S. Department of Commerce | Randy Bloomfield (randy@its.bldrdoc.gov) | SP#65 completion 12/14=>06/15. Updated WID SP-140276=>SP-140435 | New TR 23.779
40 | 640042 | Stage 2 for Mission Critical Push To Talk over LTE | MCPTT | 2 | Rel-13 | S2 | 2014-06-23 08:00 | 2015-06-17 17:00 | 0% | SP-140435 | - | U.S. Department of Commerce | Randy Bloomfield (randy@its.bldrdoc.gov) | SP#65 completion 12/14=>06/15. Updated WID SP-140276=>SP-140435 | New TS 23.179
41 | 630014 | Enhancements to WEBRTC interoperability | eWebRTCi | 1 | Rel-13 | S1,S2,S3 | 2014-03-07 08:00 | 2015-06-17 17:00 | 16% | SP-140630 | - | Alcatel-Lucent | betsy.covell@alcatel-lucent.com | SP#65 updated WID SP-14028=>SP-140630 (added SA3 part, SA1 change). Add enhanced interoperability support for WebRTC to Rel-12 Web Real Time Communication (WebRTC) Access to IMS. | Stage 1/2
42 | 630114 | Stage 1 for Enhancements to WEBRTC interoperability | eWebRTCi | 2 | Rel-13 | S1 | 2014-03-07 08:00 | 2014-09-17 17:00 | 100% | SP-140630 | S1-143303 | Alcatel-Lucent | betsy.covell@alcatel-lucent.com | SP#65 completed. Updated WID SP-140286=>SP-140630 | 22.228
43 | 640138 | TR on Stage 2 for Enhancements to WEBRTC interoperability | eWebRTCi | 2 | Rel-13 | S2 | 2014-06-19 08:00 | 2015-03-18 17:00 | 9% | SP-140630 | - | China Mobile | Yu Qing (yuqing@chinamobile.com) | SP#65 updated WID SP-14028=>SP-140630 (added SA3 part) | New TR 23.706
44 | 640038 | Stage 2 for Enhancements to WEBRTC interoperability | eWebRTCi | 2 | Rel-13 | S2 | 2014-06-23 08:00 | 2015-06-17 17:00 | 0% | SP-140630 | - | China Mobile | Yu Qing (yuqing@chinamobile.com) | SP#65 updated WID SP-14028=>SP-140630 (added SA3 part) | 23.228
45 | 650122 | TR on Security for Enhancements to WEBRTC interoperability | eWebRTCi | 2 | Rel-13 | S3 | 2014-09-17 08:00 | 2015-06-16 17:00 | 0% | SP-140630 | - | Ericsson | vesa.lehtovirta@ericsson.com | SP#65 updated WID SP-14028=>SP-140630 (added SA3 part) | New TR 33.8xy
46 | 650022 | Security for Enhancements to WEBRTC interoperability | eWebRTCi | 2 | Rel-13 | S3 | 2014-09-17 08:00 | 2015-06-17 17:00 | 0% | SP-140630 | - | Ericsson | vesa.lehtovirta@ericsson.com | SP#65 updated WID SP-14028=>SP-140630 (added SA3 part) | 33.203, 33.328
47 | 630016 | Improvements to CS/PS coordination in UTRAN/GERAN Shared Networks | CSPS_Coord | 1 | Rel-13 | S2 | 2014-03-07 08:00 | 2014-12-12 17:00 | 41% | SP-140168 | - | Ericsson | roland.gustafsson@ericsson.com | Provide improvements to the solutions for CS/PS coordination in TS 23.251 to ensure that CS/PS coordination can be achieved for all mobility scenarios | Stage 2
48 | 630116 | TR on Stage 2 for Improvements to CS/PS coordination in UTRAN/GERAN Shared Networks | CSPS_Coord | 2 | Rel-13 | S2 | 2014-03-07 08:00 | 2014-09-17 17:00 | 100% | SP-140168 | - | Ericsson | roland.gustafsson@ericsson.com | SP#65 completed. TR 23.704v200 for Approval | New TR 23.704
49 | 630216 | Stage 2 for Improvements to CS/PS coordination in UTRAN/GERAN Shared Networks | CSPS_Coord | 2 | Rel-13 | S2 | 2014-03-12 08:00 | 2014-12-12 17:00 | 0% | SP-140168 | - | Ericsson | roland.gustafsson@ericsson.com | - | 23.216, 23.251, 23.272
50 | 640040 | Enhancements to Proximity-based Services | eProSe | 1 | Rel-13 | S1,S2,S3 | 2014-06-18 08:00 | 2015-09-16 17:00 | 11% | SP-140386 | - | Qualcomm | Eddy Hall (edhall@qti.qualcomm.com) | - | Stage 1/2
51 | 640140 | Stage 1 for Enhancements to Proximity-based Services | eProSe | 2 | Rel-13 | S1 | 2014-06-19 08:00 | 2014-09-17 17:00 | 100% | SP-140386 | - | Qualcomm | Eddy Hall (edhall@qti.qualcomm.com) | SP#65 completed. Some Rel-12 ProSe service requirements have not been implemented at Stage 2/3 level. These are taken up in Rel-13 Stage 2/3 and need Stage 1 appropriate service requirements. No new service requirements are introduced. | 22.115, 22.278
52 | 640041 | Stage 2 for Enhancements to Proximity-based Services - Extensions | eProSe-Ext | 2 | Rel-13 | S2 | 2014-06-23 08:00 | 2015-06-17 17:00 | 0% | SP-140573 | - | Qualcomm | Haris Zisimopoulos (harisz@qti.qualcomm.com) | SP#65 updated WID SP-140385=>SP-140573 (added SA3 part) | 23.303, TBD
53 | 640141 | TR on Stage 2 for Enhancements to Proximity-based Services - Extensions | eProSe-Ext | 2 | Rel-13 | S2 | 2014-06-18 08:00 | 2015-03-13 17:00 | 10% | SP-140573 | - | Qualcomm | Haris Zisimopoulos (harisz@qti.qualcomm.com) | SP#65 updated WID SP-140385=>SP-140573 (added SA3 part) | New TR 23.713
54 | 650023 | Security for Enhancements to Proximity-based Services - Extensions | eProSe-Ext | 2 | Rel-13 | S3 | 2014-09-19 08:00 | 2015-09-16 17:00 | 0% | SP-140573 | - | Qualcomm | Adrian Escott (aescott@qti.qualcomm.com) | SP#65 updated WID SP-140385=>SP-140573 (added SA3 part). Specify selected security solutions based on the outcome of SA3 study TR 33.833 | 33.303
55 | 640045 | voice over E-UTRAN Paging Policy Differentiation | voE_UTRAN_PPD | 1 | Rel-13 | S1,S2,C4,C1,C3 | 2014-06-16 08:00 | 2014-12-12 17:00 | 11% | SP-140394 | - | Alcatel-Lucent | (betsy.covell@alcatel-lucent.com) | - | Stage 1/2
56 | 640145 | Stage 1 for voice over E-UTRAN Paging Policy Differentiation | voE_UTRAN_PPD | 2 | Rel-13 | S1 | 2014-06-16 08:00 | 2014-06-18 17:00 | 100% | SP-140394 | - | Alcatel-Lucent | betsy.covell@alcatel-lucent.com | SP#64 approved WID & completed | 22.228, 22.278
57 | 640245 | Stage 2 for voice over E-UTRAN Paging Policy Differentiation | voE_UTRAN_PPD | 2 | Rel-13 | S2 | 2014-06-18 08:00 | 2014-12-12 17:00 | 25% | SP-140394 | - | Alcatel-Lucent | laurent.thiebaut@alcatel-lucent.com | Architectural enhancements allowing a differentiated paging policy for IMS voice calls over E-UTRAN | 23.228, 23.401
58 | 650003 | CT aspects of voice over E-UTRAN Paging Policy Differentiation | voE_UTRAN_PPD-CT | 2 | Rel-13 | C4,C1,C3 | 2014-09-16 08:00 | 2014-12-09 17:00 | 0% | CP-140491 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | Stage 3 | Stage 3
59 | 650103 | CT4 part of CT aspects of voice over E-UTRAN Paging Policy Differentiation | voE_UTRAN_PPD-CT | 3 | Rel-13 | C4 | 2014-09-16 08:00 | 2014-12-09 17:00 | 0% | CP-140491 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | - | 29.274, 29.281
60 | 650203 | CT1 part of CT aspects of voice over E-UTRAN Paging Policy Differentiation | voE_UTRAN_PPD-CT | 3 | Rel-13 | C1 | 2014-09-16 08:00 | 2014-12-09 17:00 | 0% | CP-140491 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | - | 24.229
61 | 650303 | CT3 part of CT aspects of voice over E-UTRAN Paging Policy Differentiation | voE_UTRAN_PPD-CT | 3 | Rel-13 | C3 | 2014-09-16 08:00 | 2014-12-09 17:00 | 0% | CP-140491 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | - | 29.061
62 | 640046 | Dedicated Core Networks | DECOR | 1 | Rel-13 | S2 | 2014-06-18 08:00 | 2015-03-18 17:00 | 12% | SP-140395 | - | NTT DOCOMO | Daisuke Fujishima (fujishimad@nttdocomo.co.jp) | Enable deployment of dedicated CNs to UEs sharing the same characteristics. The specific dedicated CN that serves a UE is selected based on subscription info and operator config, without requiring UEs to be modified. | Stage 2
63 | 640146 | TR for Dedicated Core Networks | DECOR | 2 | Rel-13 | S2 | 2014-06-18 08:00 | 2014-12-12 17:00 | 30% | SP-140395 | - | NTT DOCOMO | Daisuke Fujishima (fujishimad@nttdocomo.co.jp) | - | New TR 23.707
64 | 640246 | Stage 2 for Dedicated Core Networks | DECOR | 2 | Rel-13 | S2 | 2014-06-23 08:00 | 2015-03-18 17:00 | 0% | SP-140395 | - | NTT DOCOMO | Daisuke Fujishima (fujishimad@nttdocomo.co.jp) | - | 23.060, 23.401
65 | 640047 | IP Flow Mobility support for S2a and S2b Interfaces | NBIFOM | 1 | Rel-13 | S2 | 2014-06-18 08:00 | 2015-06-17 17:00 | 8% | SP-140279 | - | ZTE | Tricci So (tso@zteusa.com) | - | Stage 2
66 | 640147 | TR for IP Flow Mobility support for S2a and S2b Interfaces | NBIFOM | 2 | Rel-13 | S2 | 2014-06-18 08:00 | 2015-03-13 17:00 | 20% | SP-140279 | - | ZTE | Tricci So (tso@zteusa.com) | Revived the Rel-12 DRAFT TR 23.861 stopped at SP#59 (at 40% completion) | New TR 23.861
67 | 640247 | Stage 2 for IP Flow Mobility support for S2a and S2b Interfaces | NBIFOM | 2 | Rel-13 | S2 | 2014-06-23 08:00 | 2015-06-17 17:00 | 0% | SP-140279 | - | ZTE | Tricci So (tso@zteusa.com) | - | 23.402, TBD
68 | 640048 | Architecture Enhancements for Service capability Exposure | AESE | 1 | Rel-13 | S2,S3 | 2014-06-18 08:00 | 2015-09-16 17:00 | 6% | SP-140301 | - | Intel | puneet.jain@intel.com | - | Stage 2
69 | 640148 | TR for Architecture Enhancements for Service capability Exposure | AESE | 2 | Rel-13 | S2 | 2014-06-18 08:00 | 2015-03-18 17:00 | 30% | SP-140301 | - | Intel | puneet.jain@intel.com | - | New TR 23.708
70 | 640248 | Stage 2 for Architecture Enhancements for Service capability Exposure | AESE | 2 | Rel-13 | S2 | 2014-06-23 08:00 | 2015-06-17 17:00 | 0% | SP-140301 | - | Intel | puneet.jain@intel.com | - | TBD
71 | 640348 | TR on Security for Architecture Enhancements for Service capability Exposure | AESE | 2 | Rel-13 | S3 | 2014-06-23 08:00 | 2015-06-17 17:00 | 0% | SP-140301 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | TR 33.8xy will capture requirements, solution alternatives, evaluations and conclusions for the AESE, MONTE and GROUPE WIDs. | New TR 33.889
72 | 640448 | Security for Architecture Enhancements for Service capability Exposure | AESE | 2 | Rel-13 | S3 | 2014-06-23 08:00 | 2015-09-16 17:00 | 0% | SP-140301 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | - | 33.187
73 | 640049 | Monitoring Enhancements | MONTE | 1 | Rel-13 | S2,S3 | 2014-06-18 08:00 | 2015-09-16 17:00 | 6% | SP-140302 | - | Intel | puneet.jain@intel.com | Linked to Rel-13 Feature Architecture Enhancements for Service Exposure (AESE). Although service requirements (TS 22.368 clause 7.2.8) are motivated by MTC, the solution may apply to normal UEs | Stage 2
74 | 640149 | TR for Monitoring Enhancements | MONTE | 2 | Rel-13 | S2 | 2014-09-17 08:00 | 2015-06-17 17:00 | 25% | SP-140302 | - | Intel | puneet.jain@intel.com | - | New TR 23.789
75 | 640249 | Stage 2 for Monitoring Enhancements | MONTE | 2 | Rel-13 | S2 | 2014-06-23 08:00 | 2015-06-17 17:00 | 0% | SP-140302 | - | Intel | puneet.jain@intel.com | - | 23.682, TBD
76 | 640349 | TR on Security for Monitoring Enhancements | MONTE | 2 | Rel-13 | S3 | 2014-06-18 08:00 | 2015-06-12 17:00 | 5% | SP-140302 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | TR 33.8xy will capture requirements, solution alternatives, evaluations and conclusions for the AESE, MONTE and GROUPE WIDs. | New TR 33.889
77 | 640449 | Security for Monitoring Enhancements | MONTE | 2 | Rel-13 | S3 | 2014-06-23 08:00 | 2015-09-16 17:00 | 0% | SP-140302 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | - | 33.187
78 | 640050 | Group based Enhancements | GROUPE | 1 | Rel-13 | S2,S3 | 2014-06-18 08:00 | 2015-09-16 17:00 | 5% | SP-140305 | - | Huawei | ZhangWanqiang@huawei.com | - | Stage 2
79 | 640150 | TR for Group based Enhancements | GROUPE | 2 | Rel-13 | S2 | 2014-06-18 08:00 | 2015-03-18 17:00 | 20% | SP-140305 | - | Huawei | ZhangWanqiang@huawei.com | - | New TR 23.769
80 | 640250 | Stage 2 for Group based Enhancements | GROUPE | 2 | Rel-13 | S2 | 2014-06-23 08:00 | 2015-06-17 17:00 | 0% | SP-140305 | - | Huawei | ZhangWanqiang@huawei.com | - | 23.682, TBD
81 | 640350 | TR on Security for Group based Enhancements | GROUPE | 2 | Rel-13 | S3 | 2014-06-18 08:00 | 2015-06-12 17:00 | 5% | SP-140305 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | TR 33.8xy will capture requirements, solution alternatives, evaluations and conclusions for the AESE, MONTE and GROUPE WIDs. | New TR 33.889
82 | 640450 | Security for Group based Enhancements | GROUPE | 2 | Rel-13 | S3 | 2014-06-23 08:00 | 2015-09-16 17:00 | 0% | SP-140305 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | - | 33.187
83 | 640051 | Enhanced CS Fallback (CSFB) | eCSFB | 1 | Rel-13 | S2,S3 | 2014-06-18 08:00 | 2015-03-13 17:00 | 14% | SP-140579 | - | China Unicom | Yang Xu (xuyang49@chinaunicom.cn) | SP#65 updated ID SP-140285=>SP-140579 (added SA3 part). Linked to Rel-8 WIs Single Radio Voice Call Continuity for 3GPP (SAES-SRVCC) and CS Fallback in EPS (SAES-CSFB) | Stage 2
84 | 640151 | TR for Enhanced CS Fallback (CSFB) | eCSFB | 2 | Rel-13 | S2 | 2014-06-18 08:00 | 2014-12-12 17:00 | 35% | SP-140579 | - | China Unicom | Yang Xu (xuyang49@chinaunicom.cn) | SP#65 updated ID SP-140285=>SP-140579 (added SA3 part) | New TR 23.772
85 | 640251 | Stage 2 for Enhanced CS Fallback (CSFB) | eCSFB | 2 | Rel-13 | S2 | 2014-06-23 08:00 | 2015-03-13 17:00 | 0% | SP-140579 | - | China Unicom | Yang Xu (xuyang49@chinaunicom.cn) | SP#65 updated ID SP-140285=>SP-140579 (added SA3 part) | 23.272
86 | 650024 | Security for Enhanced CS Fallback (CSFB) | eCSFB | 2 | Rel-13 | S3 | 2014-09-17 08:00 | 2014-09-17 17:00 | 0% | SP-140579 | - | China Unicom | Feng Gao (gaofeng149@chinaunicom.cn) | SP#65 updated ID SP-140285=>SP-140579
87 | 640053 | Double Resource Reuse for Multiple Media Sessions | DRuMS | 1 | Rel-13 | S2 | 2014-03-14 08:00 | 2015-03-13 17:00 | 49% | SP-140393 | - | Ericsson | George.Foti@ericsson.com | - | Stage 2
88 | 640153 | Stage 2 for Double Resource Reuse for Multiple Media Sessions | DRuMS | 2 | Rel-13 | S2 | 2014-03-14 08:00 | 2015-03-13 17:00 | 49% | SP-140393 | - | Ericsson | George.Foti@ericsson.com | - | 23.203, 23.228
89 | 650025 | SRVCC Enhancements for Transcoding Avoidance | SETA | 1 | Rel-13 | S2 | 2014-09-19 08:00 | 2015-06-17 17:00 | 0% | SP-140436 | - | Ericsson | George.Foti@ericsson.com | Enhance chances for end-to-end transcoder free operation (TrFo) where possible/ ensure proper CS radio resources are reserved for optimal RAN codec. Address TrFo of EVS codecs during SRVCC that are not covered by Rel-12 | Stage 2
90 | 650125 | TR for SRVCC Enhancements for Transcoding Avoidance | SETA | 2 | Rel-13 | S2 | 2014-09-19 08:00 | 2015-03-13 17:00 | 0% | SP-140436 | - | Ericsson | George.Foti@ericsson.com | - | New TR 23.7xy
91 | 650225 | Stage 2 for SRVCC Enhancements for Transcoding Avoidance | SETA | 2 | Rel-13 | S2 | 2014-09-19 08:00 | 2015-06-17 17:00 | 0% | SP-140436 | - | Ericsson | George.Foti@ericsson.com | - | 23.216, 23.237
92 | 620062 | Security Assurance Specification for 3GPP network products | SCAS | 1 | Rel-13 | S3 | 2013-12-09 08:00 | 2015-03-18 17:00 | 40% | SP-130718 | - | NTT DOCOMO | Alf Zugenmaier (alf.zugenmaier@hm.edu) | Triggered by Rel-12 TR 33.805 Study on Security Assurance Methodology for 3GPP Network Elements (FS_SECAM) | -
93 | 620162 | TR on Pilot development of Security Assurance Specification for MME network product class | SCAS | 2 | Rel-13 | S3 | 2013-12-09 08:00 | 2014-12-12 17:00 | 55% | SP-130718 | - | NTT DOCOMO | Alf Zugenmaier (alf.zugenmaier@hm.edu) | This TR collects input for the new TS 33.116 | New TR 33.806
94 | 620262 | Security Assurance Specification for 3GPP network product classes | SCAS | 2 | Rel-13 | S3 | 2013-12-13 08:00 | 2015-03-18 17:00 | 0% | SP-130718 | - | China Mobile | Judy Zhu (zhuhongru@chinamobile.com) | This TS contains results of the first WID objective | New TS 33.116
95 | 620362 | TR on Security Assurance scheme for 3GPP network products | SCAS | 2 | Rel-13 | S3 | 2013-12-09 08:00 | 2014-12-12 17:00 | 75% | SP-130718 | - | NTT DOCOMO | Alf Zugenmaier (alf.zugenmaier@hm.edu) | This TR contains results of the second WID objective | New TR 33.916
96 | 640056 | Lawful Interception in the 3GPP Rel-13 | LI13 | 1 | Rel-13 | S3 | 2014-06-18 08:00 | 2015-12-04 17:00 | 0% | SP-140578 | - | PIDS, Alcatel-Lucent | Koen Jaspers (k.b.jaspers@minjus.nl), terry.jacobson@alcatel-lucent.com | SP#65 updated WID SP-140400=>SP-140578 | 33.106, 33.107, 33.108
97 | 640058 | Video enhancements by Region-Of-Interest information signalling | ROI | 1 | Rel-13 | S4 | 2014-06-18 08:00 | 2015-06-19 17:00 | 5% | SP-140219 | - | Intel | ozgur.oyman@intel.com | Standardize the signalling of region-of-interest (ROI) information and associated capability negotiation mechanisms for MTSI in TS 26.114 | 26.114
98 | 650026 | TV video profile | TVProf | 1 | Rel-13 | S4 | 2014-09-09 08:00 | 2015-12-16 17:00 | 0% | SP-140481 | - | Orange | gilles.teniou@orange.com | Define a limited set of operation points for TV services enabling a consistent service offering within 3GPP, but also across different Ans including traditional distribution systems. TV video profiles in selected 3GPP MM services: MBMS, PSS, 3GP-DASH. | -
99 | 650126 | TR on TV video profile | TVProf | 2 | Rel-13 | S4 | 2014-09-09 08:00 | 2015-12-16 17:00 | 0% | SP-140481 | - | Orange | gilles.teniou@orange.com | - | New TR 26.9xy
100 | 650226 | Specification on TV video profile | TVProf | 2 | Rel-13 | S4 | 2014-09-09 08:00 | 2015-12-16 17:00 | 0% | SP-140481 | - | Orange | gilles.teniou@orange.com | - | 26.234, 26.244, 26.346, 26.247, New TS 26.xyz
101 | 650027 | Enhanced LTE UE Delay test methods and requirements | E_LTE_UED | 1 | Rel-13 | S4 | 2014-09-09 08:00 | 2015-12-16 17:00 | 0% | SP-140482 | - | Orange | stephane.ragot@orange.com | Enhance LTE UE delay test cases & reqs to support DTX & LTE radio optimizations (SPS, DRX), clock accuracy/behaviour of UEs in presence of clock drift, introduce jitter/loss profile condition, testing under H/O condition, MTSI serv over LTE with EVS codec | 26.131, 26.132
102 | 650028 | Media Handling Aspects of IMS-based Telepresence | IMS_TELEP_S4 | 1 | Rel-13 | S4 | 2014-09-09 08:00 | 2015-12-16 17:00 | 0% | SP-140483 | - | Intel | ozgur.oyman@intel.com | Triggered by Rel-12 IMS-based Telepresence (IMS_TELEP) UID_530042 | -
103 | 650128 | TR on Media Handling Aspects of IMS-based Telepresence | IMS_TELEP_S4 | 2 | Rel-13 | S4 | 2014-09-09 08:00 | 2015-09-16 17:00 | 0% | SP-140483 | - | Intel | ozgur.oyman@intel.com | - | New TR 26.9xy
104 | 650228 | Specification on Media Handling Aspects of IMS-based Telepresence | IMS_TELEP_S4 | 2 | Rel-13 | S4 | 2014-09-09 08:00 | 2015-12-16 17:00 | 0% | SP-140483 | - | Intel | ozgur.oyman@intel.com | - | New TS 26.1xy
105 | 650029 | HTML5 Presentation Layer | HTML5 | 1 | Rel-13 | S4 | 2014-09-09 08:00 | 2015-12-16 17:00 | 0% | SP-140484 | - | Samsung | Imed Bouazizi (i.bouazizi@samsung.com) | Triggered by Rel-12 TR 26.907 (Study of HTML5 and 3GPP User Services). Replace the scene description solutions in the 3GPP services: MBMS, PSS, MMS, and DASH. No impact on service requirements or architecture. | 26.140, 26.234, 26.247, 26.346, New TS 26.xyz
106 | 650030 | Support of EVS in 3G Circuit-Switched networks | EVSoCS | 1 | Rel-13 | S4 | 2014-09-09 08:00 | 2015-12-16 17:00 | 0% | SP-140485 | - | Qualcomm | Imre Varga (ivarga@qti.qualcomm.com) | Provide CS support of EVS to enhance voice quality in CS services over UTRAN (3G WCDMA). | 26.103, 28.062, New TS 26.xyz (EVS; Speech Codec Frame Structure), New TS 26.xyw (EVS; Interface to Iu, Uu and Nb)
107 | 650031 | Enhanced DASH (Dynamic Adaptive Streaming over HTTP in 3GPP) | eDASH | 1 | Rel-13 | S4 | 2014-09-09 08:00 | 2015-12-16 17:00 | 0% | SP-140486 | - | Qualcomm, Huawei | Thomas Stockhammer (tsto@qti.qualcomm.com), Li Zhiming (lizhiming@huawei.com) | Triggered by Rel-12 TR 26.938 Study on Improved Support for Dynamic Adaptive Streaming over HTTP in 3GPP (FS_IS_DASH) | 26.233, 26.234, 26.244, 26.247, 26.938
108 | 650032 | QoS End-to-end Multimedia Telephony Service for IMS (MTSI) extensions (Stage 3) | QOSE2EMTSI | 1 | Rel-13 | S4,C3,C1,C4 | 2013-03-06 08:00 | 2015-06-19 17:00 | 35% | SP-140601 | - | Ericsson | tomas.frankkila@ericsson.com | SP#65 updated WID SP-130670=>SP-140601 (moved work from Rel-12 incl. new TR to Rel-13). Co-ordinate with SA2, CT1/3/4, IETF MMUSIC. Linked to SA4 Rel-7 Media handling and interaction in MTSI (MTSI-MHI) UID_7040 | -
109 | 620068 | TR on improved end-to-end QoS handling for MTSI | QOSE2EMTSI | 2 | Rel-13 | S4 | 2013-12-11 08:00 | 2015-06-19 17:00 | 70% | SP-140601 | - | Ericsson | tomas.frankkila@ericsson.com | SP#65 updated WID SP-130670=>SP-140601 (moved work from Rel12 incl. new TR to Rel-13). Completion 03/15=>06/15 | new TR 26.924
110 | 650132 | SA4 part of QoS End-to-end Multimedia Telephony Service for IMS (MTSI) extensions (Stage 3) | QOSE2EMTSI | 2 | Rel-13 | S4 | 2013-03-06 08:00 | 2015-06-19 17:00 | 70% | SP-140601 | - | Ericsson | tomas.frankkila@ericsson.com | SP#65 updated WID SP-130670=>SP-140601 (moved work from Rel12 incl. new TR to Rel-13). Completion 03/15=>06/15. Stage 1 in TS 22.173. No impact on service reqs or architecture | 26.114
111 | 600007 | CT aspects of End-to-End Multimedia Telephony Service for IMS (MTSI) extensions | E2EMTSI-CT | 2 | Rel-13 | C3,C1,C4 | 2013-06-21 08:00 | 2014-09-12 17:00 | 0% | CP-130397 | - | Ericsson | susana.fernandez@ericsson.com | Stage 2/3 | Stage 2/3
112 | 600107 | CT3 part of CT aspects of End-to-End Multimedia Telephony Service for IMS (MTSI) extensions | E2EMTSI-CT | 3 | Rel-13 | C3 | 2013-06-21 08:00 | 2014-09-12 17:00 | 0% | CP-130397 | - | Ericsson | susana.fernandez@ericsson.com | - | 29.162, 29.163, 29.213, 29.214
113 | 600207 | CT1 part of CT aspects of End-to-End Multimedia Telephony Service for IMS (MTSI) extensions | E2EMTSI-CT | 3 | Rel-13 | C1 | 2013-06-21 08:00 | 2014-09-12 17:00 | 0% | CP-130397 | - | Ericsson | susana.fernandez@ericsson.com | CP#64 completion 06/14=>09/14 | 24.229
114 | 600307 | CT4 part of CT aspects of End-to-End Multimedia Telephony Service for IMS (MTSI) extensions | E2EMTSI-CT | 3 | Rel-13 | C4 | 2013-06-21 08:00 | 2014-09-12 17:00 | 0% | CP-130397 | - | Ericsson | susana.fernandez@ericsson.com | CP#64 completion 06/14=>09/14 | 23.333, 23.334, 29.238, 29.332, 29.333, 29.334
115 | 630010 | Rel-13 Operations, Administration, Maintenance and Provisioning (OAM&P) | OAM13 | 1 | Rel-13 | S5 | 2012-06-20 08:00 | 2015-12-11 17:00 | 28% | - | - | - | - | OAM13 is an umbrella Feature for changes that are not part of any other dedicated feature/WI | -
116 | 560132 | Enhanced Network Management (NM) centralized Coverage and Capacity Optimization | SON-NM-CCO | 2 | Rel-13 | S5 | 2014-09-19 08:00 | 2015-06-12 17:00 | 0% | SP-140060 | - | Ericsson | robert.petersen@ericsson.com | SP#64 work not started. SP#63 split of Rel-12 SP-130045 WID (Enhanced NM Centralized Coverage and Capacity Optimization) into a Rel-12 Study (SP-140028) and a Rel-13 Normative WID (SP-140060) | 28.627, 28.628, 32.103, 32.422, 32.425, 32.442
117 | 560034 | Compliance of 3GPP SA5 specifications to the NGMN Top Operational Efficiency (OPE) Recommendations | OAM-NGMN_OPE | 2 | Rel-13 | S5 | 2012-06-20 08:00 | 2015-03-18 17:00 | 61% | SP-140538 | - | Huawei | christian.toche@huawei.com | SP#65 updated WID SP-120349=>SP-140538. Completion 12/14=>03/15. Moved to Rel-13. Source of external requirements: NGMN Top OPE Recommendations 1.0 | -
118 | 560134 | TR on Compliance of 3GPP SA5 specifications to the NGMN Top Operational Efficiency (OPE) Recommendations | OAM-NGMN_OPE | 3 | Rel-13 | S5 | 2012-06-20 08:00 | 2015-03-18 17:00 | 72% | SP-140538 | - | Huawei | christian.toche@huawei.com | SP#65 updated WID SP-120349=>SP-140538. Completion 12/14=>03/15. Moved to Rel-13.. SP#64 TR 32.838v100 for Information | New TR 32.838
119 | 560234 | TS work on Compliance of 3GPP SA5 specifications to the NGMN Top Operational Efficiency (OPE) Recommendations | OAM-NGMN_OPE | 3 | Rel-13 | S5 | 2012-06-25 08:00 | 2015-03-18 17:00 | 50% | SP-140538 | - | Huawei | christian.toche@huawei.com | SP#65 updated WID SP-120349=>SP-140538. Completion 12/14=>03/15. Moved to Rel-13 | 32.101/2/3,32.111-1,32.111-2,32.111-6,32.15x,32.401,32.411,32.412,32.421,32.422,32.423,32.431,32.432,32.436,32.441,32.442,32.446,32.500,32.501,32.502,32.506,32.521,32.522,32.526,32.531,32.532,32.536,32.551,32.691,32.692,32.696,32.762
120 | 560235 | Converged management Performance Management Interface Definitions | OAM-PMID | 2 | Rel-13 | S5 | 2012-06-20 08:00 | 2015-12-11 17:00 | 20% | SP-140613 | - | Huawei | christian.toche@huawei.com | SP#65 updated WID SP-130641=>SP-140613. Completion 09/14=>12/15. Moved to Rel-13. Completion 09/14=>12/15. Moved out of Rel-12 Compliance of 3GPP SA5 specifications to the NGMN NGCOR | new TSs (32.PM1, 32.PM6, 32.PM7)
121 | 560036 | WLAN Management | WLAN-OAM | 2 | Rel-13 | S5 | 2012-06-27 08:00 | 2015-06-17 17:00 | 7% | SP-140535 | - | Intel | joey.chou@intel.com | SP#65 moved to Rel-13. Updated WID SP-130042=>SP-140535 (split into Rel-12 Study & Rel-13 normative WI). TR 32.841 was completed as a Rel-12 Study and has triggered this normative work | -
122 | 560136 | WLAN Network Resource Model for Type-2 interface | WLAN-OAM | 3 | Rel-13 | S5 | 2012-06-27 08:00 | 2015-06-17 17:00 | 10% | SP-140535 | - | Intel | joey.chou@intel.com | SP#65 updated WID SP-130042=>SP-140535. Completion 09/14=>06/15. Moved to Rel-13 | new TS (28.680, 28.682)
123 | 560236 | WLAN measurements defined in IEEE and IETF WLAN performance measurements for use on Type-2 interface | WLAN-OAM | 3 | Rel-13 | S5 | 2012-06-27 08:00 | 2015-06-17 17:00 | 5% | SP-140535 | - | Intel | joey.chou@intel.com | SP#65 updated WID SP-130042=>SP-140535. Completion 09/14=>06/15. Moved to Rel-13 | new TS 28.403
124 | 600044 | Energy Efficiency related Performance Measurements | OAM-PM_EE | 2 | Rel-13 | S5 | 2013-06-21 08:00 | 2015-06-17 17:00 | 25% | SP-140612 | - | Nokia Networks | Yizhi.yao@nsn.com | SP#65 updated WID SP-130263=>SP-140612. Completion 09/14=>06/15. Moved to Rel-13 | 32.425
125 | 641000 | Rel-13 Charging | CH13 | 1 | Rel-13 | S5 | 2014-06-19 08:00 | 2015-12-16 17:00 | 4% | - | - | - | - | CH13 is an umbrella Feature for changes that are not part of any other dedicated feature/WI | -
126 | 640059 | Inter-PLMN PS domain online charging | iPLMN-PS-OCH | 2 | Rel-13 | S5 | 2014-06-19 08:00 | 2015-12-16 17:00 | 4% | SP-140324 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | Study and specify Gy Reference Point “service data flows based online charging” for inter-PLMN situations | Stage 2/3
127 | 640159 | TR on Inter-PLMN PS domain online charging | iPLMN-PS-OCH | 3 | Rel-13 | S5 | 2014-06-19 08:00 | 2015-06-17 17:00 | 10% | SP-140324 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | - | New TR 32.843
128 | 640259 | Specification of Inter-PLMN PS domain online charging | iPLMN-PS-OCH | 3 | Rel-13 | S5 | 2014-06-23 08:00 | 2015-12-16 17:00 | 0% | SP-140324 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | - | 32.251, 32.299
129 | 610005 | Support of Real-time Transport Protocol (RTP) / Real-time Transport Control Protocol (RTCP) multiplexing (signalling) in IMS | RTCP_MUX | 1 | Rel-13 | C4,C1,C3 | 2013-09-09 08:00 | 2015-12-11 17:00 | 3% | CP-130436 | - | Alcatel-Lucent | Albrecht.Schwarz@alcatel-lucent.com | CP#65 moved to Rel-13. Stage 2/3 | Stage 2/3
130 | 610105 | CT4 part of Support of RTP / RTCP multiplexing (signalling) in IMS | RTCP_MUX | 2 | Rel-13 | C4 | 2013-09-09 08:00 | 2015-12-11 17:00 | 10% | CP-130436 | - | Alcatel-Lucent | Albrecht.Schwarz@alcatel-lucent.com | CP#65 moved to Rel-13. Completion 09/14=>12/15 | 23.334, 29.334
131 | 610205 | CT1 part of Support of RTP / RTCP multiplexing (signalling) in IMS | RTCP_MUX | 2 | Rel-13 | C1 | 2013-09-13 08:00 | 2015-12-11 17:00 | 0% | CP-130436 | - | Alcatel-Lucent | Albrecht.Schwarz@alcatel-lucent.com | CP#65 moved to Rel-13. Completion 09/14=>12/15 | 24.229
132 | 610305 | CT3 part of Support of RTP / RTCP multiplexing (signalling) in IMS | RTCP_MUX | 2 | Rel-13 | C3 | 2013-09-13 08:00 | 2015-12-11 17:00 | 0% | CP-130436 | - | Alcatel-Lucent | Albrecht.Schwarz@alcatel-lucent.com | CP#65 moved to Rel-13. Completion 09/14=>12/15 | 29.213, 29.214
133 | 550017 | LTE in the 1670-1675 MHz Band for US (on hold till 12/2014) | LTE_FDD_1670_US | 1 | Rel-13 | R4,R2,R3 | 2012-03-05 08:00 | 2015-06-12 17:00 | 8% | RP-121397 | - | LightSquared | masoud.olfat@lightsquared.com | RP#65 FS_LTE_FDD_1670_US is extended to 12/14 and this WI (LTE_FDD_1670_US) is on hold till 12/14 | LTE
134 | 550117 | Core part: LTE in the 1670-1675 MHz Band for US (on hold till 12/2014) | LTE_FDD_1670_US-Core | 2 | Rel-13 | R4,R2,R3 | 2013-08-06 14:12 | 2015-03-13 17:00 | 15% | RP-121397 | RP-141452 | LightSquared | masoud.olfat@lightsquared.com | RP#65 completion 03/15=>06/15. On hold till 12/2014 | 25.101, 25.104, 25.113, 25.133, 25.306, 25.307, 25.331, 25.461, 25.466, 34.124, 36.101, 36.104, 36.113, 36.124, 36.133, 36.307, new TR 36.832
135 | 550217 | Perf. Part: LTE in the 1670-1675 MHz Band for US (on hold till 12/2014) | LTE_FDD_1670_US-Perf | 2 | Rel-13 | R4 | 2012-03-05 08:00 | 2015-06-12 17:00 | 5% | RP-121397 | RP-141452 | LightSquared | masoud.olfat@lightsquared.com | RP#65 completion 06/15=>09/15. . On hold till 12/2014 | 25.133, 25.306, 25.307, 25.331, 25.461, 25.466, 34.124, 36.113, 36.124, 36.133, 36.141, 36.307
136 | 640019 | Enhanced Signalling for Inter-eNB Coordinated Multi-Point (CoMP) for LTE | COMP_LTE_IeNB_sig | 1 | Rel-13 | R3 | 2014-06-18 08:00 | 2014-12-11 17:00 | 0% | RP-141032 | - | Samsung | sunghwan.won@samsung.com | Triggered by TR 36.874 Study on Coordinated Multi-Point (CoMP) operation for LTE with Non-Ideal Backhaul (UID_600015) | LTE
137 | 640119 | Core part: Enhanced Signalling for Inter-eNB Coordinated Multi-Point (CoMP) for LTE | COMP_LTE_IeNB_sig-Core | 2 | Rel-13 | R3 | 2014-06-18 08:00 | 2014-12-11 17:00 | 0% | RP-141032 | - | Samsung | sunghwan.won@samsung.com | - | 36.300, 36.423
138 | 640036 | 2GHz FDD LTE in Region 1 (1980-2010MHz and 2170-2200MHz Bands) | LTE_1980_2170_REG1 | 1 | Rel-13 | R4 | 2014-06-17 08:00 | 2015-06-12 17:00 | 2% | RP-141710 | - | DISH Network | johny.kim@dish.com, mariam.sorond@dish.com | Triggered by TR 37.846 Study on 2GHz FDD for UTRA and LTE in Region 1 (1980-2010MHz and 2170-2200MHz Bands) FS_UTRA_LTE_1980_2170_REG1 | LTE
139 | 640136 | Core part: 2GHz FDD LTE in Region 1 (1980-2010MHz and 2170-2200MHz Bands) | LTE_1980_2170_REG1-Core | 2 | Rel-13 | R4 | 2014-06-17 08:00 | 2015-06-12 17:00 | 5% | RP-141710 | RP-141627 | DISH Network | johny.kim@dish.com, mariam.sorond@dish.com | RP#65 updated WID RP-141009=>RP-141710 | 36.101, 36.104, 36.133, 36.141, 36.307, generic TR 36.853 (3 Band CA with 1UL), New TR 36.862 (Technical Report for 2 GHz Band in Region 1)
140 | 640236 | Perf. Part: 2GHz FDD LTE in Region 1 (1980-2010MHz and 2170-2200MHz Bands) | LTE_1980_2170_REG1-Perf | 2 | Rel-13 | R4 | 2014-06-18 08:00 | 2015-06-12 17:00 | 0% | RP-141710 | RP-141627 | DISH Network | johny.kim@dish.com, mariam.sorond@dish.com | - | 36.101, 36.104, 36.133, 36.141, 36.307, 36.862
141 | 650033 | Further LTE Physical Layer Enhancements for MTC | LTE_MTCe2_L1 | 1 | Rel-13 | R1,R4,R2 | 2014-09-12 08:00 | 2016-06-16 17:00 | 0% | RP-141660 | - | Ericsson | johan.bergman@ericsson.com | Triggered by Rel-12 TR 36.888 Study on Provision of low-cost MTC UEs based on LTE (FS_LC_MTC_LTE) and Low cost & enhanced coverage MTC UE for LTE (LC_MTC_UE) | LTE
142 | 650133 | Core part: Further LTE Physical Layer Enhancements for MTC | LTE_MTCe2_L1-Core | 2 | Rel-13 | R1,R2,R4 | 2014-09-12 08:00 | 2015-02-09 17:00 | 0% | RP-141660 | - | Ericsson | johan.bergman@ericsson.com | - | 36.101, 36.104, 36.133, 36.201, 36.211, 36.212, 36.213, 36.214, 36.300, 36.302, 36.306, 36.321, 36.331
143 | 650233 | Perf. Part: Further LTE Physical Layer Enhancements for MTC | LTE_MTCe2_L1-Perf | 2 | Rel-13 | R4 | 2014-09-12 08:00 | 2016-06-16 17:00 | 0% | RP-141660 | - | Ericsson | johan.bergman@ericsson.com | - | 36.101, 36.104, 36.133
144 | 650034 | Self Organizing Networks (SON) for Active Antenna System (AAS) based deployments | UTRA_LTE_SON_AAS | 1 | Rel-13 | R3,G2 | 2014-09-12 08:00 | 2015-06-16 17:00 | 0% | RP-141624 | - | Nokia Networks | krzysztof.kordybach@nsn.com | Triggered by TR 37.822 Study on Next-Generation SON for UTRA and LTE (FS_UTRA_LTE_NG_SON) | LTE
145 | 650134 | Core part: Self Organizing Networks (SON) for Active Antenna System (AAS) based deployments | UTRA_LTE_SON_AAS-Core | 2 | Rel-13 | R3 | 2014-09-12 08:00 | 2015-06-16 17:00 | 0% | RP-141624 | - | Nokia Networks | krzysztof.kordybach@nsn.com | - | 36.300, 36.423, 36.413, 25.413
146 | 621000 | Rel-13 LTE Carrier Aggregation | LTE_CA_Rel-13 | 1 | Rel-13 | R4 | 2013-12-09 08:00 | 2015-12-11 17:00 | 13% | - | - | - | - | LTE_CA_Rel-13
147 | 620023 | LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 27 | LTE_CA_B8_B27 | 2 | Rel-13 | R4 | 2013-12-09 08:00 | 2015-06-18 17:00 | 10% | RP-140120 | - | KT | ilwhan.kim@kt.com | Inter-band CA 2DL/1UL | LTE
148 | 620123 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 27 | LTE_CA_B8_B27-Core | 3 | Rel-13 | R4 | 2013-12-09 08:00 | 2015-06-18 17:00 | 10% | RP-140120 | RP-141084 | KT | ilwhan.kim@kt.com | RP#65 completion 12/14=>06/15 | 36.101, 36.104, 36.133, generic TR 36.851
149 | 620223 | Perf. part: LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 27 | LTE_CA_B8_B27-Perf | 3 | Rel-13 | R4 | 2013-12-09 08:00 | 2015-06-18 17:00 | 10% | RP-140120 | RP-141084 | KT | ilwhan.kim@kt.com | RP#65 completion 12/14=>06/15 | 36.141, 36.307
150 | 620032 | LTE Advanced 3 band Carrier Aggregation (3DL/1UL) for Band 3, Band 8 and Band 27 | LTE_CA_B3_B8_B27 | 2 | Rel-13 | R4 | 2013-12-09 08:00 | 2015-06-18 17:00 | 25% | RP-131754 | - | KT | Chungwoo HWANG (cwhwang@kt.com) | Inter-band CA 3DL | LTE
151 | 620132 | Core part: LTE Advanced 3 band Carrier Aggregation (3DL/1UL) for Band 3, Band 8 and Band 27 | LTE_CA_B3_B8_B27-Core | 3 | Rel-13 | R4 | 2013-12-09 08:00 | 2015-06-18 17:00 | 25% | RP-131754 | RP-141084 | KT | Chungwoo HWANG (cwhwang@kt.com) | RP#65 completion 12/14=>06/15 | 36.101, 36.104, 36.133, 36.141, 36.307, new generic TR 36.853 (3 Band CA with 1UL)
152 | 620232 | Perf. part: LTE Advanced 3 band Carrier Aggregation (3DL/1UL) for Band 3, Band 8 and Band 27 | LTE_CA_B3_B8_B27-Perf | 3 | Rel-13 | R4 | 2013-12-09 08:00 | 2015-06-18 17:00 | 25% | RP-131754 | RP-141084 | KT | Chungwoo HWANG (cwhwang@kt.com) | RP#65 completion 12/14=>06/15 | 36.101, 36.104, 36.133, 36.141, 36.307
153 | 630033 | LTE Advanced inter-band Carrier Aggregation of Band 7 and Band 22 | LTE_CA_B7_B22 | 2 | Rel-13 | R4 | 2014-03-06 08:00 | 2014-12-11 17:00 | 5% | RP-140094 | - | Orange, Ericsson | erika.tejedor@ericsson.com | Inter-band CA 2DL | LTE
154 | 630133 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 7 and Band 22 | LTE_CA_B7_B22-Core | 3 | Rel-13 | R4 | 2014-03-06 08:00 | 2014-12-11 17:00 | 10% | RP-140094 | RP-141084 | Orange, Ericsson | erika.tejedor@ericsson.com | - | 36.101, 36.104, 36.133, generic TR 36.851 (2 Band CA with 1UL),
155 | 630233 | Perf. part: LTE Advanced inter-band Carrier Aggregation of Band 7 and Band 22 | LTE_CA_B7_B22-Perf | 3 | Rel-13 | R4 | 2014-03-11 08:00 | 2014-12-11 17:00 | 0% | RP-140094 | RP-141084 | Orange, Ericsson | erika.tejedor@ericsson.com | - | 36.141, 36.307
156 | 630034 | LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 13 | LTE_CA_B5_B13 | 2 | Rel-13 | R4 | 2014-03-06 08:00 | 2015-03-12 | 30% | RP-140169 | - | Intel | xinrong.wang@intel.com | Inter-band CA 2DL | LTE
157 | 630134 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 13 | LTE_CA_B5_B13-Core | 3 | Rel-13 | R4 | 2014-03-06 08:00 | 2015-03-12 | 50% | RP-140169 | RP-141084 | Intel | xinrong.wang@intel.com | RP#65 completion 12/14=>03/15 | 36.101, 36.104, 36.133, generic TR 36.851 (2 Band CA with 1UL)
158 | 630234 | Perf. part: LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 13 | LTE_CA_B5_B13-Perf | 3 | Rel-13 | R4 | 2014-03-06 08:00 | 2015-03-12 | 10% | RP-140169 | RP-141084 | Intel | xinrong.wang@intel.com | RP#65 completion 12/14=>03/15 | 36.101, 36.133, 36.141, 36.307
159 | 630039 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 2 and Band 5 | LTE_CA_B2_B2_B5 | 2 | Rel-13 | R4 | 2014-03-06 08:00 | 2015-03-12 | 50% | RP-140165 | - | Intel | peiling.zhang@intel.com | Inter-band CA 3DL | LTE
160 | 630139 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 2 and Band 5 | LTE_CA_B2_B2_B5-Core | 3 | Rel-13 | R4 | 2014-03-06 08:00 | 2015-03-12 | 90% | RP-140165 | RP-141084 | Intel | peiling.zhang@intel.com | RP#65 completion 12/14=>03/15 | 36.101, 36.104, 36.133, generic TR 36.853 (3 Band CA with 1UL)
161 | 630239 | Perf. part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 2 and Band 5 | LTE_CA_B2_B2_B5-Perf | 3 | Rel-13 | R4 | 2014-03-06 08:00 | 2015-03-12 | 10% | RP-140165 | RP-141084 | Intel | peiling.zhang@intel.com | RP#65 completion 12/14=>03/15 | 36.101, 36.133, 36.141, 36.307
162 | 630040 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 5 | LTE_CA_B4_B4_B5 | 2 | Rel-13 | R4 | 2014-03-06 08:00 | 2015-03-12 | 50% | RP-140166 | - | Intel | peiling.zhang@intel.com | Inter-band CA 3DL | LTE
163 | 630140 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 5 | LTE_CA_B4_B4_B5-Core | 3 | Rel-13 | R4 | 2014-03-06 08:00 | 2015-03-12 | 90% | RP-140166 | RP-141084 | Intel | peiling.zhang@intel.com | RP#65 completion 12/14=>03/15 | 36.101, 36.104, 36.133, generic TR 36.853 (3 Band CA with 1UL)
164 | 630240 | Perf. part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 5 | LTE_CA_B4_B4_B5-Perf | 3 | Rel-13 | R4 | 2014-03-06 08:00 | 2015-03-12 | 10% | RP-140166 | RP-141084 | Intel | peiling.zhang@intel.com | RP#65 completion 12/14=>03/15 | 36.101, 36.133, 36.141, 36.307
165 | 630041 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 5 and Band 13 | LTE_CA_B2_B5_B13 | 2 | Rel-13 | R4 | 2014-03-06 08:00 | 2015-03-12 | 30% | RP-140167 | - | Intel | xinrong.wang@intel.com | Inter-band CA 3DL | LTE
166 | 630141 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 5 and Band 13 | LTE_CA_B2_B5_B13-Core | 3 | Rel-13 | R4 | 2014-03-06 08:00 | 2015-03-12 | 50% | RP-140167 | RP-141084 | Intel | xinrong.wang@intel.com | RP#65 completion 12/14=>03/15 | 36.101, 36.104, 36.133, generic TR 36.853 (3 Band CA with 1UL)
167 | 630241 | Perf. part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 5 and Band 13 | LTE_CA_B2_B5_B13-Perf | 3 | Rel-13 | R4 | 2014-03-06 08:00 | 2015-03-12 | 10% | RP-140167 | RP-141084 | Intel | xinrong.wang@intel.com | RP#65 completion 12/14=>03/15 | 36.101, 36.133, 36.141, 36.307
168 | 630042 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 5 and Band 13 | LTE_CA_B4_B5_B13 | 2 | Rel-13 | R4 | 2014-03-06 08:00 | 2015-03-12 | 30% | RP-140168 | - | Intel | xinrong.wang@intel.com | Inter-band CA 3DL | LTE
169 | 630142 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 5 and Band 13 | LTE_CA_B4_B5_B13-Core | 3 | Rel-13 | R4 | 2014-03-06 08:00 | 2015-03-12 | 50% | RP-140168 | RP-141084 | Intel | xinrong.wang@intel.com | RP#65 completion 12/14=>03/15 | 36.101, 36.104, 36.133, generic TR 36.853 (3 Band CA with 1UL)
170 | 630242 | Perf. part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 5 and Band 13 | LTE_CA_B4_B5_B13-Perf | 3 | Rel-13 | R4 | 2014-03-06 08:00 | 2015-03-12 | 10% | RP-140168 | RP-141084 | Intel | xinrong.wang@intel.com | RP#65 completion 12/14=>03/15 | 36.101, 36.133, 36.141, 36.307
171 | 630043 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 26 | LTE_CA_B1_B3_B26 | 2 | Rel-13 | R4 | 2014-03-06 08:00 | 2014-12-11 17:00 | 90% | RP-140194 | - | China Telecom | Zhao Dong (zhaodong@ctbri.com.cn) | Inter-band CA 3DL | LTE
172 | 630143 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 26 | LTE_CA_B1_B3_B26-Core | 3 | Rel-13 | R4 | 2014-03-06 08:00 | 2014-12-11 17:00 | 90% | RP-140194 | RP-141084 | China Telecom | Zhao Dong (zhaodong@ctbri.com.cn) | - | 36.101, 36.104, 36.133, generic TR 36.853 (3 Band CA with 1UL)
173 | 630243 | Perf. part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 26 | LTE_CA_B1_B3_B26-Perf | 3 | Rel-13 | R4 | 2014-03-06 08:00 | 2014-12-11 17:00 | 90% | RP-140194 | RP-141084 | China Telecom | Zhao Dong (zhaodong@ctbri.com.cn) | - | 36.141, 36.307
174 | 630044 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 18 and Band 28 | LTE_CA_B1_B18_B28 | 2 | Rel-13 | R4 | 2014-03-06 08:00 | 2015-03-13 17:00 | 25% | RP-141610 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | Inter-band CA 3DL | LTE
175 | 630144 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 18 and Band 28 | LTE_CA_B1_B18_B28-Core | 3 | Rel-13 | R4 | 2014-03-06 08:00 | 2015-03-13 17:00 | 50% | RP-141610 | RP-141084 | KDDI | Masaaki Obara (ms-obara@kddi.com) | RP#65 updated WID RP-140451=>RP-141610 (take out B18_B28 for Rel-12 from this Rel-13 B1_B18_B28) | 36.101, 36.104, 36.133, generic TR 36.853 (3 Band CA with 1UL)
176 | 630244 | Perf. part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 18 and Band 28 | LTE_CA_B1_B18_B28-Perf | 3 | Rel-13 | R4 | 2014-03-11 08:00 | 2015-03-13 17:00 | 0% | RP-141610 | RP-141084 | KDDI | Masaaki Obara (ms-obara@kddi.com) | - | 36.141, 36.307
177 | 640022 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 2 and Band 12 | LTE_CA_B2_B2_B12 | 2 | Rel-13 | R4 | 2014-06-18 08:00 | 2015-06-18 17:00 | 0% | RP-141232 | - | U.S. Cellular | sebastian.thalanany@uscellular.com | Inter-band CA 3DL/1UL | LTE
178 | 640122 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 2 and Band 12 | LTE_CA_B2_B2_B12-Core | 3 | Rel-13 | R4 | 2014-06-18 08:00 | 2015-03-12 17:00 | 0% | RP-141232 | RP-141084 | U.S. Cellular | sebastian.thalanany@uscellular.com | RP#65 updated WID RP-140647=>RP-141232. Remove Rel-12 generic TR 36.853 (3 Band CA with 1UL) & replace with the NEW Rel-13 generic TR36.8xy (3 Band CA with 1UL). Completion 12/14=>03/15 | 36.101, 36.104, 36.133, 36.141, 36.307, generic new Rel-13 TR36.8xy [similar to Rel-12 TR 36.853 (3 Band CA with 1UL)]
179 | 640222 | Perf. Part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 2 and Band 12 | LTE_CA_B2_B2_B12-Perf | 3 | Rel-13 | R4 | 2014-06-18 08:00 | 2015-06-18 17:00 | 0% | RP-141232 | RP-141084 | U.S. Cellular | sebastian.thalanany@uscellular.com | RP#65 updated WID RP-140647=>RP-141232. Completion 03/15=>06/15 | 36.101, 36.104, 36.133, 36.141, 36.307
180 | 640023 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 7 and Band 12 | LTE_CA_B4_B7_B12 | 2 | Rel-13 | R4 | 2014-06-18 08:00 | 2015-03-12 | 0% | RP-140661 | - | Rogers Wireless | pavlo.nebesny@rci.rogers.com | Inter-band CA 3DL/1UL | LTE
181 | 640123 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 7 and Band 12 | LTE_CA_B4_B7_B12-Core | 3 | Rel-13 | R4 | 2014-06-18 08:00 | 2015-03-12 | 0% | RP-140661 | RP-141084 | Rogers Wireless | pavlo.nebesny@rci.rogers.com | - | 36.101, 36.104, 36.133, 36.307, generic TR 36.851 (2 Band CA with 1UL), generic TR 36.853 (3 Band CA with 1UL)
182 | 640223 | Perf. Part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 7 and Band 12 | LTE_CA_B4_B7_B12-Perf | 3 | Rel-13 | R4 | 2014-06-18 08:00 | 2015-03-12 | 0% | RP-140661 | RP-141084 | Rogers Wireless | pavlo.nebesny@rci.rogers.com | - | 36.133, 36.141
183 | 640024 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 7 | LTE_CA_B4_B4_B7 | 2 | Rel-13 | R4 | 2014-06-18 08:00 | 2015-03-12 | 0% | RP-140662 | - | Rogers Wireless | pavlo.nebesny@rci.rogers.com | Inter-band CA 3DL/1UL | LTE
184 | 640124 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 7 | LTE_CA_B4_B4_B7-Core | 3 | Rel-13 | R4 | 2014-06-18 08:00 | 2015-03-12 | 0% | RP-140662 | RP-141084 | Rogers Wireless | pavlo.nebesny@rci.rogers.com | - | 36.101, 36.104, 36.133, 36.307, generic TR 36.853 (3 Band CA with 1UL)
185 | 640224 | Perf. Part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 7 | LTE_CA_B4_B4_B7-Perf | 3 | Rel-13 | R4 | 2014-06-18 08:00 | 2015-03-12 | 0% | RP-140662 | RP-141084 | Rogers Wireless | pavlo.nebesny@rci.rogers.com | - | 36.133, 36.141
186 | 640025 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 3 and Band 8 | LTE_CA_B3_B3_B8 | 2 | Rel-13 | R4 | 2014-06-16 08:00 | 2015-06-18 17:00 | 15% | RP-140692 | - | CHTTL | Po-Han Hsieh (pohanhsieh@cht.com.tw) | Inter-band CA 3DL/1UL | LTE
187 | 640125 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 3 and Band 8 | LTE_CA_B3_B3_B8-Core | 3 | Rel-13 | R4 | 2014-06-16 08:00 | 2015-06-18 17:00 | 30% | RP-140692 | RP-141084 | CHTTL | Po-Han Hsieh (pohanhsieh@cht.com.tw) | - | 36.101, 36.133, generic TR 36.853 (3 Band CA with 1UL)
188 | 640225 | Perf. Part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 3 and Band 8 | LTE_CA_B3_B3_B8-Perf | 3 | Rel-13 | R4 | 2014-06-18 08:00 | 2015-06-18 17:00 | 0% | RP-140692 | RP-141084 | CHTTL | Po-Han Hsieh (pohanhsieh@cht.com.tw) | - | 36.307
189 | 640026 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 39, Band 41 and Band 41 | LTE_CA_B39_B41_B41 | 2 | Rel-13 | R4 | 2014-06-16 08:00 | 2014-12-11 17:00 | 45% | RP-140708 | - | China Mobile | PAN Qun (panqun@chinamobile.com) | Inter-band CA 3DL/1UL | LTE
190 | 640126 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 39, Band 41 and Band 41 | LTE_CA_B39_B41_B41-Core | 3 | Rel-13 | R4 | 2014-06-16 08:00 | 2014-12-11 17:00 | 90% | RP-140708 | RP-141084 | China Mobile | PAN Qun (panqun@chinamobile.com) | - | 36.101, 36.104, 36.133, generic TR 36.853 (3 Band CA with 1UL)
191 | 640226 | Perf. Part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 39, Band 41 and Band 41 | LTE_CA_B39_B41_B41-Perf | 3 | Rel-13 | R4 | 2014-06-18 08:00 | 2014-12-11 17:00 | 0% | RP-140708 | RP-141084 | China Mobile | PAN Qun (panqun@chinamobile.com) | - | 36.141, 36.307
192 | 640032 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 41, Band 42 and Band 42 | LTE_CA_B41_B42_B42 | 2 | Rel-13 | R4 | 2014-06-16 08:00 | 2014-12-11 17:00 | 15% | RP-140974 | - | Huawei | leo.liuye@huawei.com | Inter-band CA 3DL/1UL | LTE
193 | 640132 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 41, Band 42 and Band 42 | LTE_CA_B41_B42_B42-Core | 3 | Rel-13 | R4 | 2014-06-16 08:00 | 2014-12-11 17:00 | 30% | RP-140974 | RP-141084 | Huawei | leo.liuye@huawei.com | - | 36.101, 36.104, 36.133, generic TR 36.853 (3 Band CA with 1UL)
194 | 640232 | Perf. Part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 41, Band 42 and Band 42 | LTE_CA_B41_B42_B42-Perf | 3 | Rel-13 | R4 | 2014-06-18 08:00 | 2014-12-11 17:00 | 0% | RP-140974 | RP-141084 | Huawei | leo.liuye@huawei.com | - | 36.141, 36.307
195 | 640033 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 41 and Band 41 | LTE_CA_B1_B41_B41 | 2 | Rel-13 | R4 | 2014-06-18 08:00 | 2015-03-13 17:00 | 0% | RP-140963 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | Inter-band CA 3DL/1UL | LTE
196 | 640133 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 41 and Band 41 | LTE_CA_B1_B41_B41-Core | 3 | Rel-13 | R4 | 2014-06-18 08:00 | 2015-03-13 17:00 | 0% | RP-140963 | RP-141084 | KDDI | Masaaki Obara (ms-obara@kddi.com) | - | 36.101, 36.104, 36.133, generic TR 36.853 (3 Band CA with 1UL)
197 | 640233 | Perf. Part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 41 and Band 41 | LTE_CA_B1_B41_B41-Perf | 3 | Rel-13 | R4 | 2014-06-18 08:00 | 2015-03-13 17:00 | 0% | RP-140963 | RP-141084 | KDDI | Masaaki Obara (ms-obara@kddi.com) | - | 36.141, 36.307
198 | 640034 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 26, Band 41 and Band 41 | LTE_CA_B26_B41_B41 | 2 | Rel-13 | R4 | 2014-06-18 08:00 | 2015-03-12 17:00 | 0% | RP-140964 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | Inter-band CA 3DL/1UL | LTE
199 | 640134 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 26, Band 41 and Band 41 | LTE_CA_B26_B41_B41-Core | 3 | Rel-13 | R4 | 2014-06-18 08:00 | 2015-03-12 17:00 | 0% | RP-140964 | RP-141084 | KDDI | Masaaki Obara (ms-obara@kddi.com) | - | 36.101, 36.104, 36.133, generic TR 36.853 (3 Band CA with 1UL)
200 | 640234 | Perf. Part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 26, Band 41 and Band 41 | LTE_CA_B26_B41_B41-Perf | 3 | Rel-13 | R4 | 2014-06-18 08:00 | 2015-03-12 17:00 | 0% | RP-140964 | RP-141084 | KDDI | Masaaki Obara (ms-obara@kddi.com) | - | 36.141, 36.307
201 | 650037 | LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 38 | LTE_CA_B3_B38 | 2 | Rel-13 | R4 | 2014-09-15 08:00 | 2014-12-11 17:00 | 0% | RP-141129 | - | Nokia Networks | iwajlo.angelow@nsn.com | Inter-band CA 2DL/1UL | LTE
202 | 650137 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 38 | LTE_CA_B3_B38-Core | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2014-12-11 17:00 | 0% | RP-141129 | - | Nokia Networks | iwajlo.angelow@nsn.com | - | 36.101, 36.104, New TR 36.8xx
203 | 650237 | Perf. Part: LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 38 | LTE_CA_B3_B38-Perf | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2014-12-11 17:00 | 0% | RP-141129 | - | Nokia Networks | iwajlo.angelow@nsn.com | - | 36.141, 36.307
204 | 650038 | LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 28 | LTE_CA_B2_B28 | 2 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-12-11 17:00 | 0% | RP-141145 | - | Huawei | alf.ahlstrom@huawei.com | Inter-band CA 2DL/1UL | LTE
205 | 650138 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 28 | LTE_CA_B2_B28-Core | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-12-11 17:00 | 0% | RP-141145 | - | Huawei | alf.ahlstrom@huawei.com | - | 36.101, 36.104, New TR 36.8xx
206 | 650238 | Perf. Part: LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 28 | LTE_CA_B2_B28-Perf | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-03-12 17:00 | 0% | RP-141145 | - | Huawei | alf.ahlstrom@huawei.com | - | 36.141, 36.307
207 | 650039 | LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 28 | LTE_CA_B4_B28 | 2 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-12-11 17:00 | 0% | RP-141146 | - | Huawei | alf.ahlstrom@huawei.com | Inter-band CA 2DL/1UL | LTE
208 | 650139 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 28 | LTE_CA_B4_B28-Core | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-12-11 17:00 | 0% | RP-141146 | - | Huawei | alf.ahlstrom@huawei.com | - | 36.101, 36.104, New TR 36.8xx
209 | 650239 | Perf. Part: LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 28 | LTE_CA_B4_B28-Perf | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-03-12 17:00 | 0% | RP-141146 | - | Huawei | alf.ahlstrom@huawei.com | - | 36.141, 36.307
210 | 650040 | LTE Advanced inter-band Carrier Aggregation of Band 20 and Band 40 | LTE_CA_B20_B40 | 2 | Rel-13 | R4 | 2014-09-12 08:00 | 2015-03-12 17:00 | 0% | RP-141168 | - | Ericsson | imadur.rahman@ericsson.com | Inter-band CA 2DL/1UL | LTE
211 | 650140 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 20 and Band 40 | LTE_CA_B20_B40-Core | 3 | Rel-13 | R4 | 2014-09-12 08:00 | 2015-03-11 17:00 | 0% | RP-141168 | - | Ericsson | imadur.rahman@ericsson.com | - | 36.101, 36.104, 36.133, New TR 36.8xx
212 | 650240 | Perf. Part: LTE Advanced inter-band Carrier Aggregation of Band 20 and Band 40 | LTE_CA_B20_B40-Perf | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-03-12 17:00 | 0% | RP-141168 | - | Ericsson | imadur.rahman@ericsson.com | - | 36.141, 36.307
213 | 650041 | LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 40 | LTE_CA_B1_B40 | 2 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-12-11 17:00 | 0% | RP-141312 | - | KT | ilwhan.kim@kt.com | Inter-band CA 2DL/1UL | LTE
214 | 650141 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 40 | LTE_CA_B1_B40-Core | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-06-12 17:00 | 0% | RP-141312 | - | KT | ilwhan.kim@kt.com | - | 36.101, 36.104, 36.133, New TR 36.8xx
215 | 650241 | Perf. Part: LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 40 | LTE_CA_B1_B40-Perf | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-12-11 17:00 | 0% | RP-141312 | - | KT | ilwhan.kim@kt.com | - | 36.141, 36.307
216 | 650042 | LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 40 | LTE_CA_B3_B40 | 2 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-12-11 17:00 | 0% | RP-141674 | - | KT | Chungwoo HWANG (cwhwang@kt.com) | Inter-band CA 2DL/1UL | LTE
217 | 650142 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 40 | LTE_CA_B3_B40-Core | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-12-11 17:00 | 0% | RP-141674 | - | KT | Chungwoo HWANG (cwhwang@kt.com) | - | 36.101, 36.104, 36.133, New TR 36.8xx
218 | 650242 | Perf. Part: LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 40 | LTE_CA_B3_B40-Perf | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-06-12 17:00 | 0% | RP-141674 | - | KT | Chungwoo HWANG (cwhwang@kt.com) | - | 36.141, 36.307
219 | 650043 | LTE Advanced inter-band Carrier Aggregation of Band 20 and Band 31 | LTE_CA_B20_B31 | 2 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-12-11 17:00 | 0% | RP-141336 | - | Huawei | Liu Liehai (liuliehai@huawei.com) | Inter-band CA 2DL/1UL | LTE
220 | 650143 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 20 and Band 31 | LTE_CA_B20_B31-Core | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-12-11 17:00 | 0% | RP-141336 | - | Huawei | Liu Liehai (liuliehai@huawei.com) | - | 36.101, 36.104, New TR 36.8xx
221 | 650243 | Perf. Part: LTE Advanced inter-band Carrier Aggregation of Band 20 and Band 31 | LTE_CA_B20_B31-Perf | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-03-12 17:00 | 0% | RP-141336 | - | Huawei | Liu Liehai (liuliehai@huawei.com) | - | 36.141, 36.307
222 | 650044 | LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 31 | LTE_CA_B3_B31 | 2 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-12-11 17:00 | 0% | RP-141337 | - | Huawei | Liu Liehai (liuliehai@huawei.com) | Inter-band CA 2DL/1UL | LTE
223 | 650144 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 31 | LTE_CA_B3_B31-Core | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-12-11 17:00 | 0% | RP-141337 | - | Huawei | Liu Liehai (liuliehai@huawei.com) | - | 36.101, 36.104, New TR 36.8xx
224 | 650244 | Perf. Part: LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 31 | LTE_CA_B3_B31-Perf | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-03-12 17:00 | 0% | RP-141337 | - | Huawei | Liu Liehai (liuliehai@huawei.com) | - | 36.141, 36.307
225 | 650045 | LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 40 | LTE_CA_B5_B40 | 2 | Rel-13 | R4 | 2014-09-12 08:00 | 2015-03-12 17:00 | 0% | RP-141675 | - | SK Telecom | haesung.park@sk.com | Inter-band CA 2DL/1UL | LTE
226 | 650145 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 40 | LTE_CA_B5_B40-Core | 3 | Rel-13 | R4 | 2014-09-12 08:00 | 2015-03-11 17:00 | 0% | RP-141675 | - | SK Telecom | haesung.park@sk.com | - | 36.101, 36.104, New TR 36.8xx
227 | 650245 | Perf. Part: LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 40 | LTE_CA_B5_B40-Perf | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-03-12 17:00 | 0% | RP-141675 | - | SK Telecom | haesung.park@sk.com | - | 36.141, 36.307
228 | 650046 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 25, Band 41 and Band 41 | LTE_CA_B25_B41_B41 | 2 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-12-11 17:00 | 0% | RP-141673 | - | Alcatel-Lucent | Ng, Man Hung (man-hung.ng@alcatel-lucent.com) | Inter-band CA 3DL/1UL | LTE
229 | 650146 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 25, Band 41 and Band 41 | LTE_CA_B25_B41_B41-Core | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-09-11 17:00 | 0% | RP-141673 | - | Alcatel-Lucent | Ng, Man Hung (man-hung.ng@alcatel-lucent.com) | - | 36.101, 36.104, 36.307, New TR 36.833-x-yz
230 | 650246 | Perf. Part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 25, Band 41 and Band 41 | LTE_CA_B25_B41_B41-Perf | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-12-11 17:00 | 0% | RP-141673 | - | Alcatel-Lucent | Ng, Man Hung (man-hung.ng@alcatel-lucent.com) | - | 36.141
231 | 650047 | LTE Advanced intra-band contiguous Carrier Aggregation in Band 42 for 3DL | LTE_CA_C_B42_3DL | 2 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-06-12 17:00 | 0% | RP-141677 | - | CATT | Yuexia Song (songyuexia@catt.cn) | Intra-band contig. CA 3DL | LTE
232 | 650147 | Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 42 for 3DL | LTE_CA_C_B42_3DL-Core | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-06-12 17:00 | 0% | RP-141677 | - | CATT | Yuexia Song (songyuexia@catt.cn) | - | 36.101, 36.104, 36.133, New TR 36.833-5-42
233 | 650247 | Perf. Part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 42 for 3DL | LTE_CA_C_B42_3DL-Perf | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-06-12 17:00 | 0% | RP-141677 | - | CATT | Yuexia Song (songyuexia@catt.cn) | - | 36.141, 36.307
234 | 650048 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 39, Band 39 and Band 41 | LTE_CA_B39_B39_B41 | 2 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-12-11 17:00 | 0% | RP-141288 | - | China Mobile | PAN, Qun (panqun@chinamobile.com) | Inter-band CA 3DL/1UL | LTE
235 | 650148 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 39, Band 39 and Band 41 | LTE_CA_B39_B39_B41-Core | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-12-11 17:00 | 0% | RP-141288 | - | China Mobile | PAN, Qun (panqun@chinamobile.com) | - | 36.101, 36.104, 36.133, New TR 36.8xx
236 | 650248 | Perf. Part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 39, Band 39 and Band 41 | LTE_CA_B39_B39_B41-Perf | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-12-11 17:00 | 0% | RP-141288 | - | China Mobile | PAN, Qun (panqun@chinamobile.com) | - | 36.141, 36.307
237 | 650049 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 8, Band 41 and Band 41 | LTE_CA_B8_B41_B41 | 2 | Rel-13 | R4 | 2014-09-12 08:00 | 2015-12-11 17:00 | 0% | RP-141290 | - | China Mobile | PAN, Qun (panqun@chinamobile.com) | Inter-band CA 3DL/1UL | LTE
238 | 650149 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 8, Band 41 and Band 41 | LTE_CA_B8_B41_B41-Core | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-12-11 17:00 | 0% | RP-141290 | - | China Mobile | PAN, Qun (panqun@chinamobile.com) | - | 36.101, 36.104, 36.133, New TR 36.8xx
239 | 650249 | Perf. Part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 8, Band 41 and Band 41 | LTE_CA_B8_B41_B41-Perf | 3 | Rel-13 | R4 | 2014-09-12 08:00 | 2015-03-11 17:00 | 0% | RP-141290 | - | China Mobile | PAN, Qun (panqun@chinamobile.com) | - | 36.141, 36.307
240 | 650050 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 2 and Band 29 | LTE_CA_B2_B2_B29 | 2 | Rel-13 | R4 | 2014-09-15 08:00 | 2014-12-11 17:00 | 0% | RP-141448 | - | AT&T | marc.grant@att.com | Inter-band CA 3DL/1UL | LTE
241 | 650150 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 2 and Band 29 | LTE_CA_B2_B2_B29-Core | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2014-12-11 17:00 | 0% | RP-141448 | - | AT&T | marc.grant@att.com | - | 36.101, 36.104, 36.133, New TR 36.8xx
242 | 650250 | Perf. Part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 2 and Band 29 | LTE_CA_B2_B2_B29-Perf | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2014-12-11 17:00 | 0% | RP-141448 | - | AT&T | marc.grant@att.com | - | 36.141, 36.307
243 | 650051 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 38, Band 40 and Band 40 | LTE_CA_B38_B40_B40 | 2 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-06-12 17:00 | 0% | RP-141655 | - | Samsung | xutao.zhou@samsung.com | Inter-band CA 3DL/1UL | LTE
244 | 650151 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 38, Band 40 and Band 40 | LTE_CA_B38_B40_B40-Core | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-06-12 17:00 | 0% | RP-141655 | - | Samsung | xutao.zhou@samsung.com | - | 36.101, 36.104, 36.133, New TR 36.8xx
245 | 650251 | Perf. Part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 38, Band 40 and Band 40 | LTE_CA_B38_B40_B40-Perf | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-06-12 17:00 | 0% | RP-141655 | - | Samsung | xutao.zhou@samsung.com | - | 36.141, 36.307
246 | 650052 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4 and Band 29 | LTE_CA_B2_B4_B29 | 2 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-12-11 17:00 | 0% | RP-141668 | - | Huawei | SHAN Huiping (shanhuiping@huawei.com) | Inter-band CA 3DL/1UL | LTE
247 | 650152 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4 and Band 29 | LTE_CA_B2_B4_B29-Core | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-12-11 17:00 | 0% | RP-141668 | - | Huawei | SHAN Huiping (shanhuiping@huawei.com) | - | 36.101, 36.104, 36.133, New TR 36.8xx
248 | 650252 | Perf. Part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4 and Band 29 | LTE_CA_B2_B4_B29-Perf | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2014-12-11 17:00 | 0% | RP-141668 | - | Huawei | SHAN Huiping (shanhuiping@huawei.com) | - | 36.141, 36.307
249 | 650053 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 5 and Band 29 | LTE_CA_B2_B5_B29 | 2 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-12-11 17:00 | 0% | RP-141667 | - | Huawei | SHAN Huiping (shanhuiping@huawei.com) | Inter-band CA 3DL/1UL | LTE
250 | 650153 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 5 and Band 29 | LTE_CA_B2_B5_B29-Core | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-12-11 17:00 | 0% | RP-141667 | - | Huawei | SHAN Huiping (shanhuiping@huawei.com) | - | 36.101, 36.104, 36.133, New TR 36.8xy (inter-band CA 2DL/1UL (introduce CA_B5-B29), New TR 36.8xz (inter-band CA 3DL/1UL)
251 | 650253 | Perf. Part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 5 and Band 29 | LTE_CA_B2_B5_B29-Perf | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-06-12 17:00 | 0% | RP-141667 | - | Huawei | SHAN Huiping (shanhuiping@huawei.com) | - | 36.141, 36.307
252 | 610034 | (Small) Technical Enhancements and Improvements for Rel-13 | TEI13 | 1 | Rel-13 | SP,CP,RP,GP | 2013-09-18 08:00 | 2015-12-21 17:00 | 0% | - | - | - | - | - | -
253 | 0 | Release 13 Studies | - | 1 | Rel-13 | SP,RP | 2013-09-12 08:00 | 2015-12-25 17:00 | 0% | - | - | - | - | - | -
254 | 570034 | Study on Application specific Congestion control for Data Communication | FS_ACDC | 1 | Rel-13 | S1 | 2012-09-13 08:00 | 2014-09-17 17:00 | 100% | SP-130415 | S1-143305 | NTT DOCOMO | Atsushi Minokuchi (minokuchi@nttdocomo.co.jp) | SP#65 completed. SP#64 TR 22.806v200 for Approval. ACDC is applicable to UTRAN and E-UTRAN. Possible overlap with RAN2 TR 36.848 Study on smart congestion mitigation in E-UTRAN (prioritising MMTEL voice over other traffic during congestion) | 22.806
255 | 600046 | Study on Isolated E-UTRAN Operation for Public Safety | FS_IOPS | 1 | Rel-13 | S1 | 2013-06-21 08:00 | 2014-06-18 17:00 | 100% | SP-130596 | - | General Dynamics | paul.piggin@gd-broadband.com | SP#64 completed. TR 22.897v200 for Approval. Linked to Rel-12 TR 22.803 (FS_ProSe) and Features: ProSe, GCSE_LTE | 22.897
256 | 610031 | Study on enhancements for Infrastructure based data Communication Between Devices | FS_eICBD | 1 | Rel-13 | S1 | 2013-09-12 08:00 | 2014-09-17 17:00 | 100% | SP-130418 | S1-143309 | KPN | toon.norp@tno.nl | SP#65 completed. TR 22.807v200 for Approval | 22.807
257 | 610033 | Study on Co-ordinated packet data network gateway (P-GW) change for SIPTO | FS_CSIPTO | 1 | Rel-13 | S1 | 2013-09-12 08:00 | 2014-06-18 17:00 | 100% | SP-130417 | - | Intel | Eric.siow@intel.com | SP#64 completed. TR 22.828v200 for Approval. Linked to Features: Rel-10 LIPA_SIPTO & Rel-12 LIMONET | 22.828
258 | 620069 | Study on Flexible Mobile Service Steering | FS_FMSS | 1 | Rel-13 | S1 | 2013-12-11 08:00 | 2014-09-17 17:00 | 100% | SP-130597 | S1-143310 | China Mobile | Lu Lu (lulu@chinamobile.com) | SP#65 completed. TR 22.808v200 for Approval. Study supporting traffic classification and service chain selection capabilities per operator’s policy in order to realize efficient and flexible mobile service steering in the Gi-LAN network | 22.808
259 | 620070 | Study on Enhanced Calling Information Presentation | FS_ECIP | 1 | Rel-13 | S1 | 2013-12-11 08:00 | 2014-09-17 17:00 | 100% | SP-130598 | S1-143311 | China Mobile | LI Xiaofan (lixiaofan@chinamobile.com | SP#65 completed. TR 22.810v200 for Approval. Linked to Multimedia Telephony Service for IMS (UID_7038), Customized Alerting Tone (CAT) UID_370028, Customized Ringing Signal (CRS) UID_380067 | 22.810
260 | 630017 | Study on RAN Sharing Enhancements on GERAN and UTRAN | FS_GUSH | 1 | Rel-13 | S1 | 2014-03-07 08:00 | 2014-09-17 17:00 | 100% | SP-140073 | - | Telefónica | chris.friel@telefonica.com | SP#65 completed. Update on GERAN and UTRAN of Rel-12 TR 22.852 Study on RAN Sharing Enhancements (FS_RSE) | 22.852 updates
261 | 520035 | Study on Usage Monitoring Enhancements for Service, Application and Subscriber Group | FS_UMONC_sas | 1 | Rel-13 | S2 | 2011-06-08 08:00 | 2014-12-12 17:00 | 90% | SP-140403 | - | China Telecom | Jinyan Li (lijy@ctbri.com.cn) | SP#64 revived. Added to the Title "for Service, Application and Subscriber Group", Changed Acronym: FS_UMONC=>FS_UMONC_sas | 23.858
262 | 520335 | Deleted - SA1 part of Study on Usage Monitoring Control PCC Enhancement | FS_UMONC | 2 | - | S1 | 2011-06-08 08:00 | 2012-06-20 17:00 | 100% | SP-120554 | - | ZTE | Li.Mian@zte.com.cn | SP#56 completed | 23.858
263 | 520135 | SA2 part of Study on Usage Monitoring Control PCC Enhancement | FS_UMONC_sas | 2 | Rel-13 | S2 | 2013-06-02 08:00 | 2014-12-12 17:00 | 80% | SP-140403 | - | China Telecom | Jinyan Li (lijy@ctbri.com.cn) | SP#64 revived. Updated WID SP-120554=>SP-140403. Changed Justification/objectives/Rapporteut ZTE=>China Unciom. SP#58 SA2 stopped (at 70% completion) | 23.858
264 | 520235 | Deleted - SA5 part of Study on Usage Monitoring Control enhancement | FS_UMONC | 2 | - | S5 | 2012-03-02 08:00 | 2012-09-12 17:00 | 100% | SP-120554 | - | Huawei | Hui Cai (Sarah.Cai@huawei.com) | SP#57 stopped | 32.858
265 | 650035 | Study on Optimizations to support High Latency communications | FS_HLcom | 1 | Rel-13 | S2 | 2014-09-19 08:00 | 2015-06-17 17:00 | 0% | SP-140635 | - | Ericsson | hans.ronneke@ericsson.com | Apps using "3GPP constrained devices"/high latency to access devices from network side (UE battery saving/sleep making UEs unreachable for long period/ low throughput bearers) over 3GPP IP connectivity for large no of devices w/o negatively affecting perf | New TR 23.7xy
266 | 500034 | Study on Security aspects of Integration of Single Sign-On (SSO) frameworks with 3GPP networks | FS_SSO_Int_Sec | 1 | Rel-13 | S3 | 2010-12-16 08:00 | 2015-06-12 17:00 | 60% | SP-140576 | - | Ericsson | vesa.lehtovirta@ericsson.com | SP#65 moved to Rel-13. Updated WID SP-100734=>SP-140576. Completion 09/14=>06/15 | 33.895
267 | 590035 | Study on Security for Proximity-based Services | FS_ProSe_Sec | 1 | Rel-13 | S3 | 2013-03-07 08:00 | 2015-06-17 17:00 | 95% | SP-140629 | - | Qualcomm | Adrian Escott (aescott@qti.qualcomm.com) | SP#65 updated WID SP-140300=>SP-140629 (Moved the TR phase to Rel-13 as a stand-alone Study). Completion 09/14=>06/15. SP#64 TR 33.833 v100 for Information | 33.833
268 | 610043 | Study on Subscriber Privacy Impact in 3GPP | FS_SPI | 1 | Rel-13 | S3 | 2013-09-12 08:00 | 2015-12-16 17:00 | 80% | SP-130399 | - | China Unicom | Feng Gao (gaofeng149@chinaunicom.cn) | SP#65 moved to Rel-13. Completion 09/14=>12/15. Related to SA1 TR 22.949 Rel-6 Study on Privacy Capability (PrivCap) UID_31030 studied generalized privacy capability (protection of personal data and non-disclosure of identity) | 33.849
269 | 640055 | Study on Lawful Interception Service Evolution | FS_LISE | 1 | Rel-13 | S3 | 2014-06-23 08:00 | 2015-12-09 17:00 | 0% | SP-140303 | - | Alcatel-Lucent | terry.jacobson@alcatel-lucent.com | Linked to LI13 which defines existing LI service requirements in TS 33.106 as well as existing HI1, HI2 & HI3 reference points | 33.826
270 | 650036 | Study on IMS Enhanced Spoofed Call Prevention and Detection | FS_ESCAPADES | 1 | Rel-13 | S3 | 2014-09-19 08:00 | 2015-09-16 17:00 | 0% | SP-140611 | - | Sprint | Gregory.schumacher@sprint.com | Evaluate IETF WG STIR (Secure Telephone Identity Revisited) drafts for use in 3GPP networks for spoofed call detection and make recommendations on what should be incorporated into 3GPP IMS security TSs. | 33.8xy
271 | 590045 | Study on Enhanced Acoustic Test Specifications | FS_SEATS | 1 | Rel-13 | S4 | 2013-03-06 08:00 | 2014-12-12 17:00 | 30% | SP-130028 | - | Audience, Intel | Chris Steck (Audience), David Isherwood (Intel) | SP#65 completion 09/14=>12/14. Moved to Rel-13. Address existing items designated as FFS in TS 26.131/2. Coordinate with other SDOs (e.g. ITU-T SG 12, ETSI TC STQ) to leverage each other’s work and minimize overlap | 26.931
272 | 560435 | Study on Compliance of 3GPP SA5 specifications to the NGMN NGCOR | FS_OAM_NGMN_NGCOR | 1 | Rel-13 | S5 | 2012-06-20 08:00 | 2015-09-16 17:00 | 35% | SP-140539 | - | Huawei | zoulan@huawei.com | SP#65 updated WID SP-140349=>SP-140539. SP#64 TR 32.837 moved out of Rel-12 BB as a stand-alone Rel-13 Study (added NGCOR phase II in the scope) | 32.837
273 | 610045 | Study on Enhancements of OAM aspects of Distributed Mobility Load Balancing (MLB) SON function | FS_D_MLB_SON_OAM | 1 | Rel-13 | S5 | 2013-09-12 08:00 | 2014-12-12 17:00 | 20% | SP-130430 | - | Cisco | Vladimir Yanover (vyanover@cisco.com) | SP#64 completion 06/14=>12/14 | 32.860
274 | 620059 | Study on Application and Partitioning of Itf-N | FS_OAM_AP_Itf-N | 1 | Rel-13 | S5 | 2013-12-11 08:00 | 2014-12-12 17:00 | 15% | SP-130681 | - | China Mobile | Li Jian (lijian@chinamobile.com), Hu Yaxi (huyaxi@cmdi.chinamobile.com) | - | 32.861
275 | 620060 | Study on Charging aspects on Roaming End-to-end scenarios with VoLTE IMS and interconnecting networks | FS_REVOLTE_IMS_CH | 1 | Rel-13 | S5 | 2013-12-11 08:00 | 2014-12-12 17:00 | 35% | SP-130609 | - | Deutsche Telekom | Roland Jesske (r.jesske@telekom.de) | SP#64 moved to Rel-13. Completion 06/14=>12/14. Linked to CT3/CT1 draft TR 29.949 Study on Technical Aspects on Roaming End-to-end scenarios with VoLTE IMS and other networks (FS_REVOLTE_IMS) UID_610010 | 32.849
276 | 640054 | Study on Network Management of Virtualized Networks | FS_OAM_VIRNET | 1 | Rel-13 | S5 | 2014-06-09 08:00 | 2015-06-17 17:00 | 10% | SP-140398 | - | China Mobile, Huawei | Liu Jinglei (liujinglei@chinamobile.com), zoulan@huawei.com | Linked to ETSI Network Functions Virtualisation (NFV) ISG. Objective 1: Scenario, use cases & concepts for network management of Virtualized Networks. Objective 2: Recommend potential solutions supporting management of Virtualized Networks | 32.842
277 | 590010 | Study on Review of dedicated 3GPP UICC features | FS_Red_UCe | 1 | Rel-13 | C6 | 2013-03-04 08:00 | 2015-12-16 17:00 | 65% | CP-130168 | - | BlackBerry | Adrian Buckley (abuckley@blackberry.com) | CP#65 TR 31.901v100 for Information. Moved to Rel-13. Completion 09/14=>12/15. Waiting for feedback from external organizations (PTCRB/PVG). | 31.901
278 | 490006 | Study on Solutions for GSM/EDGE BTS Energy Saving | FS_Energy_BTS | 1 | Rel-13 | G1,G2 | 2009-03-10 11:12 | 2014-11-21 17:00 | 90% | GP-101638 | - | Nokia Networks, Vodafone | juergen.hofmann@nsn.com, leo.patanapongpibul@vodafone.com | GP#63 moved to Rel-13. Completion 08/14=>11/14. GP#55 TR 45.926v100 for Information. GP#47 approved WID | 45.926
279 | 590034 | Study on Downlink MIMO | FS_DOMIMO | 1 | Rel-13 | G1,G2 | 2013-08-21 08:00 | 2015-02-20 17:00 | 50% | GP-130288 | - | Nokia Networks | Khairul Hasan | GP#62 completion 08/14=>02/15. Moved to Rel-13. GP#57 approved WID | 45.8xy
280 | 620012 | Study on Power saving for Machine-Type Communications (MTC) devices | FS_uPoD | 1 | Rel-13 | G2,G1 | 2014-06-18 16:36 | 2015-05-29 17:00 | 30% | GP-131136 | - | China Mobile | Jing Han (hanjing@chinamobile.com) | GP#65 completion 02/15=>05/15. GP#60 approved WID. Linked to Rel-12 Feature MTCe, Stage 2 BB3: UE Power Consumptions Optimizations (UEPCOP) | 43.869
281 | 620013 | Study on UpLink MultiUser Multiple-Input Multiple-Output (UL MU-MIMO) | FS_UL_MU_MIMO | 1 | Rel-13 | G1,G2 | 2014-04-17 11:12 | 2015-02-20 17:00 | 20% | GP-131131 | - | Huawei | Chao Luo (chluo@huawei.com) | GP#62 completion 11/14=>02/15. GP#60 approved WID. Triggered by increase in UL connections to be served by PS domain in GSM networks (scenarios: GSM frequencies refarming to other RATs, emergence of MTC services over mobile radio networks) | 45.876
282 | 640001 | Study on Cellular system support for ultra Low Complexity and low throughput Internet of Things | FS_IoT_LC | 1 | Rel-13 | G1,G2 | 2014-05-30 08:00 | 2015-08-28 17:00 | 15% | GP-140421 | - | Vodafone | chris.pudney@vodafone.com | GP#62 approved WID | 45.8xy
283 | 570022 | Study on LTE FDD in the bands 1980-2010 MHz and 2170-2200 MHz | FS_LTE_1980_2170_Korea | 1 | Rel-13 | R4 | 2012-09-11 08:00 | 2014-12-11 17:00 | 85% | RP-141154 | RP-141153 | KT | Chungwoo HWANG (cwhwang@kt.com) | RP#65 moved to Rel-13. Completion 09/14=>12/14. Updated WID RP-140121=>RP-141154. Study only for Region 3 (so far) | LTE 36.861
284 | 600020 | Study on Positioning enhancements for E-UTRA | FS_LCSenh_LTE | 1 | Rel-13 | R4,R1 | 2013-04-25 14:36 | 2014-12-11 17:00 | 85% | RP-140667 | RP-140639 | Huawei | Jie Cui (cuijie@huawei.com) | RP#64 updated WID RP-130680=>RP-140667 (still only 3 supporting companies!). Completion 06/14=>12/14. Moved to Rel-13 | LTE 36.855
285 | 620045 | Study on Multi-RAT joint coordination | FS_MultiRAT_JC | 1 | Rel-13 | R3 | 2013-12-06 08:00 | 2014-12-11 17:00 | 50% | RP-132086 | RP-141301 | China Mobile | Kimba Dit Adamou, Boubacar (jinba@chinamobile.com) | Identify general scenarios and requirements for Multi-RAT (LTE/UMTS/GSM/CDMA/WLAN) coordination and study candidate solutions | UTRA, LTE 37.870
286 | 640016 | Study on Advanced Wireless Services (AWS) - Extension band for LTE | FS_LTE_AWS_EXT | 1 | Rel-13 | R4 | 2013-12-16 08:00 | 2014-12-11 17:00 | 10% | RP-141037 | RP-141429 | Qualcomm | Gene Fong (gfong@qti.qualcomm.com) | - | LTE 36.849
287 | 640017 | Study on MIMO OTA antenna test function for LTE | FS_LTE_MIMO_OTA_ATF | 1 | Rel-13 | R5 | 2013-03-18 08:00 | 2014-12-11 17:00 | 60% | RP-141325 | RP-141124 | Keysight | Moray_Rumney@keysight.com | RP#65 TR 36.978v100 for Information. Updated WID RP-140985=>RP-141325 (added impacted TS 36.509, although this is a SI the only change is adding an informative note to reserve message types for future use). Linked to Rel-12 TR 37.977 | 36.509, new TR 37.978
288 | 640018 | Study on Indoor Positioning Enhancements for UTRA and LTE | FS_UTRA_LTE_iPos_enh | 1 | Rel-13 | R1,R4 | 2014-06-18 08:00 | 2015-09-17 17:00 | 0% | RP-141102 | RP-141101 | NextNav | Vogedes Jerome (jvogedes@NextNav.com) | RP#65 updated WID RP-141003=>RP-141102 | UTRA, LTE 37.857
289 | 650013 | Study on Small data transmission enhancements for UMTS | FS_UTRA_SDATA | 1 | Rel-13 | R1,R2 | 2014-09-16 08:00 | 2015-06-18 17:00 | 0% | RP-141711 | - | Ericsson | gerardo.agni.medina.acosta@ericsson.com | Linked to Rel-12 SA2 Stage 2 TR23.887 and TS 23.682 on BB1: Small Data and Device Triggering Enhancements | UTRA TR 25.8xy
290 | 650014 | Study on Downlink enhancements for UMTS | FS_UTRA_EDL | 1 | Rel-13 | R2,R1 | 2014-09-12 08:00 | 2015-03-11 17:00 | 0% | RP-141657 | - | Huawei | jun.chen@huawei.com | Linked to UTRA Rel-12 Further Enhanced Uplink (EUL) enhancements (EDCH_enh) and TR 25.700 Study on Further Enhanced Uplink (EUL) enhancements (FS_EDCH_enh) | UTRA TR 25.706
291 | 650015 | Study on Elevation Beamforming/Full-Dimension (FD) MIMO for LTE | FS_LTE_EBF_FDMIMO | 1 | Rel-13 | R1 | 2014-09-12 08:00 | 2015-06-16 17:00 | 0% | RP-141644 | - | Nokia Networks (DL), Samsung (UL) | bishwarup.mondal@nsn.com, hyoungju.ji@samsung.com | Triggered by Rel-12 RAN1 TR 36.873 Study on 3D-channel model for Elevation Beamforming and FD-MIMO studies for LTE (FS_LTE_3D_channel), | LTE 36.8xy
292 | 650016 | Study on Licensed-Assisted Access using LTE | FS_LTE_LAA | 1 | Rel-13 | R1,R2,R4 | 2014-09-16 08:00 | 2015-06-18 17:00 | 0% | RP-141664 | - | Ericsson, Huawei | havish.koorapaty@ericsson.com, david.mazzarese@huawei.com | Evaluate LTE enhancements for a single global solution framework for licensed-assisted access to unlicensed spectrum. Dual Connectivity is out of scope. A standalone access to unlicensed spectrum is out of scope. | LTE 36.8xy