## Slide 1: SMARTER Status Update New Services and Markets Technology Enablers
Adrian Neal
Vodafone
SMARTER Rapporteur
3GPP TSG-SA WG1 Meeting #69
Sanya, China, 2-6 February 2015
Remember: present only slides 3, 6, 7
Notes: 1

## Slide 2: SMARTER Status
Is this a new SI? Yes
This WI has not been approved by SP
  The following slides assume approval at SP67
Notes: 1

## Slide 3: SMARTER Progress
Progress made at this meeting
  New Study item agreed.
Work/Study Item Completion: 0%
Draft TR 22.xxx Completion: 0%
S1-150315
Notes: 1

## Slide 4: SMARTER Meeting Time
Number of slots assigned at this meeting
  sum of plenary and drafting slots: 1
Number of slots requested for next meeting
  sum of plenary and drafting slots: 5
S1-150315
Notes: 1

## Slide 5: SMARTER Completion Date
Target completion date in SID (Phase 1): 03/2016 SP#71
Is current completion date the same as above? Yes
Will target completion date be met? Y
Expected date to send TR to SA plenary:
  For information: SA1#71 (08/2015)
  For approval: SA1#73 (02/2016)
S1-150315
Notes: 1

## Slide 6: SMARTER Planning/Progress
Topics to focus on at SA1#70 (Apr 2015):
  Use cases from published Industry White Papers and individual company use cases.
Planning for subsequent meetings
  SA1#71 (Aug 2015)
    Grouping of use cases.
    Selection of topics for a small number of building block TRs which will result.
  SA1#72 (Nov 2015)
    Progression of BB TRs.
    Collection of new use cases for Phase 2.
S1-150315
Notes: 1

## Slide 7: Work plan between meetings
Email discussion
  Rapporteur to provide baseline spreadsheet of existing use cases from published Industry White Papers as a starting point.
  Mature the items in the previous slide
S1-150315
Notes: 1

## Slide 8: SMARTER Progress Estimate
Estimated percentage completion (Phase 1):
  SA1#70 (Apr 2015): 25%
  SA1#71 (Aug 2015): 50%
  SA1#72 (Nov 2015): 75%
  SA1#73 (Feb 2015): 100%
S1-150315
Notes: 1

## Slide 9: SMARTER Agreed documents
List of agreed documents at this meeting:
  None.
S1-150315
Notes: 1