## Sheet3
Delegates mail | Comment | New Status | ID | Delegate | Work Item | Class | TDoc | Status | Processed | Proposed Conclusion | Description | Proposed Change | Comments | Section
|  |  | A701 | Apple (Naveen) | Mob | 1 | None | ToDo |  |  | Field description is missing for this. |  | Need to add how this resetID needs to be interpreted. We understand it is already in procedural text, but atleast the description should be captured here with reference | – LTM-Candidate
|  |  | A702 | Apple (Naveen) | Mob | 1 | None | ToDo |  |  | Wondering why a special cond tag is needed. |  | We can use the same framework as NoReset ID as the logic is the same here as well. | – LTM-Config
|  |  | B013 | Lenovo (Hyung-Nam) | CIO | 2 | None | ToDo |  | v100 | A CR implementation issue needs to be fixed here. The field cellIndividualOffsetList-r18 has been incorrectly implemented in IE PeriodicalReportConfigInterRAT. Acc. to CR4492r2 it should have been implemented in IE EventTriggerConfigInterRAT instead. | Move the field cellIndividualOffsetList-r18 to IE EventTriggerConfigInterRAT. | ZTE (LiuJing): Agree with the proposal. | – ReportConfigInterRAT
|  |  | C649 | CATT (Xiao) | NR_BWP_wor | 2 | None | PropAgree |  | v170 | Removal of this field (and also in TS 38.306) | According to the conclusion and revised WID (RP-233999) last RAN plenary, Option B-1-2 is not removed from the WID ans not supported in Rel-18. So the corresponding UE capability specified by this field should be removed (with the removal of the same field to be done also in TS 38.306). | Chenli-v180: It is correct. Option B-1-2 has been removed. Thus, the corresponding capability should be removed. Thanks. Intel (Ziyi): After coordination, this correction will be included in UE cap mega CR | – FeatureSetDownlink
|  |  | D001 | NTT Docomo (Tianyang Min) | FeMob | 1 | None | ToDo |  |  | For network behavior, we usually use "should not"" instead of "shall not" | the network shall should not configure the field sk-Counter within the RRCReconfiguration message for conditional reconfiguration execution for subsequent CPAC. | MediaTek (Felix): We think it is more common to say “the network does not configure...” | – ConditionalReconfiguration
|  |  | E053 | Ericsson (Tony) | IDC | 1 | None | PropAgree |  | v27 | In this field there are 10 spare values missing and it would be good to add them. | Add the missing spare values are follows: affectedBandwidth-r18 ENUMERATED {khz200, khz400, khz600, khz800, mhz1, mhz2, mhz3, mhz4, mhz5, mhz6, mhz8, mhz10, mhz20, mhz30, mhz40, mhz50, mhz60, mhz80, mhz100, mhz200, mhz300, mhz400, spare10, spare9, spare8, spare7, spare6, spare5, spare4, spare3, spare2, spare1} | Xiaomi (Yumin): Fine to add the spares. Thank you | – UEAssistanceInformation
|  |  | E073 | Ericsson (Tony) | CIO | 1 | R2-24xxxxx | ToDo |  | v27 | The cell individual offset in ReportConfigInterRAT is different from that one in ReportConfigNR. Therefore, would be good to specify that this CIO is for EUTRA (as also reflected in the IE used for the field). | Change cellIdividualOffsetList-r18 to cellIndividualOffsetList-EUTRA-r18. | ZTE (LiuJing): Agree with the proposal. | – ReportConfigInterRAT
|  |  | E110 | Ericsson (Tony) | IDC | 1 | None | ToDo |  | v70 | This field has two spare bits which as missing and it would be good to spell them out for future extension. | Add missing spare values are follows: autonomousDenialSlots-r18 ENUMERATED {n2, n5, n10, n15, n20, n30, spare 2, spare1}, | Xiaomi (Yumin): Fine to add the spares. Thank you | – CellGroupConfig
|  |  | E134 | Ericsson (Min) | IDC | 1 | None | PropReject |  |  | idc-FDM-Assistance, idc-TDM-Assistance are not referred in the procedure text in clause 5.7.4.3. | Refer/use the two fields in the UAI procedure text in clause 5.7.4.3. | Xiaomi (Yumin): “idc-TDM-Assistance” is used in clause 5.7.4.3. “idc-FDM-Assistance” is not used in clause 5.7.4.3, as we used “affectedCarrierFreqRangeList” and “affectedCarrierFreqRangeCombList” in “idc-FDM-Assistance” to differentiate the Rel-18 UE behaviors from the Rel-16 UE behaviors using “affectedCarrierFreqList” and “affectedCarrierFreqCombList” | – UEAssistanceInformation
|  |  | E135 | Ericsson (Min) | IDC | 1 | None | PropReject |  |  | missing procedure text for the case when the UE has addressed IDC issue. In this case, the UE shall not include IDC info the UAI. | add "else" under 2> 2> else (if the UE no longer experiences IDC problem): 3> do not include xxxxxxx in IDC-FDM-Assistance IE, and xxxxxxx in IDC-TDM-Assistance IE; This RIL issue has been existing since R16. therefore, we need R16 CR, R17 mirror CR and R18 mirror CR. | Xiaomi (Yumin): The proposed change is not needed. The current specification of the second bullet “2>” requires the UE to report the latest IDC status (including the resovled IDC issues) by removing the corresponding affected frequency. This is useful for the gNB to avoid the unnecessary deconfiguration of frequencies not experiencing IDC issue anymore | 5.7.4.2 Initiation
|  |  | E162 | Ritesh Shreevastav | NR_pos_enh2 | 2 | None | ToDo |  | to address (discuss) via rapporteur CR | the UE should also check if current TA is valid before applying the change | add condition that only if TA is valid UE should apply the change, it could also be addressed in MAC specification |  | 5.3.13.6 Cell re-selection or cell selection or L2 U2N relay (re)selection while T390, T319 or T302 is running or SDT procedure is ongoing (UE in RRC_INACTIVE) or SRS transmission in RRC_INACTIVE is configured
|  |  | E34 | Ericsson (Ali) | SON | 1 | None | ToDo |  | v013 | Wrong indentetion. | 3>2> include the sdt-Failed; |  | 5.7.10.5 RA information determination
|  |  | H053 | Huawei (Lili) | MultiRx | 1 | None | ToDo |  | v066 | Should be T346m | Change to T346m |  | 5.3.7.2 Initiation
|  |  | H054 | Huawei (Lili) | MultiRx | 1 | None | ToDo |  | v066 | Should be T346m | Change to T346m |  | 5.3.13.2 Initiation
|  |  | H055 | Huawei (Lili) | MultiRx | 1 | None | ToDo |  | v066 | Should be T346m | Change to T346m |  | 5.7.4.2 Initiation
|  |  | H056 | Huawei (Lili) | MultiRx | 1 | None | ToDo |  | v066 | Should be T346m | Change to T346m |  | 5.7.4.2 Initiation
|  |  | H057 | Huawei (Lili) | MultiRx | 1 | None | ToDo |  | v066 | Inaccurate description | Prohibit timer for multi-Rx operation preference reporting operation for FR2 reporting. |  | – OtherConfig
|  |  | H058 | Huawei (Lili) | EventA2 | 1 | None | ToDo |  |  | “serving cell” should be changed to “SCell” | The note comes from CR R2-2313918. The CR wants to clarify that the NW always expects a measurement report from the UE, even if the SCell is not detected by the UE (e.g. UE is out of SCell coverage). In some cases, the NW may blindly configure an SCell to the UE, and event A2 is important for the network to evaluate the SCell quality. However, the case should not happen to PCell, and we think it’s better to clarify that the “serving cell” here refers to SCell. Solution； If the serving cellSCell indicated by the measObjectNR associated to this event is not detectable, then the UE should consider for the value of Ms the lowest value of the value range of the measurement quantity as the serving cellSCell measurement. | ZTE(LiuJing): We see the point from HW, but in theory, RLF will be declared in case PCell/PSCell degrades, so even if "serving cell" is mentioned here, it seems reporting -140dBm for (s)PCell A2 event won't happen anyway? Just wondering whether changing the word will result in different handling in UE implementation. | 5.5.4.3 Event A2 (Serving becomes worse than threshold)
|  |  | H075 | Huawei (Tong sha) | NonCol | 1 | None | ToDo |  | v138 | In RAN2#123bis, it was agreed to remove terminologies “type1” and “type2” in RAN2 specs. Currently, there is no such terminology in RAN2 spec nor RAN4 spec. Besides, we understand the UE behaviour is clear enough when the field is present/absent according to the field description. | For nonCollocatedTypeMRDC-r18 and nonCollocatedTypeNR-CA-r18, suggest to correct to ENUMERATED { true } |  | – CellGroupConfig
|  |  | H076 | Huawei (Tong sha) | NonCol | 1 | None | ToDo |  | v138 | According to the agreement in RAN2#124: For UEs supporting new capability, adopt default type2 for nonCollocatedTypeMRDC-r18. For UEs supporting new capability, adopt default type2 for nonCollocatedTypeNR-CA-r18 The MTTD/MRTD requirement according to clause 7.5.2/7.6.2 is defined with UE capability interBandMRDC-WithOverlapDL-Bands-r16 (i.e. type2 capability). When the field is absent, this requirement is applied only when the UE indicating support of interBandMRDC-WithOverlapDL-Bands-r16, otherwise, it will bring NBC. In other words, for a UE (including legacy UE and Rel-18 UE) not supporting interBandMRDC-WithOverlapDL-Bands-r16 (i.e. type1 UE), when this RRC field is absent, the UE shall not apply the type2 capability. | If this field is absent, the UE applies (NG)EN-DC MTTD/MRTD according to clause 7.5.2/7.6.2 in TS 38.133 [14] and inter-band RF requirements when indicating support of interBandMRDC-WithOverlapDL-Bands-r16. | OPPO (Qianxi): Same view as Huawei (Actually we touched upon this issue in 124 meeting, and after further internal check, we got the same view here that it should not touch upon the UE not supporting the capability). | – CellGroupConfig
|  |  | H077 | Huawei (Tong sha) | NonCol | 1 | None | ToDo |  | v138 | The MTTD/MRTD requirements according to Table 7.5.4-1/Table 7.6.4-2 and UE RF requirements for intra-band non-collocated NR-CA including 7.10A in TS 38.101-1 is defined with UE capability nonCollocatedTypeNR-CA-r18 (i.e. type2 capability). When the field is absent, this requirement is applied only when the UE indicating support of nonCollocatedTypeNR-CA-r18. In other words, for a Rel-18 not supporting nonCollocatedTypeNR-CA-r18 (i.e. type1 UE), when this RRC field is absent, the UE shall not apply the type2 capability. | If this field is absent, the UE applies MTTD/MRTD requirements according to Table 7.5.4-1/Table 7.6.4-2 in TS 38.133 [14] and UE RF requirements for intra-band non-collocated NR-CA including 7.10A in TS 38.101-1 [15] when indicating support of nonCollocatedTypeNR-CA-r18 | OPPO (Qianxi): Same view as Huawei (Actually we touched upon this issue in 124 meeting, and after further internal check, we got the same view here that it should not touch upon the UE not supporting the capability). | – CellGroupConfig
|  |  | H780 | Huawei (Jagdeep) | IDC | 1 |  | PropAgree |  | v032 | The Note 2 is for pre R18 IDC mechanism and needs to be updated for R18 IDC enhancements. | It is proposed to add the frequency ranges for the R18 IDC enhancements as shown below. NOTE 2: For the frequencies or frequency range(s) on which a serving cell or serving cells is configured that is activated, IDC problems consist of interference issues that the UE cannot solve by itself, during either active data exchange or upcoming data activity which is expected in up to a few hundred milliseconds. For frequencies or frequency range(s) on which a SCell or SCells is configured that is deactivated, reporting IDC problems indicates an anticipation that the activation of the SCell or SCells would result in interference issues that the UE would not be able to solve by itself. For a non-serving frequency or frequency range, reporting IDC problems indicates an anticipation that if the non-serving frequency or frequency range or frequencies or frequency ranges became a serving frequency or serving frequencies then this would result in interference issues that the UE would not be able to solve by itself | Xiaomi (Yumin): The proposed change is correct. Thank you | 5.7.4.2 Initiation
|  |  | H781 | Huawei (Jagdeep) | IDC | 1 |  | PropAgree |  | v032 | The description in Note 2 means that that the UE need to include all the three field , i.e. idc-assitance, idc-FDM-assistance and idc-TDM-assistance in the UE-assitance information messsage, even if the UE just report idc-FDM-assistance when it had IDC problem. Hence this needs to be corrected | It is proposed to change Note 2 as shown below. NOTE 2: Upon not anymore experiencing a particular IDC problem that the UE previously reported, the UE provides an IDC indication with the modified contents of the UEAssistanceInformation message (e.g. by not including the IDC assistance information in the idc-Assistance, or idc-FDM-Assistance and or idc-TDM-Assistance fields). | Xiaomi (Yumin): The proposed change is correct. Thank you | 5.7.4.3 Actions related to transmission of UEAssistanceInformation message
|  |  | H782 | Huawei (Jagdeep) | IDC | 1 | R2-24xxxxx | PropAgree |  | v032 | The idc-assistanceConfig is missing in the list of parameters that can be configured by SN and should be added since SN can configure it in the SN generated RRCReconfiguraiton messaage and transmit it to the UE via the MN. | It is proposed to add the missing idc-assistanceConfig in the list of fields configured by SN as shown below. otherConfig Contains configuration related to other configurations. When configured for the SCG, only fields drx-PreferenceConfig, maxBW-PreferenceConfig, maxBW-PreferenceConfigFR2-2, maxCC-PreferenceConfig, maxMIMO-LayerPreferenceConfig, maxMIMO-LayerPreferenceConfigFR2-2, minSchedulingOffsetPreferenceConfig, minSchedulingOffsetPreferenceConfigExt, rlm-RelaxationReportingConfig, bfd-RelaxationReportingConfig, btNameList, wlanNameList, sensorNameList, obtainCommonLocation, idc-assistanceConfig and uav-FlightPathAvailabilityConfig can be included | Xiaomi (Yumin): The proposed change is correct. Thank you | – RRCReconfiguration
|  |  | H783 | Huawei (Jagdeep) | IDC | 1 |  | PropAgree |  | v032 | The field description currently seems misleading for the activeDuration as it is not due to the IDC problem but rather to resolve the IDC problem. | It is proposed to change the field description as shown below. activeDuration Indicates the UE's preferred active duration to help resolve due to the IDC problem. Value in multiples of 1/32 ms (subMilliSeconds) or in ms (milliSecond). For the latter, value ms1 corresponds to 1 ms, value ms2 corresponds to 2 ms, and so on. | Xiaomi (Yumin): Agree with the issue, but suggest to use “to resolve the IDC problem” instead. Thank you. | – UEAssistanceInformation
|  |  | H784 | Huawei (Jagdeep) | IDC | 1 |  | PropAgree |  | v032 | The field description currently has a mistake. | It is proposed to change the field description as shown below. affectedCarrierFreqCombList Indicates a list of NR carrier frequencyie combinations that are affected by IDC problems due to Inter-Modulation Distortion and harmonics from NR when configured with UL CA or NR-DC. | Xiaomi (Yumin): The proposed change is correct. Thank you | – UEAssistanceInformation
|  |  | H785 | Huawei (Jagdeep) | IDC | 1 |  | PropAgree |  | v032 | The field description currently seems misleading for the cycleLength as it is not due to the IDC problem but rather to resolve the IDC problem. | It is proposed to change the field description as shown below. cycleLength Indicates the UE's preferred cycle length to help resolve due to the IDC problem. Value in ms. Value ms2 corresponds to 2 ms, value ms3 corresponds to 3 ms, and so on. | Xiaomi (Yumin): Agree with the issue, but suggest to use “to resolve the IDC problem” instead. Thank you. | – UEAssistanceInformation
|  |  | H786 | Huawei (Jagdeep) | IDC | 1 |  | PropAgree |  | v032 | The field description currently seems misleading for the slotOffset as it is not due to the IDC problem but rather to resolve the IDC problem. | It is proposed to change the field description as shown below. slotOffset Indicates the UE's preferred slot offset to help resolve due to the IDC problem, in multiples of 1/32 ms. | Xiaomi (Yumin): Agree with the issue, but suggest to use “to resolve the IDC problem” instead. Thank you. | – UEAssistanceInformation
|  |  | H787 | Huawei (Jagdeep) | IDC | 1 |  | PropAgree |  | v032 | The field description currently seems misleading for the startOffset as it is not due to the IDC problem but rather to resolve the IDC problem. | It is proposed to change the field description as shown below. startOffset Indicates the UE's preferred start offset to help resolve due to the IDC problem, in multiples of 1 ms. | Xiaomi (Yumin): Agree with the issue, but suggest to use “to resolve the IDC problem” instead. Thank you. | – UEAssistanceInformation
|  |  | H900 | Huawei (YinghaoGuo) | Pos | 1 |  | ToDo |  | v014 | Wrong field name | Correct the field name to the right name |  | 5.8.3.3 Actions related to transmission of SidelinkUEInformationNR message
|  |  | H901 | Huawei (YinghaoGuo) | Pos | 1 | R2-24xxxxx | ToDo |  |  | Currently, SL-configCommonNR is not defined as an IE, but as a type under SIB12. Should move it out of SIB12 and define as an IE. | if we still want to reuse SL-ConfigCommonNR, Define the type SL-ConfigCommonNR as an IE |  | – SIB23
|  |  | H902 | Huawei (YinghaoGuo) | Pos | 1 | R2-24xxxxx | ToDo |  |  | Currently, SL-configCommonNR is reused, but a lot of fields under the type are not needed for SL positioning. We should also examine how SIB12 and Sib23 should work together | Discuss the co-esitence between SIB12 and Sib23 and what SIB23 should contain, whether we should still use the legacy type SL-COnfigCommonNR, used for SL communications |  | – SIB23
|  |  | H903 | Huawei (YinghaoGuo) | POS | 2 | R2-24xxxxx | ToDo |  | v226 | This IE is defined but not used anywhere in the spec | Add this IE to SL-UE-SelectedConfig |  | – SL-CBR-CommonTxDedicated-SL-PRS-RP-List
|  |  | H903 | Huawei (YinghaoGuo) | POS | 2 | R2-24xxxxx | ToDo |  |  | currently, the IE SL-CBR-Comon-TxDedicated-SL-PRS-RP-List has already been defined by RAN1 and added in the RRC spec but not used. We think here it should be used for resource allocation scheme 2 for the congestion control for SL-PRS | add a new field for the Tx configuration for congestion control for SL-PRS defined by the IE SL-CBR-Comon-TxDedicated-SL-PRS-RP-List |  | – SL-UE-SelectedConfig
|  |  | I109 | Intel (Sudeep) | SON | 2 | None | ToDo |  | V71 | This is an inter-RAT HO command message. There is no delta configuration for this inter-RAT configuration in this message itself and hence no need to use setupRelease in this message. | Remove setupRelease and use Need R. | Lenovo (Hyung-Nam): Agree to remove Setup/Release type but on need code I think “Need N” is better. | – MobilityFromNRCommand
|  |  | I112 | Intel (Sudeep) | IDC | 2 | None | PropAgree |  | V71 | An extension marker is used only for FDM assistance information and not for TDM. We suggest two options – option 1) add extension marker also for TDM or option 2) define an IDC assistance information IE that groups both FDM and TDM assistance info and add extension marker to that IE. | Option 1: add extension marker to IDC-TDM-Assistance-r18. Option 2: UEAssistanceInformation-v1800-IEs ::= SEQUENCE { idc-FDM-Assistance-r18 IDC-FDM-Assistance-r18 OPTIONAL, idc-TDM-Assistance-r18 IDC-TDM-Assistance-r18 OPTIONAL, idc-Assistance-r18 IDC-Assistance-r18 OPTIONAL, multiRx-PreferenceFR2-r18 ENUMERATED {single} OPTIONAL, musim-Assistance-v1800 MUSIM-Assistance-v1800 OPTIONAL, flightPathInfoAvailable-r18 ENUMERATED {true} OPTIONAL, ul-TrafficInfo-r18 UL-TrafficInfo-r18 OPTIONAL, n3c-RelayUE-InfoList-r18 N3C-RelayUE-InfoList-r18 OPTIONAL, sl-PRS-UE-AssistanceInformationNR-r18 SL-PRS-UE-AssistanceInformationNR-r18 OPTIONAL, nonCriticalExtension SEQUENCE {} OPTIONAL } IDC-Assistance-r16 ::= SEQUENCE { affectedCarrierFreqList-r16 AffectedCarrierFreqList-r16 OPTIONAL, affectedCarrierFreqCombList-r16 AffectedCarrierFreqCombList-r16 OPTIONAL, ... } IDC-Assistance-r18 ::= SEQUENCE { idc-FDM-Assistance-r18 IDC-FDM-Assistance-r18 OPTIONAL, idc-TDM-Assistance-r18 IDC-TDM-Assistance-r18 OPTIONAL, ... } IDC-FDM-Assistance-r18 ::= SEQUENCE { affectedCarrierFreqRangeList-r18 AffectedCarrierFreqRangeList-r18 OPTIONAL, affectedCarrierFreqRangeCombList-r18 AffectedCarrierFreqRangeCombList-r18 OPTIONAL, ... } | Xiaomi (Yumin): Prefer Option 1, as “idc-Assistance” has already been used as the Rel-16 function in the procedural text | – UEAssistanceInformation
|  |  | I127 | Intel (Sudeep) | NonCol | 2 | None | ToDo |  | V71 | These two small fields using Need R in an extension group is not efficient signalling. Suggest to group both these fields into an IE and use setupRelease for that IE. | Define an IE to group this and the next field, and use setupRelease for that. | Huawei v138: ok but looks like a tiny optimization (it may save nothing or 1 byte | – CellGroupConfig
|  |  | I145 | Intel (Sudeep) | MeasSequence | 1 | None | ToDo |  | V82 | Suggest to rephrase to say "a frequency in the order of increasing values with a lowest value is measured first" to make clear that configurations do not always have to start with value 1. | Change “Value 1 means the corresponding frequency is measured firstly. Value 2 means the corresponding frequency is measured secondly and so on” to “A frequency with a lowest value is measured before a frequency with higher value” |  | – MeasObjectEUTRA
|  |  | I146 | Intel (Sudeep) | Mob | 1 | None | ToDo |  | V82 | CHO related configurations are not considered oneshot and hence cannot be Need N. Need R could be OK | Change Need N to Need R. |  | – MeasObjectNR
|  |  | I301 | Intel (Sudeep) | CIO | 2 | None | ToDo |  | V82 | As this is a list, consider setupRelease to allow delta configuration without having to include this list everytime. | Consider setupRelease | ZTE (LiuJing): We do not see much benefit of supporting delta config in ReportConfig IE, usually, when changes e.g. A3->A5, the network will release the old reportConfig ID and provide a new one. If handover is triggered, normally, the CIO values to be configured by target cell will be different from source cell. So, it is fine to always provide a complete list. | – ReportConfigNR
|  |  | I306 | Intel (Sudeep) | CIO | 2 | None | ToDo |  | V82 | As this is a list, consider setupRelease to allow delta configuration without having to include this list everytime. | Consider setupRelease | ZTE (LiuJing): We do not see much benefit of supporting delta config in ReportConfig IE, usually, when changes e.g. A3->A5, the network will release the old reportConfig ID and provide a new one. If handover is triggered, normally, the CIO values to be configured by target cell will be different from source cell. So, it is fine to always provide a complete list. | – ReportConfigInterRAT
|  |  | N001 | Jarkko T. Koskela (Nokia) | MultiRX | 3 | None | ToDo |  |  | It seems if UE needs to send UAI for some other purpose while prohibit timer is still running UE cannot include this field and absence of the field is interpreted by the NW as UE preferring multiRX. This is not likely the intention but UE should be still able to indicate preference for multi-RX | Easiest is to add also multi-RX as option for indicating preference – this way NW may consider UE preference has not changed since last sending of message. Also in 5.7.4.3 one would then delete “ 2> else (if the UE has the preference for operating on multi-Rx for FR2): 3> not include multiRx-PreferenceFR2”. See N002 for the location of this. | Ericsson-Nithin: Agree, should add another variable to the multiRx-PreferenceFR2-r18 | – UEAssistanceInformation
|  |  | N002 | Jarkko T. Koskela (Nokia) | MultiRX | 3 | None | ToDo |  |  | Relates to N001 – This procedural text here means that absence of field is interpreted by NW as preferring multi-RX. In case after sending single RX preference UE needs to send UAI for other purposes absence of multi-RXPreferenceFR2 is interpreted as UE preferring multi-RX operation which is likely not the intention. | See N001 for solution. |  | 5.7.4.3 Actions related to transmission of UEAssistanceInformation message
|  |  | N006 | Jarkko T. Koskela (Nokia) | MultiRX | 0 | None | ToDo |  |  | Probablye we are nore porting person information here but assistance | assistant -> assistance |  | – OtherConfig
|  |  | N094 | Nokia(Srinivasan) | Mob |  | None | ToDo |  |  | The lines related to indicating support for SCPAC is not clear. Because this field itself is meant for configuration of SCPAC | Presence of this field indicates that subsequent CPAC is enabled for this candidate cell. |  | – CondReconfigToAddModList
|  |  | N094 | Nokia(Srinivasan) | Mob |  | None | ToDo |  |  | The model used for reference configuration differs depending on whether it is received via MCG or SCG. The current lines may give interpretation that reference configuration contains parameter for the specific cell-group. In case of SCPAC the reference configuration if uss MN format ( sent via MCG) it contains all parts of configuration. If it is sent via SCG it refers to SCG part. These details to be clarified. | The IE ReferenceConfiguration is used to provide configuration that is common to all configured non-complete candidate configurations. If this parameter is included in the RRC message provided through Master-cell-group the RRC-Reconfiguration includes all parameters. If this parameter is included in the RRC message sent from SCG, the RRC-Reconfiguration refers to the secondary-cell-group and other related Ies only |  | – ReferenceConfiguration
|  |  | O434 | OPPO (Bingxue) | SLrelay |  | None | ToDo |  |  | U2U Remote need to check whether it has PC5-RRC connection with the target remote UE indicated in sl-PeerRemoteUE-ToReleaseList. | Different from L2 U2N Relay case, in U2U relay, the configuration from network is nottarget remote UE addition, but just configure the SRAP configuration to the existing U2U connections. So remote UE need to check whether the L2 IDs indicated are valid, i.e., has PC5-RRC connection. 1> for each L2 U2U Relay UE indicated in sl-L2IdentityRelay value included in the sl-U2U-RelayUE-ToAddModList that is part of the current UE configuration (L2 U2U Relay UE modification): 2> for each peer target L2 U2U Remote UE included in the sl-PeerRemoteUE-ToReleaseList which has PC5-RRC connection with the current UE (peer target L2 U2U Remote UE Release): 3> release the configuration associated with the peer target L2 U2U Remote UE; 2> for the peer target L2 U2U Remote UE indicated in sl-TargetUE-Identity included in the sl-PeerTargetRemoteUE-ToAddModList which has PC5-RRC connection with the current UE that is not part of the current UE configuration (peer target L2 U2U Remote UE Addition): 3> configure the parameters to SRAP entity in accordance with the sl-SRAP-ConfigU2U; 2> for the peer target L2 U2U Remote UE indicated in sl-TargetUE-Identity included in the sl-PeerTargetRemoteUE-ToAddModList which has PC5-RRC connection with the current UE that is part of the current UE configuration (peer target L2 U2U Remote UE modification): 3> modify the configuration in accordance with the sl-SRAP-ConfigU2U; |  | 5.3.5.16.2 L2 U2U Relay UE Addition/Modification
|  |  | S264 | Samsung (Milos Tesanovic) | IAB | 2 | None | ToDo |  | v135 | cg-RACH-Less-RetransmissionTimer is missing for mIAB, despite this being agreed in RAN2#124 or unify the RACH-less for IAB/LTM/NTN framework under one IE. | Introduce cg-RACH-Less-RetransmissionTimer in cg-mIAB-Configuration-r18 |  | – ConfiguredGrantConfig
|  |  | V990 | vivo-Chenli | BWPwor | 1 | None | PropAgree |  | v053 | The description for UE supporting B-1-1 to indicate no gap needs some update | UE supporting B-1-1 is a per-FS capability, while “no-gap” indication is reported in RRC complete message, which is not indicated per-band. It should be reported per-serving cell, but the current description “for the corresponding band(s)” may have some mis-understanding. Thus, it is suggested to update it as “This field shall be set to ‘no-gap’ for the serving cell(s) belongs to the corresponding band(s) where bwpOperationMeasWithoutInterrupt-r18 is supported by the UE.” | Chenli-v180: The description should be updated. Detailed wording could be discussed in CR | – NeedForGapsConfigNR
|  |  | V991 | vivo-Chenli | BWPwor | 1 | None | PropAgree |  | v053 | similar as V990, the description for UE supporting B-1-1 to indicate no gap no ncsg needs some update | similar as V990, it is suggested to update it as “This field shall be set to ‘nogap-noncsg’ for the serving cell(s) belongs to the corresponding band(s) where bwpOperationMeasWithoutInterrupt-r18 is supported by the UE.” | Chenli-v180: The description should be updated. Detailed wording could be discussed in CR | – NeedForGapNCSG-InfoNR
|  |  | V992 | vivo-Chenli | BWPwor | 1 | None | PropAgree |  | v053 | similar as V990, the description for UE supporting B-1-1 to indicate no-gap-no-interruption needs some update | similar as V990, it is suggested to update it as “This field shall be set to no-gap-no-interruption for the serving cell(s) belongs to the corresponding band(s) where bwpOperationMeasWithoutInterrupt-r18 is supported by the UE.” | Chenli-v180: The description should be updated. Detailed wording could be discussed in CR | – NeedForInterruptionInfoNR
|  |  | V993 | vivo-Chenli | BWPwor | 1 | None | PropAgree |  | v053 | Correction on NCD-SSB time offset for non-RedCap UEs in TDD | In RAN2#123bis, RAN2 has received an LS from RAN1 (R2-2311712) on NCD-SSB time offset for RedCap UEs in TDD. RAN1 has made the following agreement: “For RedCap UE in TDD, the NW ensures that the NCD-SSB time domain location is a subset of the time domain location of CD-SSB” In RAN2#124, it was agreed to capture in the spec that for RedCap UEs in TDD, the time offset needs to be restricted so that NCD-SSB coincides with CD-SSB, i.e., NCD-SSB time offset has to be a multiple of CD-SSB periodicity, in R2-2313748. The similar restriction should also be naturally applicable for non-RedCap UEs in case NCD-SSB is configured in TDD. Thus, the field description should be updated as: For RedCap UEs in TDD cells, the network configures this time offset to be an integer multiple of the periodicity of the serving cell's CD-SSB. | Chenli-v180: It is correct. The description should be updated. Detailed wording could be discussed in CR. Ericsson(Emre): What about eRedCap UEs? Should “RedCap” be replaced with “(e)RedCap” | – NonCellDefiningSSB