## Slide 1: SA WG3 Status report for CryptoSP
Mohsin Khan
Ericsson

## Slide 2
TUs planned
WT1: 1 TU (0.25 TU in each meeting cycle)
WT2 and WT3: 1 TU (0.25 TU in each meeting cycle)
Total TU estimates: 2 TU (4 meeting cycles)
In SA3#115 meeting
  Collect the proposed changes in Draft CRs
In SA3#115Adhoc-e meeting
  Collect the proposed changes in Draft CRs
In SA3#116 meeting
  Collect the proposed changes in Draft CRs
In SA3#117 meeting
  Declare the living documents frozen and only changes related to deprecating old algorithms are allowed in the living documents in the upcoming meeting.
In SA3#118 meeting
  Discuss changes (only for the changes that remove algorithms and protocols) that are already endorsed but may have serious impact if implemented and update endorsed CRs only if necessary.
In SA3#119 meeting
  Convert the living documents into regular CRs and agree the CRs
Overall plan
CryptoSP overall plan

## Slide 3
General
    What happened at SA3#117:
      Updated the baseline of the living documents
      Updated the use of implicit IV in IPSec SA in the living document to 33.210
      Declared the living documents frozen
    Focus for the Next Meeting :
      Companies sleep on the living documents and, if applicable, bring concerns related to the changes that deprecate algorithms.
Dependencies:
  None
Contentious Issue:
  None
Risks:
  None identified
CryptoSP status after SA3#116
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1020042 | 3GPP profiles for cryptographic algorithms and security protocols | CryptoSP | Rel-19 | S3 | Dec 2024 | 50% | 80% | Draft CR S3-243428 Draft CR S3-243429 Draft CR S3-243430 Draft CR S3-243431

## Slide 4
Pending issues
  Forbidding the broken use of the algorithm name aes-gcm and aes-gmac in IMS
Dependencies:
  Work based on other WGs study outcomes
TUs consumed
  SA3#115: 0.5
  SA3#115Adhoc-e: 0.5
  SA3#116: 0.5
  SA3#117: 0.5
TUs remaining
  SA3#118 – 0.5 (will most probably not be needed)
  SA3#119 – 0.5
Plan for completion
  Work item will complete in SA3#119
  The work item is taking 0.5 TU longer than initially planned. The reason is that in SA3#115, a DP was endorsed in which it was agreed that the draft CRs will be converted into regular CRs and be endorsed in SA3#117, left for discussion for one meeting cycle, i.e., SA3#118, and be finally agreed in SA3#119
CryptoSP pending work and plan for completion