## Slide 1: SA WG3 Status report for FS_5G_ProSe_Ph3_SEC
Ao Lei, Huawei
Weihan Gao, China Telecom

## Slide 2
Overall plan
FS_5G_ProSe_Ph3_SEC overall plan
Meeting | Plans | SID TU | WID TU
SA3#115ah-e (April), finished | TR skeleton, assumptions and new KIs are agreed | 0.5 | 
SA3#116 (May), finished | New solutions and KI updates are agreed | 0.5 | 
SA3#117 (August), finished | Solution update and evaluations | 0.5 | 
SA3#118 (October) | Start conclusion work | 0.75 | 
SA3#119 (November) | Finalise SID conclusions Corresponding WID proposal | 0.75 | 
SA#106 (December) | Send TR to SA for information and for approval |  | 
Prior to SA3#120 | Potentially offline session to accelerate normative work progress Offlist email discussions for prepared CRs |  | 
SA3#120 (Feb 2025) | Normative work |  | 0.5
Between SA3#120 and #121 | Offline sessions and offlist email discussions |  | 
SA3#121 (April 2025) | Finalise the Normative work |  | 0.5

## Slide 3
General
  TR 33.743 v0.3.0 contains 2 key issues and 15 solutions
Dependencies:
  SA2’s SID on FS_5G_ProSe_Ph3, TR 23.700-03 (100%)
  SA2 WID (WID on 5G_ProSe_Ph3)
    Normative work is already started
Contentious Issue:
  None
Risks:
  None identified.
FS_5G_ProSe_Ph3_SEC status after SA3#117
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1030034 | Study on Security Aspects of Enhancement for Proximity Based Services in 5GS Phase 3 | FS_5G_ProSe_Ph3_SEC | Rel-19 | S3 | Dec-2024 | 30% | 60% | TR 33.743

## Slide 4
Pending issues
  Resolves Editor‘s Notes in the solutions
  Agreement on the conclusions of KI#1 and KI#2
Dependencies:
  SA2’s work on 5G_ProSe_Ph3, TS 23.304
TUs consumed
  SA3#115ah-e – 0.5
  SA3#116 – 0.5
  SA3#117 – approx. 0.75
TUs remaining
  SA3#118 – 0.75
  SA3#119 – 0.75
Plan for completion
  SA3#119 Finalise the SID, send TR for information and approval
  SA3#121 Finalise the Normative text
FS_5G_ProSe_Ph3_SEC pending work and plan for completion