## Slide 1: SA WG3 Status report for ‘FS_AIoT_Sec’
Marcus Wong – OPPO
Longhua Guo - Huawei

## Slide 2
TUs 6
In SA3#115-Adhoc meeting: -
  Get KIs agreed
In SA3#116 meeting -
  Get KIs agreed
  Get solutions agreed
In SA3#117 meeting -
  Get Kis, architecture and assumptions agreed
  Get additional solutions and evaluations agreed
  Get initial conclusion agreed
In SA3#118 meeting -
  Get final solutions agreed
  Get more conclusions agreed
In SA3#119 meeting -
  Finalize all conclusions
  Get TR ready for SA plenary approval
Overall plan
FS_AIoT_Sec overall plan

## Slide 3
General
  61 contributions from SA3#117 – 43 not treated (~ 3/4)
Dependencies:
  SA1 guidance and clarification regarding stage 1 requirement for A-IoT taking aspects such as the business models and scope of the lifecycle management into account
  SA2 on stable architecture
  RAN on device capabilities and protocol stack
Contentious Issue:
  Authentication requirements (what use cases requires authentication, whether authentication is mandatory, whether authentication is one-way or mutual, which entity in the network to perform authentication,. secure credential storage)
  Communication security requirements cannot be agreed
  Solutions to other KI cannot be agreed due to dependencies with authentication and communication security
Risks:
  Without stable architecture from SA2 and clear SA1 guidance, authentication and communication security requirements cannot be finalized.
  Without authentication and communication security requirements, solutions to authentication and communication KI cannot be proposed or discussed.
  Not enough TU to deal with contention issues.
  Without progress on security requirements and solutions, completion of AIoT security study in R19 is jeopardized.
‘FS_AIoT_Sec status after SA3#116
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1030031 | Security of Ambient IoT services in 5G | FS_AIoT_Sec | Rel-19 | S3 | Nov-2024 | 30% | 35% | +5%

## Slide 4
Pending issues
  Issue#1: authentication requirement (e.g., network entity for authentication, use case for authentication, mandatory vs optional, one-way vs mutual authentication, secure credential storage, authentication in 3GPP layer vs application layer)
  Issue#2: there is no agreement on communication security requirement (e.g., termination points of communication)
Dependencies:
  SA2 on stable architecture
  RAN on device capabilities and protocol stack
  SA1 guidance and clarification regarding stage 1 requirement for A-IoT taking aspects such as the business models and scope of the lifecycle management into account
TUs consumed
  SA3#115 AdHoc – 1 TU
  SA3#116 – 2 TU
  SA3#117 – 2 TU
TUs remaining
  SA3#118 - 1 TU
  SA3#119 - 1 TU
Plan for completion
  Pre-SA3#118: conference call(s) prior to the meeting #118 to progress untreated contributions, focus on solutions
  SA3#118: Refine and finalize security requirements for authentication and communication, focus on solution proposals, evaluations and initial conclusions on KIs.
FS_AIoT_Sec pending work and plan for completion