## Slide 1: SA WG3 Status report for FS_EDGE_Ph3
Ge Yao (China Unicom)
Bo Zhang (Huawei)

## Slide 2
TUs planned
  TU estimates and dependencies
  Total TU estimates for the study phase: 4
  Total TU estimates for the normative phase: 2
  Total TU estimates: 6
In SA3#116 meeting:
  KI on UE info verification agreed
In SA3#117 meeting:
  All KIs and solution to be proposed.
In SA3#118 meeting:
  Solution, evaluation, and its conclusion have to be achieved.
In SA3#119 meeting:
  Normative work in TS 33.501, or TS 33.558
FS_EDGE_Ph3 overall plan
Work Task ID | TU Estimate (Study) | TU Estimate (Normative) | RAN Dependency (Yes/No/Maybe) | Inter Work Tasks Dependency
Objective #1 | 0.5TU | 0.25 TU | No | No
Objective #2 | 1 TU | 0.25 TU | No | No
Objective #3 | 1TUs | 0.5 TU | No | No
Objective #4 | 1.5TUs | 1TU | No | No

## Slide 3
General
  TR 33.749 v0.3.0 contains scope, 2 key issues and 8 solutions.
Dependencies:
  SA2 WID ("WID on Enhancement of support for Edge Computing in 5G Core network - Phase 3")
    Normative work is ablout to start
  SA6 WID (TS 23.558: "Architecture for enabling Edge Applications")
    Normative work is already started
Contentious Issue:
  For the new KI#1.1, security requirements need to be defined.
Risks:
  None identified
FS_EDGE_Ph3 status after SA3#117
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1030036 | Study on Security Aspects of Enhancement of Support for Edge Computing in 5GC phase 3 | FS_EDGE_Ph3 | Rel-19 | S3 | December 2024 | 30% | 60% | 1 new KI 7 new Solutions

## Slide 4
Pending issues
  None
TUs consumed
  SA3#115 Adhoc-e - 0.5 TU
  SA3#116 - 0.5 TU
  SA3#117 - 0.5 TU
TUs remaining
  SA3#118, 119 - 2.5 TU
Plan for completion
  SA3#119
FS_EDGE_Ph3 pending work and plan for completion