## Slide 1: SA WG3 Status report for FS_eZTS
Sheeba Backia Mary B.
Lenovo

## Slide 2
26th Feb – 1st Mar meeting (SA3#115, Greece):
  Agreed aspects: (i) Skeleton-Scope (Stable); (ii) Security Assumptions (Initial); (iii) 4 Usecases to identify data (relevant for security evaluation & monitoring) (Initial); (iv) 1 usecase (relevant to dynamic policy enforcement) (Close to Stable); (v) Partial KI#1 (Initial); and (vi) Annex (Known API Security Risks).
15th – 19th April Meeting (SA3#115-Adhoc-e):
  Agreed aspects: (i) Security Assumptions (Stable); (ii) 4 (existing) + 1 (new) Usecases to identify data (relevant for security evaluation & monitoring) (Close to Stable); (iii) 1 usecase (relevant to dynamic policy enforcement) (Stable); (iv) KI#1 (Stable) ; and (v) Partial New KI#2 (Initial).
20th – 24th May Meeting (SA3#116, Korea):
  Agreed aspects: (i) 5 (existing) + 1 (new) Usecases to identify data (relevant for security evaluation & monitoring) (Close to Stable); ; (ii) Candidate Solutions for KI#1 agreed with ENs (Initial); (iii) KI#2 complete (Stable);
19th – 23rd August Meeting (SA3#117, NL):
  Agreed aspects: New Usecase with EN added. Most of KI#1 Solutions were fully evaluated, and new solutions were partially evaluated (Almost Stable); Conclusions for KI#1 (Initial/Close to stable); KI#2 Solutions agreed, but evaluation is TBD;
14th – 18th Oct Meeting (SA3#118, India):
  Focus to achieve: KI#2 Solutions evaluations (Stable), Conclusions for KI & 2 (Stable), TR Clean-up, Send TR 33.794 for approval to SA#106 in Dec 2024.
  WID Proposal for discussion and approval
11th – 15th Nov Meeting (SA3#119, US):
  Focus to achieve: Initiate and Progress Normative Work
17th – 21st Feb Meeting (SA3#120, Athens):
  Focus to achieve: Stabilize the Normative Work
07th – 11th April Meeting (SA3#121, Goteborg):
  Focus to achieve: Cleanup and Complete the Normative Work
FS_eZTS Status Over-all Plan
TU estimates
Total TU estimates for the study phase: 2.5 TUs (5 meeting cycles)
Total TU estimates for the normative phase: 1 TUs (3 meeting cycles)
Buffer TU: .5 TU
Total TU Estimates: 4 TUs

## Slide 3
Key Issues | Solutions | Solution status
KI#1: Data exposure for security evaluation and monitoring | Solution #1, #2, #3, #4, #5, #6, #7 and #8 | Solutions stable and almost evaluated. Few new solutions approved in SA3#117 have EN. Initial Conclusions provided.
KI#2: Security mechanisms for policy enforcement at the 5G SBA | Solution #9, #10, #11 and #12 | Solution evaluations to be done
TR 33.794 Summary
FS_eZTS Status
SA3#115 Feb-March 2024
Agreed: Skeleton, Scope, Partly  security assumptions, usecases, and 1 KI. Additional info in Annex.
SA3#115-Adhoc-e April 2024
Almost stabilized Usecases, KIs and Security assumptions.
New Usecase, KI#1 completed & KI#2 Initiated.
SA3#116 May 2024
Progressed with KI#1 Solutions. Stabilized KI#2. Stabilized usecases for data collection.
[Last Meeting for New KIs]
SA3#117 Aug 2024
Solutions almost stable for KI#1.
Solutions partially stable for KI#2.
KI#1 Initiate Conclusion.
[Last Meeting for New Solutions to KIs]
SA3#118 Oct 2024
Solutions stable for KI#1 & KI#2.
Conclude all KIs and TR clean-up.
Send for TR for Approval.
Initiate WID proposal
SA3#119 Nov 2024 Initiate Normative work.
SA3#120 Feb 2025
Progress and stabilize Normative work.
SA3#121 April 2025
Complete and Cleanup Normative work.

## Slide 4
General
  TR 33.794 v0.3.0 contains the following aspects.
    Scope (Complete)
    Security Assumptions (Stable)
    7 Usecases - Use cases for security evaluation and monitoring (Almost Stable)
      Use case #1: Information on Malformed Message
      Use case #2: Massive number of SBI Messages
      Use case #3: Unauthorized/unauthenticated NF service access request
      Use case #4: Service discovery
      Use case #5: Reconnaissance
      Use case #6: API Security Risks
      Use case #7: Attacks on network slices (Have EN)
    1 Usecase - Security mechanism for dynamic policy enforcement (Stable)
      Use Case #1: Access control decision enhancement
    2 Key Issues and solutions (Almost Stable)
      Key Issue #1: Data exposure for security evaluation and monitoring
        8 candidate solutions agreed – Almost evaluated and only new solutions evaluation is TBD
        Initial Conclusion provided – with working agreement #63
      Key Issue #2: Security mechanisms for policy enforcement at the 5G SBA –
        4 candidate solutions agreed – Evaluation is TBD.
    Annex - Known API Security Risks
Dependencies:
  None (the SID has no RAN impacts)
FS_eZTS status after SA3#117
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1020034 | Study on enablers for Zero Trust Security | FS_eZTS | Rel-19 | S3 | Dec 2024 | 50% | 75% | TR 33.794

## Slide 5: FS_eZTS status after SA3#117
  SA2/RAN impacts and dependencies:
  None for RAN.
  SA2 – For KI#1 solutions, architectural aspects of the 5GS may need to be confirmed by SA WG2.
Contentious Issue:
  Initial Key Issue #1 Conclusion related contention was resolved with working agreement #63.
    If any further contention arises in further finalizing the KI#1 aspects (i.e., security events data exposure to Operator’s security function), it may impact the overall progress of the work.
Focus for the Next Meeting :
  Mainly KI#2 solution evaluations completion
  KI#1 & KI#2 conclusions
Overall Plan:
  See dedicated slide (No. 2).
Risks:
  Same as contentious issue above.