## Slide 1: SA WG3 Status report for ‘FS_MASSS_Sec’
Abhijeet Kolekar
Intel

## Slide 2
Meeting | Plan | Comments | TU SID | TU WID
SA3#115-AdHoc-e | Key Issues |  | 0.5 | 
SA3#116(May) | Key Issue Updates and Solutions |  | 0.5 | 
SA3#117(August) | Closure of the SID | 3 Editor’s Notes are still left to be removed | 0.5 | 
SA#105(September) | Send TR for Information |  |  | 
SA3#118 | Closure of SID(Remove 3 Ens) |  |  | 
SA3#119 | NO Normative Work |  |  | 
SA#106 | Send TR for Approval |  |  | 
Overall plan
‘FS_MASSS_Sec’ overall plan

## Slide 3
General
  Contains 2 key issues and 8 Solutions
Dependencies:
  No
Contentious Issue:
  None
Risks:
  None
‘FS_MASSS_Sec’ status after SA3#116
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1030037 | Study on security aspects for Multi-Access (DualSteer + ATSSS Ph-4) | FS_MASSS_Sec | Rel-19 | S3 | Mar-2024 | 45% | 95% | TR 33.754

## Slide 4
Pending issues
Dependencies:
  No
TUs consumed
  SA3#116- 1.0, SA3#117 – 0.5
TUs remaining
  0
Plan for completion
  SA3#117 : Closure of the SID as no conclusion reached in SA2
‘FS_MASSS_Sec’ pending work and plan for completion