## Slide 1: SA WG3 Status report for ‘FS_CAPIF_Ph3-sec’
Henry Leung
Xiaomi
Niraj Rathod
Ericsson

## Slide 2
TUs planned: 2.5
In SA3#117 meeting
  Get KIs agreed
In SA3#118 meeting
  Add solutions, evaluation
  Last meeting to add KIs
In SA3#119 meeting
  Add/update solution, add/update evaluation and conclusions
  WID proposal
In SA3#120 meeting
  Send TR for approval
  Normative work
In SA3#121 meeting
  Review/revise Normative work
In SA3#122 meeting
  Finalise the normative text
Overall plan
’ FS_CAPIF_Ph3-sec’ overall plan

## Slide 3
General
  TR 33.700-22 v0.1.0 contains 5 key issues.
Dependencies:
  Finer granularity authorization depends on SA6 requirements.
Contentious Issue:
  None
Risks:
  None
‘FS_CAPIF_Ph3-sec’ status after SA3#117
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1040025 | Study on security aspects of CAPIF Phase3 | FS_CAPIF_Ph3-sec | Rel-19 | S3 | Nov-2024 | 0% | 20% | 5 key issues are added.

## Slide 4
Pending issues
  None
Dependencies:
  None
TUs consumed
  SA3#117- 1 TU
TUs remaining
  1.5 TU
Plan for completion
  SA3#120 Send TR for approval
  SA3#122 Finalise the normative text
‘FS_CAPIF_Ph3-sec’ pending work and plan for completion