## Slide 1
SA WG3 Status report for ‘FS_AIoT_Sec’
Marcus Wong – OPPO
Longhua Guo - Huawei

## Slide 2
In SA3#115-Adhoc meeting: -
  Get KIs agreed
In SA3#116 meeting -
  Get KIs agreed
  Get solutions agreed
In SA3#117 meeting -
  Get Kis, architecture and assumptions agreed
  Get additional solutions and evaluations agreed
  Get initial conclusion agreed
In SA3#118 meeting -
  Get final solutions agreed
  Get more conclusions agreed
In SA3#119 meeting -
  Finalize all conclusions
  Get TR ready for SA plenary approval
In SA3#119 Ad Hoc meeting -
  Get conclusions Agreed
In SA3#120 meeting -
  Get conclusions Agreed, TR ready for March SA plenary approval
FS_AIoT_Sec overall plan – 6 TU

## Slide 3
General
  59 contributions from SA3#118
  71 contributions from SA3#119 – 14 not treated ( ~ 20%)
Dependencies:
  SA1 guidance and clarification regarding stage 1 requirement for A-IoT taking aspects such as the business models and scope of the lifecycle management into account
  SA2 on stable architecture and conclusions
  RAN on device capabilities and protocol stack
Contentious Issue:
  Conclusions all 5 KIs
  Solutions and KI with too many editor’s notes
  Companies are still trying to bring new KI to the studies
Risks:
  Not enough TU to deal with contention issues.
  Without stable architecture from SA2 and clear SA1 guidance on business model, termination point for authentication and communication cannot be finalized.
  Without authentication and communication security KI conclusions, other Kis cannot conclude.
‘FS_AIoT_Sec status after SA3#116
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1030031 | Security of Ambient IoT services in 5G | FS_AIoT_Sec | Rel-19 | S3 | Nov-2024 March-2025 | 35% | 55% | +20%

## Slide 4
Pending issues
  Issue#1: authentication requirement (e.g., network entity for authentication, use case for authentication, mandatory vs optional, one-way vs mutual authentication, secure credential storage, authentication in 3GPP layer vs application layer)
  Issue#2: there is no agreement on communication security requirement (e.g., termination points of communication)
  KI conclusions on communication and disabling/enabling RF capability depends on authentication KI conclusion
Dependencies:
  SA2 on final architecture and conclusion
  RAN on device capabilities and protocol stack
  SA1 guidance and clarification regarding stage 1 requirement for A-IoT taking aspects such as the business models and scope of the lifecycle management into account
TUs consumed
  SA3#115 AdHoc – 1 TU
  SA3#116 – 2 TU
  SA3#117 – 2 TU
  SA3#118 – 3 TU
  SA3#119 – 2 TU
TUs remaining
  SA3#119 Adhoc - 0 TU
  SA3#120 - 0 TU
Plan for completion
  SA3#119AdHoc: get conclusions agreed
  SA3#120: Finalize all conclusions, get TR ready, submit to March 2025 SA plenary for approval
FS_AIoT_Sec pending work and plan for completion