## Slide 1: SA WG3 Status report for FS_eZTS
Sheeba Backia Mary B.
Motorola Mobility

## Slide 2
26th Feb – 1st Mar meeting (SA3#115, Greece):
  Agreed aspects: (i) Skeleton-Scope (Stable); (ii) Security Assumptions (Initial); (iii) 4 Usecases to identify data (relevant for security evaluation & monitoring) (Initial); (iv) 1 usecase (relevant to dynamic policy enforcement) (Close to Stable); (v) Partial KI#1 (Initial); and (vi) Annex (Known API Security Risks).
15th – 19th April Meeting (SA3#115-Adhoc-e):
  Agreed aspects: (i) Security Assumptions (Stable); (ii) 4 (existing) + 1 (new) Usecases to identify data (relevant for security evaluation & monitoring) (Close to Stable); (iii) 1 usecase (relevant to dynamic policy enforcement) (Stable); (iv) KI#1 (Stable) ; and (v) Partial New KI#2 (Initial).
20th – 24th May Meeting (SA3#116, Korea):
  Agreed aspects: (i) 5 (existing) + 1 (new) Usecases to identify data (relevant for security evaluation & monitoring) (Close to Stable); ; (ii) Candidate Solutions for KI#1 agreed with ENs (Initial); (iii) KI#2 complete (Stable);
19th – 23rd August Meeting (SA3#117, NL):
  Agreed aspects: New Usecase with EN added. Most of KI#1 Solutions were fully evaluated, and new solutions were partially evaluated (Almost Stable); Conclusions for KI#1 (Initial); KI#2 Solutions agreed, but evaluation is TBD;
14th – 18th Oct Meeting (SA3#118, India):
  Agreed aspects: KI#2 Solutions evaluations (Stable), Conclusions for KI & 2 (Close to Stable).
  WID Proposal provided for discussion
11th – 15th Nov Meeting (SA3#119, US):
  Agreed aspects: 1 new solution for KI#1 added. Concluded KI & 2 (Complete), TR cleanup and sent for Plenary Approval.
  But WID couldn’t be agreed – no consensus.
17th – 21st Feb Meeting (SA3#120, Athens):
  Focus to achieve: WID Approval. Initiate and Progress Work.
07th – 11th April Meeting (SA3#121, Goteborg):
  Focus to achieve: Cleanup and Complete the Work
FS_eZTS Status Over-all Plan
TU estimates
Total TU estimates for the study phase: 2.5 TUs (5 meeting cycles)
Total TU estimates for the normative phase: 1 TUs (3 meeting cycles)
Buffer TU: .5 TU
Total TU Estimates: 4 TUs

## Slide 3
Key Issues | Solutions | Solution status
KI#1: Data exposure for security evaluation and monitoring | Solution #1, #2, #3, #4, #5, #6, #7, #8, and #13 | 9 Solutions stable and evaluations completed. Conclusion completed The key issue will be addressed by requirements for data collection to enable security evaluation and monitoring on the SBA layer.
KI#2: Security mechanisms for policy enforcement at the 5G SBA | Solution #9, #10, #11 and #12 | 4 Solutions stable and evaluations completed. Conclusion completed No normative work is needed for KI#2. For security policy enforcement and improved access control decisions based on security evaluation and monitoring results aspects are described in TR 33.794.
TR 33.794 Summary
FS_eZTS Status

## Slide 4
General
  TR 33.794 v0.6.0 contains the following aspects.
    Scope
    Security Assumptions
    7 Usecases - Use cases for security evaluation and monitoring
      Use case #1: Information on Malformed Message
      Use case #2: Massive number of SBI Messages
      Use case #3: Unauthorized/unauthenticated NF service access request
      Use case #4: Service discovery
      Use case #5: Reconnaissance
      Use case #6: API Security Risks
      Use case #7: Attacks on network slices
    1 Usecase - Security mechanism for dynamic policy enforcement
      Use Case #1: Access control decision enhancement
    2 Key Issues and solutions [Concluded]
      Key Issue #1: Data exposure for security evaluation and monitoring
        9 candidate solutions agreed, and KI#1 concluded
      Key Issue #2: Security mechanisms for policy enforcement at the 5G SBA –
        4 candidate solutions agreed, and KI#2 concluded
      Annex - Known API Security Risks
Dependencies:
  None (the SID has no RAN impact)
FS_eZTS status after SA3#119
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1020034 | Study on enablers for Zero Trust Security | FS_eZTS | Rel-19 | S3 | Dec 2024 | 75% | 95% | TR 33.794

## Slide 5: FS_eZTS status after SA3#119
  SA2/RAN impacts and dependencies:
  None.
Contentious Issue:
  No consensus on WID [to do 900 series TR vs Normative Text]
Focus for the Next Meeting :
  WID Proposal.
Overall Plan:
  See dedicated slide (No. 2).
Risks:
  Same as contentious issue above.