## Slide 1: SA WG3 Status report for ‘NR_Mob_Ph4_Sec’
Rajavelsamy R(Samsung)

## Slide 2
TUs planned
In SA3#117 meeting:
  1 new Key issue approved (Security aspects of inter-CU LTM Handover)
  9 new solutions (for KI#1, no DC scenario) were approved
In SA3#118 meeting:
  Solution updates(s) (for KI#1 (no DC scenario))
  Conclusion made for “CU is acting as SN and MN is unchanged” scenario and LS reply to RAN WGs
  LS to RAN2 to indicate SA3 preferred options (for no DC scenario) and requested RAN2 feedback
In SA3#119 meeting:
  Partial conclusion on “no DC scenario”, specifically for the parameters in AS security context, which are not changing per inter-CU LTM handover
  Conclusion on MAC CE protection (no solution for Rel-19)
In SA3#120 meeting:
  Update to KI#1 based on RAN progress is expected
  Conclusion for “no DC” scenario and LS reply to RAN WGs
  New KI(s) based on RAN agreed scenarios (for example, Conditional LTM) is expected
  Further Conclusion and Normative text proposals based on conclusion(s)
‘NR_Mob_Ph4_Sec’ overall plan
Work Task ID | TU Estimate (Study) | TU Estimate (Normative)
WT1 | -- | 4

## Slide 3
General
  draftCR Annex contains 1 key issue and 9 solutions for LTM (no Dual Connectivity) .
  Solution evaluation & Conclusion needs another meeting cycle, awaiting RAN2 feedback.
  Conclusion on the scenario “CU is acting as SN and MN is unchanged” to use SCPAC
  Partial conclusion on “no DC scenario”, specifically for the parameters in AS security context, which are not changing per inter-CU LTM handover
Dependencies:
  SA3 work depends on the work progress in RAN WGs.
Contentious Issue:
  None
Risks:
  Completing the normative work within timeline
NR_Mob_Ph4_Sec status after SA3#119
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1040023 | Security aspects of NR mobility enhancement Phase 4 | NR_Mob_Ph4_Sec | Rel-19 | S3 | Mar-2025 | 20% | 60% | -

## Slide 4
Pending issues
  Evaluation and Conclusion for KI#1
Dependencies:
  SA3 work depends on the work progress in RAN WGs.
TUs consumed
  SA3#117 - 1 TU
  SA3#118 – 1 TU
  SA3#119 – 1 TU
TUs remaining
  SA3#120 – 1 TU
Plan for completion
  SA3#120
NR_Mob_Ph4_Sec: Pending work and plan for completion