## Slide 1: SA WG3 Status report for FS_Energy_SEC
Bo Bjerrum
Nokia
Ferhat Karakoc
Ericsson

## Slide 2
Meeting | Deadlines | Notes | TU SID | TU WID
SA3#115-ADHOC (April) |  |  | 0.5 | 
SA3#116 (May) | Last meeting for new KI’s |  | 0.5 | 
SA3#117 (August) |  |  | 0.5 | 
SA#105 (September) |  | Send TR to SA for information (Delayed due to missing SA/2/5 agreement on exposure architecture) |  | 
SA3#118 (October) | Last meeting for new solution (Extended due to delay) |  | 0.5 | 
SA3#119 (November) | Last meeting for new solution |  | 0.5 | 
SA3#119 AdHoc (January) |  | Conclude KI#1 and KI#2 | 0.5 | 
SA3#120 (Feb - 2025) | Closure of SID |  |  | 
SA#107 (March) |  | Send TR for information and approval |  | 
SA3#121 (April - 2025) | Normative work |  |  | 0.5
Overall plan
FS_Energy_SEC Status

## Slide 3
General
  TR 33.766 v0.5.0 contains 2 key issues and 5 solutions
Dependencies:
  SA2’s work on FS_EnergySys, TR 23.700-66
  Conclusion on architectural direction for exposure.
FS_Energy_SEC status after SA3#119
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1030038 | Study on security aspects of energy saving in 5G | FS_Energy_SEC | Rel-19 | S3 | March-2025 | 70% | 90 % | TR 33.766

## Slide 4: FS_Energy_SEC status after SA3#119
  SA2/RAN impacts and dependencies:
  SA2 has concluded their study without a clear architectural direction. During normative work, the direction is not clear either.
Contentious Issue:
  None
Next plan:
  Concluded the study and send it for approval.
Risks:
  If architectural direction for exposure cannot be agreed the study will be delayed.