## Slide 1: SA WG3 Status Report for ACME_SBA
Charles Eckel, Cisco Systems

## Slide 2
ACME_SBA Overall Plan
Meeting | Plans | SID TU | WID TU
SA3#115 (Feb 2024) | Initial version of TR 33.776 with introduction, scope, and five key issues | 0.5 | 
SA3#116 (May 2024) | Two new key issues, solutions for several key issues, and initial evaluations for a few key issues | 0.5 | 
SA3#117 (Aug 2024) | Solutions for all but one key issues and progress on evaluations | 0.5 | 
SA3#118 (Oct 2024) | Solution for remaining key issues, additional solutions and evaluations, start of conclusions | 0.5 | 
SA3#119 (Nov 2024) | Study complete and work item agreed for corresponding normative work | 0.5 | 
SA#106 (Dec 2024) | Sent TR to SA for information and for approval |  | 
SA3#120 (Feb 2025) | Normative work started, draft-CR skeleton and main content agreed |  | 0.5
SA#107 (March 2025) | Send Work Item Exception Sheet to SA for approval |  | 
SA3#121 (April 2025) | Complete normative work |  | 0.5
SA3#122 (May 2025) | Minor maintenance of normative work |  | < 0.5
SA#108 (June 2025) | Send CR to SA for approval |  | 

## Slide 3
General
  Normative work complete.
Dependencies:
  None.
Contentious Issue:
  None identified.
Risks:
  None identified.
ACME_SBA Status after SA3#120
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1060066 | WID on Automatic Certificate Management Environment (ACME) for the Service Based Architecture (SBA) | ACME_SBA | Rel-19 | S3 | Jun-2025 | 55% | 100% | Normative work complete. CR to TS 33.310 ready for approval.

## Slide 4
Pending issues
  None.
Dependencies:
  None.
TUs consumed
  SA3#121: 0.4
  SA3#122: 0.1
TUs remaining
  None.
Plan for completion
  Normative work complete.
ACME_SBA Pending Work and Plan for Completion