## Slide 1: SA WG3 Status Report for 5G_ProSe_Ph3_SEC
Ao Lei, Huawei
Weihan Gao, China Telecom

## Slide 2
Overall plan
5G_ProSe_Ph3_SEC Overall Plan
Meeting | Plans | SID TU | WID TU
SA3#115ah-e (April), finished | TR skeleton, assumptions and new KIs are agreed | 0.5 | 
SA3#116 (May), finished | New solutions and KI updates are agreed | 0.5 | 
SA3#117 (August), finished | Solution update and evaluations | 0.5 | 
SA3#118 (October) | Start conclusion work | 0.75 | 
SA3#119 (November) | Finalise SID conclusions Corresponding WID proposal | 0.75 | 
SA#106 (December) | Send TR to SA for information and for approval |  | 
SA3#120 (Feb 2025) | Normative work and TR maintenance |  | 0.5
SA3#121 (April 2025) | Finalise the Normative work and preparation for SA approval |  | 0.5

## Slide 3
General
  The EN clean up of WID proposal has been approved at SA3#122.
Dependencies:
  None.
Contentious Issue:
  None identified.
Risks:
  None identified.
5G_ProSe_Ph3_SEC Status after SA3#122
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1060057 | WID on Security Aspects of Proximity Based Services in 5GS Phase 3 | 5G_ProSe_Ph3_Sec | Rel-19 | S3 | Jun-2025 | 95% | 100% | 

## Slide 4
Pending issues
  None.
Dependencies:
  None.
TUs consumed
  SA3#122 -> 0.1
TUs remaining
  None.
Plan for completion
  None.
5G_ProSe_Ph3_SEC Pending Work and Plan for Completion