## Slide 1: SA WG3 Status report for UAS3
Markus Hanhisalo
Ericsson

## Slide 2
TUs planned
  Total TU estimates for the study phase: 1.5
  Total TU estimates for the normative phase: 1.5
  Total TU estimates: 3
In SA3#115Ad-hoc meeting:
  One KI approved
In SA3#116 meeting
  4 KI1 solutions were approved
In SA3#117 meeting
  2 KI1 solutions were approved
  Evaluations approved
In SA3#118 meeting
  1 new solution was approved (S3-244426)
  Evaluations approved (S3-244380, S3-244381)
  KI1 was concluded (S3-244427)
  TR 33.759 0.4.0 (S3-243830)
In SA3#119 meeting
  2 new solutions were approved (S3-245256, S3-245257) and one solution update (S3-244842)
  TR 33.759 0.5.0 (S3-245194) was sent to TSG for information and approval
  The WID on UAS security enhancements (S3-245321) was agreed in SA3#119
In SA3#120 meeting
  9 CR contributions but no agreement for the normative CR
  The plan is to finish work in SA3#121 in Goteborg
In SA3#122 meeting in Fukuoka UAS3 work was finished and CR was sent for approval
Overall plan
UAS3 overall plan

## Slide 3
General
  TR scope has been set
  TR overview and security assumptions have been set
  Key Issue for security enhancements to NEF services in support of multiple USSs has been set
  7 solutions agreed, one new solutions was agreed in SA3#118 (S3-244426)
  Evaluations agreed (S3-244380, S3-244381)
  Conclusion agreed (S3-244427)
Dependencies:
  SA2’s study work on UAS TR 23.700-59
Contentious Issue:
  None
Risks:
  None identified
UAS3 status after SA3#118
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1030033 | Security of Uncrewed Aerial Systems (UAS) Phase 3 | FS_UAS_Ph3_Sec | Rel-19 | S3 | Mar-2024 | 50% | 100% | pCRs to TR 33.759

## Slide 4
General
  TR is ready and completed, it has one key issue, 9 solutions and it has been concluded
  It has one Key Issue for security enhancements to NEF services in support of multiple USSs
  9 solutions, two new solutions were approved in SA3#119 (S3-245256, S3-245257) and one solution update (S3-244842)
  Evaluations are done
  Editor’s Notes were changed to Notes
  Conclusion was approved in SA3#118 meeting (S3-244427)
  Presentation of Report to TSG: TR 33.759 'Study on security enhancements of Uncrewed Aerial Systems (UAS) Phase 3', Version 1.0.0 (S3-245370) was approved
Dependencies:
  SA2’s study work on UAS TR 23.700-59
Contentious Issue:
  None
Risks:
  None identified
UAS3 status after SA3#119
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1030033 | Security of Uncrewed Aerial Systems (UAS) Phase 3 | FS_UAS_Ph3_Sec | Rel-19 | S3 | Mar-2024 | 100% | % | pCRs to TR 33.759

## Slide 5
General
  Normative work started at SA3#120. There were 9 CR proposals for the normative work. Only one CR was agreed at the SA3#120 meeting.
  The plan is to finish the normative work at the next SA3#121 meeting in Goteborg.
  Exception sheet was sent to SA March plenary (S3-251165). New expected completion date is June 2025.
Dependencies:
  SA2’s work item on UAS TS 23.256
Contentious Issue:
  In USS changeover procedure during a UAV flight from USS1 to USS2, who triggers the UUAA, is it UAV or USS2 and is it UUAA or re-auth that is triggered (TS 23.256 clause 5.13.2, step 20).
Risks:
  None identified
UAS3 status after SA3#120
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1030033 | Security of Uncrewed Aerial Systems (UAS) Phase 3 | FS_UAS_Ph3_Sec | Rel-19 | S3 | Mar-2025 | 100% | % | TR 33.759
1060058 | Security of Uncrewed Aerial System Phase 3 | UAS_Ph3_Sec | Rel-19 | S3 | Mar-2025 | 0% | 5% | CR to TS 33.256

## Slide 6
General
  Group agreed one merged draft CR for TS 33.256 for normative work.
  The plan is to send it for approval at the SA3#122 meeting in Fukuoka.
  Expected completion date is June 2025.
Dependencies:
  SA2’s work item on UAS TS 23.256
Contentious Issue:
  In USS changeover procedure during a UAV flight from USS1 to USS2, who triggers the UUAA, is it UAV or USS2 and is it UUAA or re-auth that is triggered (TS 23.256 clause 5.13.2, step 20).
Risks:
  None identified
UAS3 status after SA3#121
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1030033 | Security of Uncrewed Aerial Systems (UAS) Phase 3 | FS_UAS_Ph3_Sec | Rel-19 | S3 | Mar-2025 | 100% | % | TR 33.759
1060058 | Security of Uncrewed Aerial System Phase 3 | UAS_Ph3_Sec | Rel-19 | S3 | Mar-2025 | 0% | 90% | Draft CR to TS 33.256

## Slide 7
General
  The group agreed one merged CR “S3‑252314 Adding support for multiple USSs” for TS 33.256. Normative work is done.
  LS on USS changeover procedure was sent to SA2 to ask clarification on whether the UAV can trigger the UUAA procedure in case of the USS changeover and whether the UAV after receiving the instruction from the serving USS can execute the UUAA procedure with the new USS (USS 2). LS: S3‑252263
Dependencies:
  SA2’s work item on UAS TS 23.256
Contentious Issue:
  Whether the UAV can trigger the UUAA procedure in case of the USS changeover and whether the UAV after receiving the instruction from the serving USS can execute the UUAA procedure with the new USS (USS 2). (TS 23.256 clause 5.13.2, step 20).
Risks:
  None identified
UAS3 status after SA3#122
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1030033 | Security of Uncrewed Aerial Systems (UAS) Phase 3 | FS_UAS_Ph3_Sec | Rel-19 | S3 | Mar-2025 | 100% | % | TR 33.759
1060058 | Security of Uncrewed Aerial System Phase 3 | UAS_Ph3_Sec | Rel-19 | S3 | Mar-2025 | 0% | 95% | CR to TS 33.256

## Slide 8
Pending issues
  In USS changeover procedure during a UAV flight from USS1 to USS2, who triggers the UUAA, is it UAV or USS2 (TS 23.256 clause 5.13.2, step 20).
Dependencies:
  SA2’s work on UAS TS 23.256
TUs consumed
  SA3#121 – 0,3
  SA3#122 – 0,2
TUs remaining
  SA3#123 – 0,5
Plan for completion
  The plan is to wait SA2’s response for the LS at the next SA3#123 meeting in Goteborg in August 2025 and based on the response handle the remaining Editor’s Note.
UAS3 pending work and plan for completion