## Slide 1: SA WG3 Status report for 5GSAT_Ph3_SEC
Wei Zhou, CATT
Bhatt Rakshesh P., Nokia

## Slide 2
Meeting plan
  Meeting 1 (SA3#120 2025-02-17 2025-02-21 Athens, GR)
    TS skeleton + Content
  Meeting 2 (SA3#121 2025-04-07 2025-04-11 Goteborg, SE)
    TS skeleton + Content
  Meeting 3 (SA3#122 2025-05-19 2025-05-23 Fukuoka, JP)
    Content finalization
3 TUs planned
Overall plan
5GSAT_Ph3_SEC overall plan

## Slide 3
General
  New definitions have been set.
  Security for Store and Forward Satellite operation is organized in a new annex.
  Normative content is in the "General" sub clause.
  Security aspects of Split MME architecture are in an informative sub clause.
  Security aspects of Full EPC in each satellite are in an informative sub clause.
Dependencies:
  None
Contentious Issue:
  None
Risks:
  None identified
5GSAT_Ph3_SEC status after SA3#120
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1060065 | Security Aspects of 5G Satellite Access Phase 3 | 5GSAT_Ph3_SEC | Rel-19 | S3 | June-2025 | 35% | 100% | TS 33.401

## Slide 4
Pending issues
  None
Dependencies:
  None
TUs consumed
  3 TUs used by SA3#120, SA3#121 and SA3#122
TUs remaining
  None
Plan for completion
  None
5GSAT_Ph3_SEC pending work and plan for completion