## Slide 1: SA WG3 Status report for ‘AIML_CN_SEC’
Chang Liu (China Mobile)
Li Hu (vivo)

## Slide 2
4.5 TUs planned
In SA3#115 meeting (2024.2):
  SID approved
In SA3#115e meeting (2024.4):
  3 new KIs added
In SA3#116 meeting (2024.5):
  1 new KIs added
  13 new solutions added
In SA3#117 meeting (2024.8):
  KI & solution & evaluation update
  Add new solutions
  Add conclusion
In SA3#118 meeting (2024.10):
  Solution & evaluation update
  Add conclusions
In SA3#119 meeting (2024.11):
  normative work phase
  send TR for information and approval
  start normative work
Overall plan
‘AIML_CN_SEC’ overall plan
In SA3#120 meeting (2025.2):
  normative work phase
  Leave one EN to align with SA2 architecture
In SA3#121 meeting (2025.4):
  normative work phase
In SA3#121 meeting (2025.4):
  normative work phase,
  complete normative work

## Slide 3
General
  CR for TS 33.501 on Security aspect of AIML based LCS and VFL.
Dependencies:
  SA2 and RAN for architecture aspects
Contentious Issue:
  None
Risks:
  None identified
‘FS_AIML_CN_SEC’ status after SA3#122
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1060059 | Security aspects of Core Network Enhanced Support for AIML | AIML_CN_SEC | Rel-19 | S3 | June-2025 | 80% | 100% | CR for TS 33.501