## Slide 1: SA WG3 Status Report for AmbientIoT-SEC
Marcus Wong – OPPO
Longhua Guo - Huawei

## Slide 2
Overall plan
5G_ProSe_Ph3_SEC Overall Plan
Meeting | Plans | WID TU
SA3#120 (Feb 2025) | TS skeleton, scope, terms, security requirements | 3
SA3#121 (April 2025) | Additional requirements, high-level call flow for authentication and command protection | 4
SA3#122 (August 2025) | Details on authentication and command protection. Procedures on ID privacy protection | 4
SA3#122 (October 2025) | Maintenance and detail update | TBD

## Slide 3
General
  Partial requirements on device/AIOTF/ADM were agreed;
  The authentication procedure for Ambient IoT devices was described;
  security procedures for the information protection in command message were added.
  Initial consensuses for ID privacy, including high-level direction for group inventory and candidate solutions for individual inventory
Dependencies:
  Coordination with SA2 on ID privacy
Contentious Issue:
  Requirements and solutions related to security credential storage and processing.
  Solution selection for ID privacy (espicially for individual inventory)
Risks:
  Multiple editor’s notes added, which requires additional work to resolve.
AmbientIoT-SEC Status after SA3#122
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1070022 | Security Aspects of Ambient IoT Services in 5G | AmbientIoT-SEC | Rel-19 | S3 | Sep-2025 | 0% | 60% | 

## Slide 4
Pending issues
  Details on authentication and command protection.
  ID protection solutions
Dependencies:
  None.
TUs consumed
  SA3#121 -> 3
  SA3#122 -> 4
TUs remaining
  7.
Plan for completion
  Sep, 2025.
AmbientIoT-SEC Pending Work and Plan for Completion