## Sheet1
Abbr. | Acronym | 3GPP Rel-19 SA5 Study and Work Items | Total TU (Planned) | Study TU (Planned) | Normative TU (Planned) | Study TU (Real) | Normative TU (Real) | Jan 2024 （SA5#153） | 2024-04-01 | 2024-05-01 | Aug. 2024
[9 empty] | （SA5#154） | (SA5#155) | (SA5#156)
SID/WID Title and WT Description
AIML | FS_AIML_MGT_Ph2 | Study on AI/ML management - phase 2 | 8.1 | 4.2 | 3.9 |  |  | 0 | 1.45 | 0.95 | 1.8
|  | WT-1. Continue the study on AI/ML emulation, AI/ML inference coordination and ML knowledge transfer that are leftover from Rel-18. |  | 1 | 1 |  |  | 0 | 0.5 | 0 | 0.5
|  | WT-2. Study the management aspects (LCM CM and PM) of AI/ML functionalities defined by other 3GPP WGs, including |  | 0 | 0 |  |  | 0 | 0 | 0 | 0
WT-2.1. AI/ML model transfer in 5GS (SA1, Rel-18 WID 920037 and Rel-19 WID 1000030),
Note: Whether SA5 can start work on WT-2.1 will be discussed at SA#105 (Sep. 2024) based on the outcome of the related work in the involved RAN WGs(s)
|  | WT-2.2. 5GS support for AI/ML-based services (SA2, Rel-18 WID 980019) |  | 0.4 | 0.3 |  |  | 0 | 0.2 | 0.2 | 0
|  | WT-2.3. Support for AI/ML services at application enablement layer (SA6, Rel-18 WID 970036), |  | 0.4 | 0.3 |  |  | 0 | 0.2 | 0 | 0.2
|  | WT-3. Study the management aspects (LCM CM and PM) of AI/ML functionalities defined by 3GPP SA5 WG, including |  | 0.4 | 0.3 |  |  | 0 | 0 | 0.2 | 0.2
WT-3.1. MDA (Management Data Analytics) phase 3 (SA5)
|  | WT-4. Study the AI/ML management and operation capabilities to support different types of AI/ML technologies as needed to support the AI/ML in 5GS, such as Federated Learning, Reinforcement Learning, Online and Offline training, Distributed Learning, and Generative AI. |  | 1 | 1 |  |  | 0 | 0.3 | 0.3 | 0.4
|  | WT-5. Study the sustainability aspect of AI/ML, including |  | 0.5 | 0.5 |  |  | 0 | 0.25 | 0 | 0.25
WT-5.1 Evaluation of energy consumption/efficiency impacts associated with AI/ML solutions for all operational phases (training, emulation, deployment, inference).
|  | WT-6. Further study the trustworthiness aspects related to the AI/ML functionalities in 5GS, including |  | 0.25 | 0.25 |  |  | 0 | 0 | 0.15 | 0.1
WT-6.1 Concept of trustworthiness for AI/ML in the context of OAM,
|  | WT-6.2 Data (e.g., measurements, events) to support calculation of trustworthiness indicators. |  | 0.25 | 0.25 |  |  | 0 | 0 | 0.1 | 0.15