## Slide 1: SA5 Status Report to SA#106
Zou Lan, SA5 Chair, Huawei
Thomas Tovinger, SA5 Vice Chair, Ericsson
Anatoly Andrianov, SA5 Vice Chair, Nokia
Gerald Görmer, SA5 Charging SWG Chair, MATRIXX Software
Antoine Mouquet, MCC, ETSI

## Slide 2: SA5 leadership
SA5
Zou Lan (Huawei) Chair since 08/2023
Thomas Tovinger (Ericsson) Vice Chair since 08/2023 Anatoly Andrianov (Nokia) Vice Chair since 08/2023
Antoine Mouquet MCC since 11/2023
  Charging Sub-Working Group (SWG)
Gerald Görmer (MATRIXX Software) SWG Chair since 08/2021 Chen Shan (Huawei) SWG Vice Chair since 05/2016

## Slide 3: Contents
General aspects of SA5
SA5 overall progress since SA#105
Management Feature relations with other WGs
Management and Orchestration
Charging

## Slide 4: SA5 general information since SA#105
  Statistics SA5#157, 14 – 18 October, 2024 Hyderabad , IN
    129 delegates ‘attended’ (checked-in) 53 registered for ‘On-Line’ participation
    1078 documents (including revisions) including:
      395 CRs submitted (including revisions)，Total CRs agreed: 206
      19 Incoming LSs, 4 postponed
      7 Outgoing LSs Approved
    SA5 CH SWG statistics:
      participation to this meeting
        9 delegates participated to Charging session
        8 delegates from remote
      documents to this meeting
        92 submitted contributions and 47 agreed contributions
        5 Rel-19 WID (+1 completed) and 4 Rel-19 SID
        1 liaison postponed (1 in, 0 out)
        3 agreed CRs for Rel-19, 33pCRs for Rel-19, 11 CRs for Maintenance
Two f2f meeting in 4Q2024
  Statistics SA5#158, 18 – 22 November, 2024 Orlando , US
    172 delegates ‘attended’ (checked-in) 28 registered for ‘On-Line’ participation
    1062 documents (including revisions) including:
      397 CRs submitted (including revisions)，Total CRs agreed: 201
      17 Incoming LSs, 2 postponed
      11 Outgoing LSs Approved
    SA5 CH SWG statistics:
      participation to this meeting
        14 delegates participated to Charging session
        4 delegates from remote
      documents to this meeting
        105 submitted contributions and 68 agreed contributions
        4 Rel-19 WID (+2 completed) and 4 Rel-19 SID
        2 liaisons replied (2 in, 3 out)
        4 agreed CRs for Rel-19, 44 pCRs for Rel-19, 20 CRs for Maintenance
Special thanks to Ingbert Sigovich supporting SA5#157 and Joern Krause supporting SA5#158 on site, Antoine supporting both meetings remotely!

## Slide 5: Report of SA5 CH SWG Assessment
SA5 has discussed the action from SA on assessment of current CH SWG in SA5#157
  SA5 agreed on the corresponding update of SA5 ToR in SP-241571 with adding scope of CH SWG，SA#106 is asked to approve SP-241571

## Slide 6: SA5 meeting statistics (2023/2024)
Chart: LS exchange
| SA5#146Bis-e | SA5#147 | SA5#148-e | SA5#149 | SA5#150 | SA5#151 | SA5#152 | SA5#153 | SA5#154 | SA5#155 | SA5#156 | SA5#157 | SA5#158
incoming LS | 0 | 38 | 33 | 33 | 29 | 19 | 29 | 45 | 32 | 14 | 27 | 19 | 17
Outgoing LS | 0 | 18 | 13 | 13 | 9 | 6 | 13 | 21 | 21 | 7 | 14 | 7 | 11
Chart: Number of delegates in SA5
| SA5#146Bis-e | SA5#147 | SA5#148-e | SA5#149 | SA5#150 | SA5#151 | SA5#152 | SA5#153 | SA5#154 | SA5#155 | SA5#156 | SA5#157 | SA5#158
F2F delegates | 0 | 151 | 0 | 153 | 176 | 142 | 150 | 76 | 170 | 140 | 188 | 129 | 172
Online delegates | 139 | 51 | 149 | 42 | 41 | 37 | 44 | 28 | 21 | 20 | 29 | 53 | 28
Chart: Total number and agreed tdoc numbers
| SA5#146Bis-e | SA5#147 | SA5#148-e | SA5#149 | SA5#150 | SA5#151 | SA5#152 | SA5#153 | SA5#154 | SA5#155 | SA5#156 | SA5#157 | SA5#158
Total number of tdocs | 183 | 1131 | 524 | 1005 | 1085 | 989 | 1021 | 1092 | 1122 | 1137 | 1515 | 1078 | 1062
Number of agreed tdocs | 45 | 496 | 203 | 405 | 467 | 378 | 453 | 447 | 379 | 460 | 698 | 447 | 408
Chart: Allocation of agreed tdocs
| SA5#146Bis-e | SA5#147 | SA5#148-e | SA5#149 | SA5#150 | SA5#151 | SA5#152 | SA5#153 | SA5#154 | SA5#155 | SA5#156 | SA5#157 | SA5#158
R15 CR | 0 | 10 | 0 | 4 | 4 | 3 | 2 | 1 | 4 | 1 | 9 | 3 | 1
R16 CR | 0 | 30 | 0 | 20 | 37 | 9 | 18 | 13 | 12 | 15 | 32 | 12 | 7
R17 CR | 0 | 89 | 5 | 67 | 85 | 43 | 66 | 37 | 37 | 43 | 76 | 29 | 24
R18 CR | 0 | 76 | 6 | 114 | 167 | 148 | 182 | 215 | 133 | 163 | 154 | 62 | 70
R19 CR | 22 | 32 | 108 | 100 | 118
others | 45 | 291 | 192 | 200 | 174 | 175 | 185 | 181 | 164 | 205 | 311 | 241 | 188

## Slide 7: SA5 meeting statistics (Rel-19 OAM TUs)
 | Planned/consumed TU | Bonus TU | Total consumed TU
AIML | 6.2 | 5.7 | 11.9
MDA | 4.7 | 0.33 | 5.03
IDM | 4 | 3.76 | 7.76
CCL | 6.4 | 1 | 7.4
NDT | 3.3 | 2.5 | 5.8
CMO | 6.6 | 6.26 | 12.9
MSEC | 1 | - | 1
SBMA | 5.5 | - | 5.5
PTM | 4 | - | 4
MADCOL | 2.9 | - | 2.9
SREP | 2 | - | 2
PM | 2.2 | - | 2.2
AdNRM | 2.8 | - | 2.8
TMQ | 0.5 | - | 0.5
NTNM | 3.9 | - | 3.9
IABM | 1.6 | - | 1.6
RedcapM | 3.3 | - | 3.3
NWDAF | 1.5 | - | 1.5
NSM | 2.5 | - | 2.5
EE | 5 | 3.7 | 8.7
MExpo | 4.55 | 2.7 | 7.25
MonstraM | 1.5 | - | 1.5
Chart: Rel-19 OAM submited tdocs
| AIML | MADCOL | SEPM | PM | AdNRM | TMQ | NTNM | IABM | RedcapM | NWDAFM | NSM | MDA | EE | Mexpo | MonstraM | IDM | CCL | NDT | CMO | MSEC | SBMA | PTM
#153 | 7 | 3 | 12 | 6 | 13 | 5
#154 | 29 | 9 | 5 | 18 | 8 | 6 | 13 | 7 | 6 | 8 | 5 | 14 | 16 | 13 | 19 | 19 | 14 | 25 | 6 | 5
#155 | 28 | 5 | 6 | 13 | 12 | 3 | 10 | 2 | 9 | 7 | 3 | 23 | 17 | 15 | 19 | 15 | 19 | 26 | 13 | 8
#156 | 50 | 2 | 4 | 27 | 15 | 6 | 16 | 5 | 14 | 9 | 8 | 21 | 22 | 15 | 25 | 24 | 29 | 25 | 4 | 23 | 11
#157 | 54 | 8 | 1 | 11 | 11 | 6 | 10 | 4 | 9 | 2 | 8 | 9 | 23 | 12 | 13 | 25 | 21 | 35 | 12 | 13
#158 | 43 | 4 | 0 | 9 | 9 | 7 | 13 | 0 | 4 | 4 | 6 | 13 | 24 | 14 | 15 | 14 | 7 | 14 | 28 | 3 | 7 | 8
total | 204 | 28 | 16 | 78 | 55 | 28 | 62 | 18 | 42 | 30 | 30 | 80 | 109 | 72 | 15 | 102 | 96 | 110 | 144 | 7 | 61 | 45
Observation/Analysis: Average TU for a study topic should be around 8~10 TU, adding TU in normative phase, 10~15 TU per topic in total in a release would be desired.

## Slide 8
New Rel-19 Study / Work Items
TDoc | Title | Type | UID | (Suggested) Acronym
SP-241552 | New WID on management aspects of Network Digital Twin | WID NEW |  | NDT
SP-241553 | New WID on Service Based Management Architecture enhancement phase 3 | WID NEW |  | SBMA_Ph3
SP-241554 | New WID on energy efficiency and energy saving aspects of 5G networks and services | WID NEW |  | Energy_OAM_Ph3
SP-241555 | New WID on management aspects of RedCap features | WID NEW |  | NR_RedCap_OAM
SP-241556 | New WID on Enhanced OAM for management exposure to external consumers | WID NEW |  | MExpo
SP-241557 | New WID on Closed Control Loop Management | WID NEW |  | CCLM
SP-241558 | New WID on AI/ML management phase 2 | WID NEW |  | AIML_MGT_Ph2
SP-241559 | New WID on Management for MonStra | WID NEW |  | Monstra-OAM
SP-241560 | New WID on intent driven management services for mobile network phase 3 | WID NEW |  | IDMS_MN_Ph3
SP-241561 | New WID on Management Data Analytics (MDA) – Phase 3 | WID NEW |  | eMDAS_Ph3
SP-241562 | New WID on management of IAB nodes | WID NEW |  | NR_mobile_IAB_OAM
SP-241563 | New WID on Management Aspects of NTN Phase 2 | WID NEW |  | NTN_OAM_Ph2
SP-241564 | New WID on Management of Network Sharing Phase 3 | WID NEW |  | NetShare_OAM_Ph3
13 new Rel-19 study/work items sent for SA approval, including 13 OAM work items
To be updated with #106 list

## Slide 9
Revised Rel-19 Study / Work Items
Tdoc | Type | Release | Title | Comment
SP-241565 | WID revised | Rel-19 | Revised WID on 5G Advanced NRM features phase 3 | Add new objective to support multi-RAT deployments
SP-241566 | SID revised | Rel-19 | Revised SID on Cloud Aspects of Management and Orchestration | Update TU allocation, group decided to use Rel-19 for cloud management study only.
SP-241567 | SID revised | Rel-19 | Revised SID on AIML management phase 2 | Downscoping study, remove management support to SA1 and SA6.
SP-241568 | SID revised | Rel-19 | Revised SID on energy efficiency and energy saving aspects of 5G networks and services | Downscoping study, remove the management support to RAN EE in Rel-19
SP-241569 | SID revised | Rel-19 | Revised SID on Service Based Management Architecture enhancement phase 3 | Downscoping study, remove the study for generic mechanism and common data type
SP-241570 | SID revised | Rel-19 | Revised SID on Enhanced OAM for management exposure to external consumers | Downscoping study, remove exposure study to network slicing.
6 revised OAM study/work items sent for SA approval

## Slide 10: Overview of Rel-19 SA5 OAM topics
 |  | Abbr. | Acronym | Title | UID | rapp | Tdoc | TS/TR | Type
Intelligence and Automation | 1 | AIML | FS_AIML_MGT_Ph2 | Study on AI and ML management phase 2 | 1020007 | Intel, NEC | SP-231780 | TR 28.908 | SID
 |  |  | -> AIML_MGT_Ph2 | AI/ML management phase 2 (for SA approval) |  |  |  |  | WID
 | 2 | MDA | FS_eMDAS_Ph3 | Study on Management Data Analytics (MDA) – Phase 3 | 1020019 | Huawei | SP-231726 | TR 28.866 | SID
 |  |  | -> eMDAS_Ph3 | Management Data Analytics phase 3 (for SA approval) |  |  | S5-246126 | TS 28.104 | WID
 | 3 | IDM | FS_IDMS_MN_Ph3 | Study on intent driven management services for mobile networks phase 3 | 1020008 | Huawei, Ericsson | SP-231737 | TR 28.914 | SID
 |  |  | -> IDMS_MN_Ph3 | Intent driven management services for mobile network phase 3 (for SA approval) |  |  | S5-246125 | TS 28.312 | WID
 | 4 | CCL | FS_CCLM | Study on Closed Control loop management | 1020009 | Samsung, Nokia | SP-231735 | TR 28.867 | SID
 |  |  | -> CCLM | Closed Control Loop Management(for SA approval) |  |  |  |  | WID
 | 5 | NDT | FS_NDT | Study on Management aspect of Network Digital Twin | 1020018 | CMCC | SP-231727 | TR 28.915 | SID
 |  |  | -> NDT | Management aspects of Network Digital Twins (for SA approval) |  |  |  |  | WID
Management Architecture and Mechanisms | 6 | CMO | FS_Cloud_OAM | Study on cloud aspects of management and orchestration | 1020010 | Microsoft,CMCC | SP-231781 | TR 28.869 | SID
 | 7 | MSEC | FS_SECM | Study on Enablers for Security Monitoring | 1020016 | Nokia | SP-231736 | TR 28.870 | SID
 | 8 | SBMA | FS_SBMA_Ph3 | Study on SBMA enhancement phase 3 | 1020011 | Huawei, Ericsson | SP-231725 | TR 28.871 | SID
 |  |  | ->SBMA_Ph3 | Service Based Management Architecture enhancement phase 3 |  |  |  |  | WID
 | 9 | PTM | FS_PlanM | Study on Plan management | 1020033 | Nokia, Ericsson | SP-231721 | TR 28.872 | SID
 |  |  | -> PlanM | Management of planned configurations | 1050032 | Nokia | SP-241379 | TS 28.572 | WID
 | 10 | MADCOL | MADCOL_Ph2 | Data Management phase 2 | 1020025 | Nokia | SP-231746 | TS 28.622 | WID
 | 11 | SEPM | FS_Data_SREP | Study on data management, regarding subscriptions and reporting | 1020012 | Ericsson | SP-231732 | TR 28.873 | SID
 |  |  | -> Data_SREP | Data management, regarding subscriptions and reporting | 1050033 | Ericsson | SP-241380 | 28.537/28.550/28.532/32.421/32.422/32.423/28.404/28.405/28.622/28.623 | WID
 | 12 | PM | PM_KPI_5G_Ph4 | 5G performance measurements and KPIs phase 4 | 1020026 | China Telecom, ZTE | SP-231747 | TS 28.552/554 | WID
 | 13 | AdNRM | AdNRM_Ph3 | 5G Advanced NRM features phase 3 | 1020027 | Nokia, Huawei | SP-231745 | TS 28.541/622 | WID
 | 14 | TMQ | TraceQoE_OAM | Subscriber and Equipment Trace and QoE collection management | 1020028 | Ericsson | SP-231748 | TS 32.422/405 | WID
 | 15 | NTNM | FS_ NTN_OAM_Ph2 | Study on Management Aspects of NTN Phase 2 | 1020013 | China Unicom, CATT | SP-231733 | TR 28.874 | SID
 |  |  | ->NTN_OAM_Ph2 | Management Aspects of NTN Phase 2 (for SA approval) |  |  | S5-246131 | TS 28.541/552/554/658/662/540/530 | WID
 | 16 | IABM | FS_NR_mobile_IAB_OAM | Study on Management of IAB Nodes | 1020014 | Ericsson | SP-231729 | TR 28.875 | SID
 |  |  | -> NR_mobile_IAB_OAM | Management of IAB nodes (for SA approval) |  |  | S5-246130 | TS 28.541/540/531/314/315 | WID
 | 17 | RedcapM | FS_NR_RedCap_OAM | Study on management aspects of RedCap feature | 1020017 | China Unicom, Asiainfo | SP-231734 | TR 28.876 | SID
 |  |  | ->NR_RedCap_OAM | Management Aspects of RedCap features (for SA approval) |  |  |  |  | WID
 | 18 | NWDAFM | FS_NWDAF_OAM_Ph2 | Study on Enhancement of Management Aspects related to NWDAF Phase 2 | 1020020 | China Telecom | SP-231724 | TR 28.877 | SID
 |  |  | -> NWDAF_OAM_Ph2 | Enhancement of Management Aspects related to NWDAF Phase 2 | 1050031 | China Telecom | SP-241378 | 28.552/28.541 | WID
 | 19 | NSM | FS_NetShare_OAM_Ph3 | Study on Management of Network Sharing Phase 3 | 1020015 | China Unicom | SP-231731 | TR 28.878 | SID
 |  |  | ->NetShare_OAM_Ph3 | Management of Network Sharing Phase 3 (for SA approval) |  |  | S5-246289 | TS 28.552/32.130/28.541 | WID
Support of New Services | 20 | EE | FS_Energy_OAM_Ph3 | Study on energy efficiency and energy saving aspects of 5G networks and services | 1020021 | Huawei, Samsung | SP-231723 | TR 28.880 | SID
 |  |  | ->Energy_OAM_Ph3 | Energy efficiency and energy saving aspects of 5G networks and services (for SA approval) |  |  |  |  | WID
 | 21 | Mexpo | FS_MExpo | Study on Enhanced OAM for management exposure to external consumers | 1020022 | Nokia | SP-231728 | TR 28.879 | SID
 |  |  | ->MExpo | Enhanced OAM for management service exposure to external consumers through CAPIF (for SA approval) |  |  |  |  | WID
 | 22 | MonStra | Monstra-OAM | Management for MonStra (for SA approval) |  |  | S5-245981 | TS 28.abc | WID
22 topics including: 14 OAM prime features and 8 OAM support to network features (in red background). 16 topics completed the study. 13 new WIDs wait for SA approval.

## Slide 11
Overview of Rel-19 CH topics
 | Abbr. | Acronym | Title | UID | Rapp | Tdoc | TS/TR | Type
1 | CHSEG | CHFSeg | WID on CHF Segmentation | 1040012 | Verizon | SP-241001 | TS 32.290/291 | WID
2 | SATCH | FS_5GSAT_Ph3_CH | Study on charging aspects of satellite access Phase 3 | 1040014 | CATT | SP-240980 | TR 28.846 | SID
3 | CAPCH | FS_CAPIF_Ph2_CH | Study on Charging Aspects of CAPIF | 1040015 | Nokia | SP-240981 | TR 28.849 | SID
4 | RTCCH | FS_NG_RTC_Ph2_CH | Study on Charging aspects of next generation real time communication services phase 2 | 1040016 | CMCC | SP-240982 | TR 28.851 | SID
5 | UASCH | FS_UAS_Ph2_CH | Study on Charging aspects of Uncrewed Aerial Vehicle | 1040017 | CMCC | SP-240983 | TR 28.853 | SID
6 | RAGCH | Ranging_SL_CH | WID on Charging Aspects of Ranging and Sidelink Positioning | 1040013 | China Telecom | SP-241002 | TS 32.240/290/ 271/291/298 | WID
7 | EESCH | EnergySys_CH | WID on Charging Aspects for Energy Efficiency of 5G | 1040018 | Huawei | SP-241003 | TS 28.201/202 TS 32.240/291/298 | WID
8 | NSCH | NetShare_CH | WID on Charging enhancement for indirect network sharing | 1040019 | Ericsson | SP-241004 | TS 32.240/255/256 | WID
9 | PROCH | 5G_ProSe_Ph3_CH | New WID on Charging Aspects for 5G ProSe Phase 3 (SP-241156 wait for SA approval) | 1050030 | China Telecom | SP-241156 | TS 32.277/291/298 | WID
9 CH topics including: 1 CH prime feature and 8 CH support to network features (in red background, 2 WID completed – marked n green color). No new WIDs wait for SA approval.

## Slide 12: Update of SA5 Rel-19 OAM ongoing WI/SI progress
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020021 | Study on energy efficiency and energy saving aspects of 5G networks and services | FS_Energy_OAM_Ph3 | 12/12/2024 | 60% | SP-231723 | 100% | 
1020007 | Study on AI/ML management - phase 2 | FS_AIML_MGT_Ph2 | 12/12/2024 | 55% | SP-240965 | 100% | 
1050033 | Data management regarding subscriptions and reporting | Data_SREP | 09/09/2025 | 0% | SP-241380 | 0% | 
1020019 | Study on Management Data Analytics (MDA) Phase 3 | FS_eMDAS_Ph3 | 12/12/2024 | 90% | SP-241157 | 100% | 
1020008 | Study on intent driven management services for mobile network phase 3 | FS_IDMS_MN_Ph3 | 12/12/2024 | 95% | SP-231737 | 100% | 
1020009 | Study on closed control loop management | FS_CCLM | 12/12/2024 | 90% | SP-231735 | 100% | 
1020018 | Study on management aspects of Network Digital Twin | FS_NDT | 12/12/2024 | 95% | SP-231727 | 100% | 
1020010 | Study on Cloud Aspects of Management and Orchestration | FS_Cloud_OAM | 12/12/2024 | 80% | SP-231781 | 90% | 
1020016 | Study on Enablers for Security Monitoring | FS_SECM | 12/12/2024 | 90% | SP-231736 | 100% | 
1020011 | Study on Service Based Management Architecture enhancement phase 3 | FS_SBMA_Ph3 | 12/12/2024 | 75% | SP-231725 | 100% | 
1020033 | Study on Management of planned configurations | FS_PlanM | 09/09/2024 | 100% | SP-231721 |  | 
1050032 | Management of planned configurations | PlanM | 09/09/2025 | 0% | SP-241379 | 60% | 
1020025 | Data management phase 2 | MADCOL_Ph2 | 06/06/2025 | 80% | SP-240877 | 88% | 
1020012 | Study on data management regarding subscriptions and reporting | FS_Data_SREP | 09/09/2024 | 100% | SP-231732 |  | 
1020026 | 5G performance measurements and KPIs phase 4 | PM_KPI_5G_Ph4 | 06/06/2025 | 30% | SP-241155 | 65% | 
1020027 | 5G Advanced NRM features phase 3 | AdNRM_Ph3 | 06/06/2025 | 30% | SP-240875 | 60% | 
1020028 | Subscriber and Equipment Trace and QoE collection management | TraceQoE_OAM | 06/06/2025 | 40% | SP-231748 | 75% | 
1020013 | Study on Management Aspects of NTN Phase 2 | FS_NTN_OAM_Ph2 | 12/12/2024 | 90% | SP-231733 | 100% | 
1020014 | Study on management of IAB nodes | FS_NR_mobile_IAB_OAM | 12/12/2024 | 90% | SP-231729 | 100% | 
1020017 | Study on management aspects of RedCap feature | FS_NR_RedCap_OAM | 12/12/2024 | 75% | SP-231734 | 100% | 
1020020 | Study on Enhancement of Management Aspects related to NWDAF Phase 2 | FS_NWDAF_OAM_Ph2 | 09/09/2024 | 100% | SP-231724 |  | 
1050031 | Enhancement of Management Aspects Related of NWDAF Phase 2 | NWDAF_OAM_Ph2 | 06/06/2025 | 0% | SP-241378 | 60% | 
1020015 | Study on Management of Network Sharing Phase3 | FS_NetShare_OAM_Ph3 | 12/12/2024 | 90% | SP-240966 | 100% | 
1020022 | Study on Enhanced OAM for management exposure to external consumers | FS_MExpo | 12/12/2024 | 60% | SP-240967 | 100% | 
 | Management for MonStra | Monstra-OAM | 12/12/2024 | 0% | S5-245981 | 80% | New WID submitted to SA#106 for approval

## Slide 13: Update of SA5 Rel-19 CH ongoing WI/SI progress
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1040012 | CHF Segmentation | CHFSeg | 03/03/2025 | 25 % | SP-241001 | 55 % | 
1040013 | Charging Aspects of Ranging and Sidelink Positioning | Ranging_SL_CH | 03/03/2025 | 50 % | SP-241002 | 100 % | This WI is a Rel-19 WI instead of Rel-18.
1040014 | Study on charging aspects of satellite access Phase 3 | FS_5GSAT_Ph3_CH | 12/12/2024-> 03/03/2025 | 40 % | SP-240980 | 75 % | Delayed, pending work in SA2 on 5GSAT_Ph3-ARC)
1040015 | Study on Charging Aspects of CAPIF | FS_CAPIF_CH ->FS_CAPIF_Ph2_CH | 12/12/2024-> 03/03/2025 | 35 % | SP-240981 | 75 % | Acronym needs to be updated. Delayed, additional aspects from GSMA OPG, WID is feasible based on CRs in Rel-19
1040016 | Study on Charging aspects of next generation real time communication services phase 2 | FS_NG_RTC_Ph2_CH | 12/12/2024-> 03/03/2025 | 45 % | SP-240982 | 75 % | Delayed, pending work in SA2 on NG_RTC_Ph2
1040017 | Study on Charging aspects of Uncrewed Aerial Vehicle | FS_UAS_CH -> FS_UAS_Ph2_CH | 12/12/2024-> 03/03/2025 | 40 % | SP-240983 | 75 % | Acronym needs to be updated. Delayed, pending work in SA2 on UAS_Ph3
1040018 | Charging Aspects for Energy Efficiency of 5G | EnergySys_CH | 06/06/2025 | 45 % | SP-241003 | 45 % | 
1040019 | Charging enhancement for indirect network sharing | NetShare_CH | 12/12/2024 | 0 % | SP-241004 | 100 % | 
1050030 | Charging Aspects for 5G ProSe Phase 3 | 5G_ProSe_Ph3_CH | 12/09/2025 | 0 % | SP-241156 | 0 % | 

## Slide 14
Acronym | OAM | Not covered by SA5 OAM yet | CH | Not covered by SA5 CH yet
5GSAT_Ph3_ARCH | FS_ NTN_OAM_Ph2 |  | FS_5GSAT_Ph3_CH | 
NG_RTC_Ph2 | NA | NA | FS_NG_RTC_Ph2_CH | 
XRMPh2 | PM_KPI_5G_Ph4(CMCC) | OAM (NRM)?? |  | CH?? (CH indicated in SA2 WID)
MPS4msg | NA | NA |  | CH?? (CH indicated in SA2 WID)
VMR_Ph2 | AdNRM_Ph3(Samsung) | (PM??) |  | CH?? (CH indicated in SA2 WID)
5G_ProSe_Ph3 | AdNRM_Ph3 (CATT) | (PM??) | 5G_ProSe_Ph3_CH | 
UIA_ARC | NA | NA |  | CH?? (CH indicated in SA2 WID)
eEDGE_5GC_Ph3 |  | OAM (NRM+PM)?? |  | CH?? (CH indicated in SA2 WID)
UAS_Ph3 | NA | NA | FS_UAS_Ph2_CH (to be checked) | FS_UAS_Ph2_CH only targets UAS_Ph2
UPEAS_Ph2 |  | OAM (NRM+PM)?? |  | CH?? (CH indicated in SA2 WID)
5G_Femto | NA | NA | NA | NA
MASSS |  | OAM (NRM)?? PM (not related) | NA | NA
AIML_CN | FS_AIML_MGT_Ph2 FS_NWDAF_OAM_Ph2 |  |  | CH?? (CH indicated in SA2 WID)
TEI19_NetShare | FS_NetShare_OAM_Ph3 |  | NetShare_CH | 
FS_AmbientIoT |  | OAM (TBD) |  | CH?? CH indicated in SA2 SID
FS_EnergySys | FS_Energy_OAM_Ph3 FS_MExpo |  | EnergySys_CH | CH indicated in SA2 SID
Summary of SA5 Rel-19 management support to SA2 features
OAM Summary
The following features, there are no extra management standardization support identified so far:
  NG_RTC_Ph2
  MPS4msg
  UIA_ARC
  UAS_Ph3
  5G_Femto
The following features, need to check whether OAM support are needed in Rel-19.
  XRMPh2
  VMR_Ph2
  5G_ProSe_Ph3
  eEDGE_5GC_Ph3
  UPEAS_Ph2
  MASSS
  FS_AmbientIoT
CH Summary
The following features, there are no extra CH management standardization support identified so far:
  5G_Femto
  MASSS
The following features, need to check whether Charging support are needed in Rel-19.
  XRMPh2
  MPS4msg
  VMR_Ph2
  UIA_ARC
  eEDGE_5GC_Ph3
  UAS_Ph3
  UPEAS_Ph2
  AIML_CN
  FS_AmbientIoT
  FS_EnergySys
The content of this slides is to be updated based on working progress

## Slide 15
Acronym | OAM | Not covered by SA5 yet
NR_MIMO_Ph5-Core | NA | NA
FS_NR_7_24GHz_CHmod | NA | NA
NR_MIMO_Ph5 | NA | NA
Netw_Energy_NR_enh-Core | NA | NA
FS_Sensing_NR |  | OAM (TBD)
NR_AIML_air-Core | FS_AIML_MGT_Ph2 | other OAM (TBD)
NR_duplex_evo | NA | NA
NR_LPWUS-Core |  | OAM (NRM+PM)？？
FS_Ambient_IoT_solutions |  | OAM (TBD)
FS_NR_AIML_Mob | FS_AIML_MGT_Ph2 | other OAM (TBD)
NR_Mob_Ph4 | PM_KPI_5G_Ph4 AdNRM_Ph3 | 
NR_NTN_Ph3-Core | FS_ NTN_OAM_Ph2 | 
IoT_NTN_Ph3-Core | FS_ NTN_OAM_Ph2 | 
NR_XR_Ph3-Core | NA | NA
LTE_TN_NR_NTN_mob | FS_ NTN_OAM_Ph2 | 
NR_ENDC_SON_MDT_Ph4 | PM_KPI_5G_Ph4 AdNRM_Ph3 TraceQoE_OAM | 
FS_NR_WAB_5GFemto | NA | NA
FS_NR_AIML_NGRAN_enh | FS_AIML_MGT_Ph2 FS_Energy_OAM_Ph3 | 
Summary of SA5 Rel-19 management support to RAN1/2/3 features
RAN1
RAN2
RAN3
OAM Summary:
RAN1:
1. The following features, there are no extra management standardization support identified so far:
NR_MIMO_ph5-Core
FS_NR_7_24GHz_CHmod
NR_MIMO_Ph5
Netw_Energy_NR_enh-Core
NR_duplex_evo
2. The following features, need to check whether OAM support are needed in Reld-19.
FS_Sensing_NR
NR_LPWUS-Core
FS_Ambient_IoT_solutions
RAN2:
1. The following features, there are no extra management standardization support identified so far:
NR_XR_Ph3-Core
RAN3:
1. The following features, there are no extra management standardization support identified so far:
FS_NR_WAB_5GFemto
CH Summary: There are no extra CH features related to RAN features.
The content of this slides is to be updated based on working progress

## Slide 16
SA5 Rel-19 topics relation to other WGs (OAM)
Abbreviation | Acronym | SA1 | SA2 | SA3 | SA4 | SA6 | RAN1 | RAN2 | RAN3 | CT3 | CT4 | Other related groups
AIML | FS_AIML_MGT_Ph2 | TS 22.261 (AIML) | AIML_CN(R19) | X |  | X | NR_AIML_air-Core (R19) | FS_NR_AIML_Mob (R19) | FS_NR_AIML_NGRAN_enh(R19) |  |  | 3GPP SA (TR 22.850)
MDA | FS_eMDAS_Ph3 |  |  |  |  |  |  |  | X (EE cost index) |  |  | 
IDM | FS_IDMS_MN_Ph3 | TS 22.125 (UAV pre-flight) |  |  |  |  |  |  |  |  |  | GSMA/CAMARA/ETSI ZSM/TMF
CCL | FS_CCLM |  |  |  |  |  |  |  |  |  |  | ETSI ZSM
NDT | FS_NDT |  | X |  |  |  |  |  |  |  |  | ETSI ZSM
CMO | FS_Cloud_OAM |  |  |  |  |  |  |  |  |  |  | ETSI NFV
MSEC | FS_SECM |  |  | X |  |  |  |  |  |  |  | 
SBMA | FS_SBMA_Ph3 |  |  |  |  |  |  |  |  |  |  | 
PTM | FS_PlanM |  |  |  |  |  |  |  |  |  |  | 
MADCOL | MADCOL_Ph2 |  |  |  |  |  |  |  |  |  |  | 
SREP | FS_Data_SREP |  |  |  |  |  |  |  |  |  |  | 
PM | PM_KPI_5G_Ph4 | TS 22.137 (Sensing KPI) (TBD) |  |  |  |  | FS_Sensing_NR (TBD) | NR_Mob_Ph4 (R19) | XNR_ENDC_SON_MDT_Ph4 (R19) |  |  | 
AdNRM | AdNRM_Ph3 |  | VMR_Ph2 (R19) |  |  | eEDGE_5GC_Ph3 (R19) | FS_Sensing_NR?? | NR_Mob_Ph4 (R19) | NR_ENDC_SON_MDT_Ph4 (R19) |  | SBIProtoc19 (R19) | GSMA (GST)
TMQ | TraceQoE_OAM |  | X |  | X |  |  | X | X |  | X | 
NTNM | FS_ NTN_OAM_Ph2 |  | 5GSAT_Ph3_ARCH (R19) |  |  |  |  | NR_NTN_Ph3-Core(R19) IoT_NTN_Ph3-Core(R19) | LTE_TN_NR_NTN_mob(R19) |  |  | 
IABM | FS_NR_mobile_IAB_OAM |  |  |  |  |  |  |  | X |  |  | 
RedcapM | FS_NR_RedCap_OAM |  | NR_REDCAP_Ph2 (R18) |  |  |  | NR_redcap_enh-Core (R18) |  |  |  |  | 
NWDAFM | FS_NWDAF_OAM_Ph2 |  | TS 23.288, eNA_Ph 2 (R17) |  |  |  |  |  |  |  |  | 
NSM | FS_NetShare_OAM_Ph3 | TS 22.261 | TEI19_NetShare(R19) |  |  |  |  |  |  |  | X | 
EE | FS_Energy_OAM_Ph3 | TS 22.261 (EE as a service) | FS_EnergySys (R19) |  |  |  |  |  | FS_NR_AIML_NGRAN_enh (R19) |  |  | NGMN/ETSI NFV/ETSI EE/ITU-T SG5
Mexpo | FS_MExpo | TS 22.261 (EE as a service) |  | TS 33.222 (CAPIF) |  | TS 23.222(CAPIF) |  |  |  | TS 29.222 (CAPIF) |  | GSMA OPG/CAMARA/TMF
MonStra | Monstra-OAM | TS 22.261-6.51 (MonStra) |  |  |  |  |  |  |  |  |  | 
The content of this slides is to be updated based on working progress

## Slide 17
SA5 Rel-19 topics relation to other WGs (CH)
Abbreviation | Acronym | SA1 | SA2 | SA6 | CT1 | CT3 | CT4 | Other related groups
SATCH | FS_5GSAT_Ph3_CH | 5GSAT_Ph3 (R19) (TS 22.261) | 5GSAT_Ph3_ARCH (TS 23.501; TS 23.502; TS 23.503; TS 23.682; TS 23.228; TS 23.401 ) | 5GSAT_Ph3_App (TS 23.558; TS 23.434; TS 23.289 ) |  |  |  | 
CAPCH | FS_CAPIF_Ph2_CH |  |  | CAPIF(R15)?? eCAPIF(R16)?? FS_CAPIF_Ph3 |  |  |  | 
RTCCH | FS_NG_RTC_Ph2_CH |  | NG_RTC_Ph2?? (TS 23.228; TS 23.502 ) FS_NG_RTC_Ph2 (TR 23.700-77) |  |  |  |  | 
UASCH | FS_UAS_Ph2_CH | ID_UAS (R17) (TS 22.125) UAS_Ph3(R19)?? | ID_UAS (R17) (23.501; 23.502; 23.503; 23.401) UAS_Ph2 (R18) (23.256) UAS_Ph3 (R19) ?? (TS 23.256; TS 23.288; TS 23.503; TS 23.502; TS 23.401 ) | UASAPP_Ph3?? |  | UASAPP_Ph3?? ID_UAS（R17） UAS_Ph2（R18) (TS 29.502；TS 29.503；TS 29.504；TS 29.505；TS 29.510；TS 29.518；TS 29.571；TS 29.274；TS 29.256；TS 23.008） | ID_UAS（R17） UAS_Ph2（R18) (TS 29.502；TS 29.503；TS 29.504；TS 29.505；TS 29.510；TS 29.518；TS 29.571；TS 29.274；TS 29.256；TS 23.008） | 
CHSEG | CHFSeg |  |  |  |  |  |  | 
RAGCH | Ranging_SL_CH | Ranging (R18) (TS 22.261) | Ranging_SL(R18) (23.304; 23.287; 23.273; 23.502; 23.503 ; 23.586) |  | Ranging_SL (R18) (24.501; 24.554; 24.555; 24.571; 24.587; 24.588; 24.514) | Ranging_SL (R18) (29.513; 29.122; 29.522; 29.591; 29.525; 29.519) | Ranging_SL (R18) (24.080; 29.503; 29.504; 29.505; 29.510; 29.515; 29.518; 29.571; 29.572; 29.586) | 
EESCH | EnergySys_CH | EnergyServ (R19) (TS 22.261) | FS_EnergySys (R19) (TR 23.700-66) |  |  |  |  | 
NSCH | NetShare_CH | NetShare (R19) (TS 22.261) | TEI19_NetShare (R19) (TS 23.501; TS 23.502 ) |  | TEI19_NetShare (24.501) |  | TEI19_NetShare (29.502; 29.503; 29.509; 29.510; 29.531) | 
PROCH | 5G_ProSe_Ph3_CH |  | 5G_ProSe_Ph3 (R19) |  |  |  |  | 
The content of this slides is to be updated based on working progress

## Slide 18
Release 20 timeline– figure with SA5 (recommended by SA5 leaders)
Reference：SP-241424
2024
#103
Mar.
#111
Mar.
#107
Mar.
#104
Jun.
#108
Jun.
#112
Jun.
#105
Sep.
#109
Sep.
#102
Dec.
#106
Dec.
#110
Dec.
Now
TSGs
SA1 5GA SID definition
Workshop 6G TSGs
100%
SA1 5GA Studies + Norm 80%
100%
St. 2 (SA2, SA6, …) 5GA St.+Norm 80%
Stage 3 5GA St + Norm
Stage 3 6G SID def.
#113
Sep.
#114
Dec.
#115
Mar.
Jun
Workshop IMT-2030 use cases
RAN1
RAN Completion (RAN2/3/4core)
#116
SA1 6G Study(ies)
RAN4 C.def.
RAN4 Perf
RP Content def.
SA1 6G SID def.
RP IMT-2030 disc.
RP ITU Study
RP 6G Study(ies)
RAN1 6G Study(ies)
SA2 6G Study(ies)
Stage 3 6G Study(ies)
Rel-20 – FS_6G part
2025
2026
2027
SA2 & RAN WGs 6G SID def.
SA3/4/6 SID def. and compl. TBD
5GA ASN.1 & Open APIs
RAN2/3/4 6G Study(ies)
St.2 SID def. TBD
St.3 SID def. TBD
Release 20 timeline
or
TBD
Note: All starting dates are indicative
Workshop 5GA RAN
Workshop 5GA SA
Management Stage 2/Stage3 St.+Norm supporting SA&RAN (SA5)
3GPP SA5
Time plan
OAM/CH prime feature:
Start of Rel-20 study: Jan.2025 (SA#107/SA5#159)
End of Rel-20 work: Mar.2027 (SA#115/SA5#172)
OAM/CH support to network feature (SA5 is ready to support network features pending the availability of inputs from other WGs. )
Start of Rel-20 study: Jun.2025 (SA#108/SA5#161)
End of Rel-20 study: Mar.2027 (SA#115/SA5#172)
SA5 6G SID def.
SA5 6G Study(ies)
Rel-20 - 5GA part
OAM/CH prime Stage1
The content of this slides is preliminary information for comments

## Slide 19: Detailed Rel-20 time plan with 5GA/6G
Overall Plan:
OAM/CH prime feature:
  Start of Rel-20 study: Jan.2025 (SA#107/SA5#159)
  End of Rel-20 work: Mar.2027 (SA#115/SA5#172)
OAM/CH support to network feature (SA5 is ready to support network features pending the availability of inputs from other WGs. )
  Start of Rel-20 study: Jun.2025 (SA#108/SA5#161)
  End of Rel-20 study: Mar.2027 (SA#115/SA5#172)
5GA:
OAM/CH Prime:
  OAM/CH prime Stage-1 freeze: Jun 2025 – (same as SA1 stage-1 freeze)
  Stage-2 freeze : Jun 2026 (>=80%); Sep 2026 (100%) – (same as SA2 stage-2 freeze)
  Stage-3 freeze : Mar 2027 – (same as CT stage-3 freeze)
OAM/CH support network features:
  OAM/CH support Stage-1 freeze : Dec 2025 – (6 months later than SA1 stage-1 freeze)
  Stage-2 freeze: Sep 2026 (>=80%); Dec 2026 (100%) – (3 months later than SA2 stage-2 freeze)
  Stage-3 freeze : Mar 2027 – (3 months earlier than CT OpenAPI/ASN.1 freeze)
6G SI Approval:
OAM/CH Prime:
  SA5 SI approval: TSG#108 (Jun 2025) – (same as SA2 SI approval)
OAM/CH support:
  SA5 SI approval: TSG#110 (Dec 2025) – (6 months later than SA2 SI approval)
6G SI completion:
OAM/CH Prime:
  SA5 6G SI completion: Dec 2026 or Mar 2027 (To be confirmed at future TSG meeting)
OAM/CH support:
  SA5 6G SI completion: Dec 2026 or Mar 2027 (To be confirmed at future TSG meeting) ·
The content of this slides is preliminary information for comments

## Slide 20: SA5 Rel-20 capacity summary
SA5 capacity:
  Max TUs: 124 (OAM) / 80 (Charging)
    Additional buffer TUs: 61(OAM)/40(CH)
  Max number of SIs/WIs: 10~15 (OAM) / 6~10 (Charging)
    Note: one feature made up of SI+WI is counted as one item
  Max TUs per Feature: 12~8 TU
Assumptions
  Start: Jun 2025, End: Mar 2027 (21 months)
  One track for OAM and One track for Charging
  Number of meetings: 10
  Expected total TUs per meeting (for all releases): 18.5 (OAM) / 12 (Charging)
  Total TUs (for all releases): 185 (OAM) / 120 (Charging)
  TUs for maintenance of past releases: 35 (OAM) / 18 (Charging)
The content of this slides is preliminary information for comments

## Slide 21: TU allocation portion of 5GA part/6G part in Rel-20
SA5 has discussed the TU allocation and hasn’t reached agreement yet. The following information are currently under discussion:
  Management support of network features:
    for management of RAN: follow the RAN2/RAN3 split allocation: e.g. x% (5GA), y%(6G)
    for management of 5GC: follow the SA2 split allocation e.g. m% (5GA), n%(6G)
  OAM Prime features:
    Option A (bottom up): Decide the TU allocation when we have a full Rel-20 feature list.
    Option B (top down): Give the budget allocation for OAM prime features with considering companies’ inputs on how to split it.
      Samsung opinion is to consider 30% of total 6G TU for 5GA for OAM prime feature.

## Slide 22: Potential Rel-20 management features workshop (planned)
Plan for management Feature Workshop (details to be updated according to the availability of inputs):
The scope of the workshops is 5GA related new management features including OAM/CH prime features and management support to new network features.
  January 2025: Online presentation on potential topics and directions (4 TUs)
  February 2025 (SA5#159): Contributions more focused on concrete topics, especially on management prime features (2 TUs)
Draft Agenda
  Opening of the workshop
  Contributions from 3GPP member companies
    Contributions on potential Rel-20 management use cases and requirements, etc.
    Up to one contribution per company
  Chairman's summary and open discussion
  Closing of the workshop
  Please feel free to contact Chair if you plan to provide presentation, and it will be helpful to make better planning for this activity.

## Slide 23: SA5 Liaisons to SA
Tdoc | Reply To | Title | Doc-type | Source | To | Cc | Action from SA
SP-241443 | LS S5-240463/OPAG_94_Doc_07 and partial S5-243816/ OPAG_112_Doc_03 | LS from SA WG5: LS on 3GPP_Correlation information for API volume-based charging | LS out | SA5 | GSMA OPG Operator Platform API Group | GSMA OPG, 3GPP SA2, 3GPP SA | No action required from SA
SP-241444 |  | LS from SA WG5: LS to ETSI ATTM, ETSI OEU and ITU-T SG5 on carbon emissions related KPIs | LS out | SA5 | ETSI ATTM, ETSI OEU, ITU-T SG5 | ETSI EE, 3GPP SA1, 3GPP SA2, 3GPP SA | No action required to SA
SP-241445 |  | LS from SA WG5: LS on AI/ML Model transfer/delivery to UE | LS out | SA5 | RAN2, RAN1 | RAN, SA, RAN3 | No action required from SA
SP-241446 |  | LS from SA WG5: Reply LS on AIML Data Collection | LS out | SA5 | RAN2 | TSG RAN, RAN1, RAN2, RAN3, TSG SA, SA2, SA3 | No action required from SA
 | RP-242389 on LS on AIML data collection from TSG RAN | LS from SA WG5: Reply LS on AIML Data Collection | LS out | SA5 | RAN | TSG SA, SA2, SA3, RAN1, RAN2, RAN3 | May be discussed together with other related LS
 | LS to ITU-T Study Group 13 (incoming LS in S5-246415) | Reply to LS on establishment of new Focus Group on Artificial Intelligence Native for Telecommunication Networks (FG-AINN) | LS out | SA5 | SA |  | SA5 plans to send LS to ITU-T, SA may need to provide a consolidated reply with including the inputs from SA5.
To be updated with #106 list

## Slide 24: TRs / TSs to SA#106 for information/approval
Tdoc | Title | For
SP-241599 | Presentation of TR 28.871 Study on Service Based Management Architecture enhancement phase 3 to SA for Approval | For approval
SP-241600 | Presentation of TR 28.846 Study on charging aspects of satellite access phase 3 to SA for Information | For information
SP-241601 | Presentation of TR 28.849 Study on charging aspects of Common API Framework for Northbound APIs (CAPIF) phase 2 to SA for Information | for Information
SP-241602 | Presentation of TR 28.851 Study on charging aspects of next generation real time communication services phase 2 to SA for Information | for Information
SP-241603 | Presentation of TR 28.853 Study on charging aspects of uncrewed aerial systems to SA for Information | for Information
SP-241604 | Presentation of TR 28.858 Study on Artificial Intelligence / Machine Learning (AI/ML) management phase 2 to SA for Information and Approval | for Information and Approval
SP-241605 | Presentation of TR 28.878 Study on Management of Network Sharing Phase3 to SA for Approval | For approval
SP-241606 | Presentation of TR 28.880 Study on energy efficiency and energy saving aspects of 5G networks and services to SA for Approval | For approval
SP-241607 | Presentation of TR 28.915 Study on management aspect of Network Digital Twin to SA for Approval | For approval
SP-241608 | Presentation of TR 28.876 Study on management aspect of RedCap feature to SA for Approval | For approval
SP-241609 | Presentation of TR 28.870 Study on Enablers for Security Monitoring to SA for Information and Approval | for Information and Approval
SP-241610 | Presentation of TS 28.abc to SA for Information and Approval | for Information and Approval
SP-241611 | Presentation of TR 28.879 Study on OAM for service management and exposure to external consumers to SA for Approval | For approval
SP-241612 | Presentation of TR 28.866 Study on Management Data Analytics (MDA) – Phase 3 to SA for Approval | For approval
SP-241613 | Presentation of TR 28.867 Study on closed control loop management to SA for Information and Approval | for Information and Approval
SP-241614 | Presentation of TR 28.874 Study on Management Aspects of NTN Phase 2 to SA for Approval | For approval
SP-241615 | Presentation of TR 28.875 Study on management of IAB nodes to SA for Approval | For approval
SP-241616 | Presentation of TR 28.914 Study on intent driven management service for mobile network phase 3 to SA for Approval | For approval
4 TRs send to SA for information, approval, 10 TRs send to SA for approval, 4 TRs send to SA for information and approval

## Slide 25: List of SA5 CR pack to SA#106
List of Rel-19 CRs:
SP-241638 CR Pack on TEI19 - Pack 1/3
SP-241639 CR Pack on TEI19 - Pack 2/3
SP-241640 CR Pack on TEI19 - Pack 3/3
SP-241647 CR Pack on AdNRM_Ph3
SP-241648 CR Pack on PM_KPI_5G_Ph4
SP-241649 CR Pack on TraceQoE_OAM
SP-241654 CR Pack on NWDAF_OAM_Ph2
SP-241660 CR Pack on Ranging_SL_CH
SP-241661 CR Pack on CHFSeg
SP-241664 CR Pack on eMDAS_Ph2
SP-241665 CR Pack on NetShare_CH
SP-241666 CR Pack on FS_Data_SREP
List of Rel-11/Rel-15/Rel-16/Rel-17/Rel-18 CRs:
SP-241631 CR Pack on TEI17 - Pack 1/4
SP-241632 CR Pack on TEI17 - Pack 2/4
SP-241633 CR Pack on TEI17 - Pack 3/4
SP-241634 CR Pack on TEI17 - Pack 4/4
SP-241635 CR Pack on TEI16 - Pack 1/3
SP-241636 CR Pack on TEI16 - Pack 2/3
SP-241637 CR Pack on TEI16 - Pack 3/3
SP-241641 CR Pack on TEI18 - Pack 1/3
SP-241642 CR Pack on TEI18 - Pack 2/3
SP-241643 CR Pack on TEI18 - Pack 3/3
SP-241644 CR Pack on AIML_MGT - Pack 1/2
SP-241645 CR Pack on AIML_MGT - Pack 2/2
SP-241646 CR Pack on TEI15
SP-241650 CR Pack on eSBMA
SP-241651 CR Pack on AdNRM_ph2
SP-241652 CR Pack on CHRACHF
SP-241653 CR Pack on eECM
SP-241655 CR Pack on IDMS_MN_ph2
SP-241656 CR Pack on PM_KPI_5G_Ph3
SP-241657 CR Pack on OAM_NTN
SP-241658 CR Pack on eMDAS
SP-241659 CR Pack on 5GMDT_Ph2
SP-241662 CR Pack on eQoE
SP-241663 CR Pack on MANS_ph2
SP-241667 CR Pack on EE5GPLUS_Ph2

## Slide 26: Management and Orchestration

## Slide 27: 1. AIML：Study on AI/ML management - phase 2
Progress since SA#105:
  Following AIML management capabilities have been concluded and recommended for R19 normative work:
    Management capabilities for ML model training，including ML-Knowledge-based Transfer Learning, ML pre-training and fine-tuning, Management of Reinforcement Learning, Sustainable AI/ML for ML training, Management of Federated Learning, ML explainability, etc.
    Management capabilities for AI/ML inference emulation, including ML inference emulation, ML inference emulation environment selection.
    Management capabilities for ML model deployment, including Enhancements to ML model loading, ML model transfer/delivery.
    Management capabilities for AI/ML inference, including Coordination between the ML capabilities, ML remedial action management, etc.
  Following AIML management scenarios have been concluded and recommended for normative work:
    NG-RAN AIML-based Coverage and Capacity Optimization, and NG-RAN AIML-based Network Slicing defined by RAN3,
    Model delivery/transfer as defined by RAN1/2,
    ML model training and AI/ML inference functions for 5GC as defined by SA2
    MDA (Management Data Analytics) as defined by SA5.
  Impacts and dependencies on other WGs:
  Collaboration with SA1 on AI/ML related requirements, SA2 on 5GC AIML, SA3 on AIML security, SA6 on Application enablement layer AIML and RAN WGs for related requirements.
Next steps:
  This study is completed, Rel-19 normative work will start from next meeting.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020007 | Study on AI/ML management - phase 2 | FS_AIML_MGT_Ph2 | 12/12/2024 | 55% | SP-240965 | 100% | 
OAM Prime feature

## Slide 28: 2. MDA：Study on Management Data Analytics (MDA) – Phase 3
Progress since SA#105:
  Added use case to improve handling of predicted failures
  Added conclusions and recommendations
  Impacts and dependencies on other WGs:
  Coordination with SA1 on service requirements, SA2 on NWDAF, RAN3 on data collection.
Next steps:
  This study is completed, Rel-19 normative work will start from next meeting.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020019 | Study on Management Data Analytics (MDA) Phase 3 | FS_eMDAS_Ph3 | 12/12/2024 | 90% | SP-241157 | 100% | 
OAM Prime feature

## Slide 29: 3. IDM: Study on intent driven management services for mobile network phase 3
Progress since SA#105:
  WT-3: The intent negotiation functionalities during fulfillment phase are evaluated and concluded, and following functionalities are recommended for normative work: checking for fulfillable outcomes, checking for best possible outcome, recommending fulfillable intent targets and contexts, advises on preferred alternatives.
  WT-4: The Intent Utility Function are evaluated and concluded, it is recommended to start normative work for specifying methods by which consumers can express the relative value of an intent's expectations to assist the IDMS producer(s) in fulfilling their intents in the most acceptable manner.
  Impacts and dependencies on other WGs:
  Provide radio network management support to SA1 on UAV pre-flight preparation requirements
Next steps:
  This study is completed, Rel-19 normative work will start from next meeting.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020008 | Study on intent driven management services for mobile network phase 3 | FS_IDMS_MN_Ph3 | 12/12/2024 | 95% | SP-231737 | 100% | 
OAM Prime feature

## Slide 30: 4. CCL: Study on closed control loop management
Progress since SA#105:
  Evaluation and Conclusion are updated for Use case 5
  Clarification provided for escalation Recipient
  Clarify evaluation for Feedback use case
  Impacts and dependencies on other WGs:
  None
Next steps:
  This study is completed, Rel-19 normative work will start from next meeting.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020009 | Study on closed control loop management | FS_CCLM | 12/12/2024 | 90% | SP-231735 | 100% | 
OAM Prime feature

## Slide 31: 5. NDT: Study on management aspects of Network Digital Twin
Progress since SA#105:
  Following NDT use cases have been concluded and recommended for normative work:
  NDT support for network automation including signaling storm analysis, emergency preparedness, network failure and risk prediction and network issue inducement.
  NDT support for verification including RAN energy saving policy verification, configuration verification.
  NDT support for generation including generating data for ML model training and measuring customer satisfaction with the network services
  Advanced NDT capabilities including nested NDTs.
  Impacts and dependencies on other WGs:
  Coordination with SA1 on terminology.
Next steps:
  This study is completed, Rel-19 normative work will start from next meeting.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020018 | Study on management aspects of Network Digital Twin | FS_NDT | 12/12/2024 | 95% | SP-231727 | 100% | 
OAM Prime feature

## Slide 32: 6. CMO: Study on Cloud Aspects of Management and Orchestration
Progress since SA#105:
  General : Discussion CMO blocking points, evaluations and conclusions, but have no consensus at this meeting, so the TR has been extended.
  WT-1: Discussion on use cases in terms of configuration, traffic, upgrade and policy management, but have no consensus at this meeting, and some other updates
  of use cases were documented.
  WT-2: Discussion on evaluation for use cases in terms of LCM of NF Deployment and data streaming use cases, but have no consensus at this meeting. And have
  achieved updates agreement on some solutions and Annexs.
  WT-3: Discussion on adding potential solution for Placement of cloud native NFs, but have no consensus.
  Impacts and dependencies on other WGs:
  None
Next steps:
  The group decided to continue the study in Rel-19 on this topic.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020010 | Study on Cloud Aspects of Management and Orchestration | FS_Cloud_OAM | 12/12/2024 | 80% | SP-231781 | 90% | 
OAM Prime feature

## Slide 33: 7. MSEC: Study on Enablers for Security Monitoring
Progress since SA#105:
  Final rapporteur's clean-up of the draft TR.
  Impacts and dependencies on other WGs:
  The events/usecases which can lead to security risks/threats and the related data that needs to be exposed need to be primarily defined by SA3
Next steps:
  This study is completed, no normative Rel-19 work is planned so far.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020016 | Study on Enablers for Security Monitoring | FS_SECM | 12/12/2024 | 90% | SP-231736 | 100% | 
OAM Prime feature

## Slide 34: 8. SBMA: Study on Service Based Management Architecture enhancement phase 3
Progress since SA#105:
  The following topics were approved:
  Conclusions for Alarm handling
  Reliable notification handling improvements
  Correct missing reference
  Update recommendation and conclusion for MnS Version Number Handling
  Presentation sheet for SA approval
  Impacts and dependencies on other WGs:
  None
Next steps:
  This study is completed, Rel-19 normative work will start from next meeting.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020011 | Study on Service Based Management Architecture enhancement phase 3 | FS_SBMA_Ph3 | 12/12/2024 | 75% | SP-231725 | 100% | 
OAM Prime feature

## Slide 35: 9. PTM: Management of planned configurations
Progress since SA#105:
  The following topics are discussed and approved:
  Stage 1 and 2 for conditional activation of planned configurations was added
  Improvements were agreed for stage 2 of
    managing planned configurations.
    managing planned configuration groups.
    validating planned configurations.
    activating planned configurations.
  Some stage 3 examples were added.
  Impacts and dependencies on other WGs:
  None
Next steps:
  Continue according to the plan
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020033 | Study on Management of planned configurations | FS_PlanM | 09/09/2024 | 60% | SP-231721 | 100% | 
1050032 | Management of planned configurations | PlanM | 09/09/2025 | 0% | SP-241379 | 60% | 
OAM Prime feature

## Slide 36: 10. MADCOL: Data management phase 2
Progress since SA#105:
  Solution for managing external management data agreed
  description of requirements for external management data agreed
  Model for external data has been enhanced.
  Impacts and dependencies on other WGs:
  None
Next steps:
  continue according to the plan.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020025 | Data management phase 2 | MADCOL_Ph2 | 06/06/2025 | 80% | SP-240877 | 88% | 
OAM Prime feature

## Slide 37: 11. SREP: Data management regarding subscriptions and reporting
Progress since SA#105:
  WT#1 did not have any contributions
  WT#2 had 4 contributions that was withdrawn. .
  Impacts and dependencies on other WGs:
  None
Next steps:
  Continue as per plan
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020012 | Study on data management regarding subscriptions and reporting | FS_Data_SREP | 09/09/2024 | 60% | SP-231732 | 100% | 
1050033 | Data management regarding subscriptions and reporting | Data_SREP | 09/09/2025 | 0% | SP-241380 | 0% | 
OAM Prime feature

## Slide 38: 12. PM: 5G performance measurements and KPIs phase 4
Progress since SA#105:
  WT-1 (Rel19 PM/KPI):
    Add PMF measurement of network-initiated PLR for ATSSS
    Monitoring of Sub-Optimal Handovers
    New performance measurements for Reduced Capability (RedCap) Device Early Identification
    Correct LTM measurements and Update mobility KPI for LTM and Add LTM use case
    Add Mean time and max time of MA PDU session establishment (agreed)
    Add UC reference for LTM related PM definition(agreed)
    New measurements to monitor Inter MN CHO with Candidate SCGs?
    New measurements to monitor the DL packet delay for XR PDU sets (not pursued)
  WT-2 (Rel18 PM/KPI):
    Add XR PDU set packet delay measurement
    New performance measurements for eDRX negotiation registration requests and accepts and new KPIs for Extended DRX Negotiation Success Rate
    New performance measurements for UE assistance information with RRM Measurement Relaxation and new KPIs for Connected Mode RRM Relaxation Usage
    enhance the RAN UE throughput definition in 28.552 and 28.554(not pursued)
    contribution on Sub Optimal Handover Metrics (trigger a revised CR)
  WT-3 (UE level measurements), “corrections on UE level measurement related to Data Volume was submitted in this meeting” is agreed.
  WT-4 No contribution for PM streaming framework enhancement was submitted in this meeting.
  Impacts and dependencies on other WGs:
  Potential coordination: providing performance measurements to network features defined in SA2, RAN2 and RAN3.
Next steps:
  Continue the work per the plan, some WTs may need to be expedited.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020026 | 5G performance measurements and KPIs phase 4 | PM_KPI_5G_Ph4 | 06/06/2025 | 30% | SP-241155 | 65% | 
OAM Support to Network features

## Slide 39: 13. AdNRM: 5G Advanced NRM features phase 3
Progress since SA#105:
  The following topics are discussed and approved:
  WT-1 (5GC NRM):
    Enhancements on DefaultNotificationSubscription agreed.
    Enhancements on NFService in NRFFunction IOC
    NRM enhancements to NFProfile discussed but not agreed.
    Alignment of attribute value list with TS29.510 for UPInterfaceType notificationType and supportedDataSets agreed.
  WT-2 (NR NRM):
    NRM extensions for VMR Ph2 discussed, a basic modeling agreed.
    Way forward for Federated Network Information Model (FNIM) agreed
    Add max preamble to support msg1 repetition for RACH discussed but not agreed
    Adding cell coverage configuration to support CCO in RAN3 is discussed and agreed
  WT-4 (Generic NRM):
    Alignment of IP Address modeling agreed
    Enhance the multiplicity property for generic NRM
    Enhance the isUnique property for stage 3 OpenAPI for TraceControlNrm
  WT-5 (Stage3 enhancement):
    Enhance the OpenAPI related to multiplicity for NrNrm and SliceNrm
    5GC NRM and Network Slicing NRM openAPI to include the missing default values NRM.
    Enhance the isUnique/isReadOnly property for stage 3 OpenAPI.
  WT-6 (Edge):
    adding managed services to Edge entities agreed
  Revising the WID related to TS28.662 has been discussed and agreed, one new WT added.
  Impacts and dependencies on other WGs:
  Potential coordination: providing network resource model for network features defined in SA2, CT4, RAN3 and RAN4.
Next steps:
  5GC/NR/Edge/Stage3 NRM enhancement.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020027 | 5G Advanced NRM features phase 3 | AdNRM_Ph3 | 06/06/2025 | 30% | SP-240875 | 60% | 
OAM Support to Network features

## Slide 40: 14. TMQ: Subscriber and Equipment Trace and QoE collection management
Progress since SA#105:
  The procedure for Trace session activation for RRC reporting in NG-RAN in 32.422 was corrected as well as corrections of RRC reporting was made in 32.421, 32.422, 28.622 and 28.623
  Update minor error of RRC report
  enhance the area scope to support Network Slice Based MDT according to the incoming RAN3 LS
  Impacts and dependencies on other WGs:
  SA2, SA4, CT1, CT4, RAN2 and RAN3.
  RAN has proposals for work that might impact Trace, MDT and QoE in RP-232624.
  Studies in SA2 might impact Trace, MDT and QoE in Rel-19.
  If Signalling Based Activation is affected, CT4, RAN2 and RAN3 are affected.
Next steps:
  Continue according to the plan
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020028 | Subscriber and Equipment Trace and QoE collection management | TraceQoE_OAM | 06/06/2025 | 40% | SP-231748 | 75% | 
OAM Support to Network features

## Slide 41: 15. NTNM: Study on Management Aspects of NTN Phase 2
Progress since SA#105:
  Following aspects have been agreed:
  A generic time based configuration solution was agreed to support configuration of :
    Connections between RAN node on-board satellite and CN (regenerative mode)
    Associations between SectorEquipmentFunction on-board satellite and the RAN nodes (gNB/eNB) on ground (transparent mode)
    NTN neighbor cell management
    Connections between UPF on board and SMF on ground
  Provide the solution to support configuration of NTN gNB supported TAIs to AMF to support regenerative payload as required by RAN3 (R3-245845)
  Impacts and dependencies on other WGs:
  Co-ordination with SA2, RAN2, RAN3 where appropriate.
Next steps:
  This study is completed, Rel-19 normative work will start from next meeting.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020013 | Study on Management Aspects of NTN Phase 2 | FS_NTN_OAM_Ph2 | 12/12/2024 | 90% | SP-231733 | 100% | 
OAM Support to Network features

## Slide 42: 16. IABM: Study on management of IAB nodes
Progress since SA#105:
  All of contributions including WID were approved in this meeting:
  S5-246130 New WID on management of IAB nodes
  S5-245443 Presentation of TR 28.875 to SA for information
  S5-246098 pCR TR 28.875 conclusion for IAB node configuration
  S5-246099 pCR TR 28.875 conclusion for IAB node OAM connectivity.
  Impacts and dependencies on other WGs:
  Collaboration with SA2 on architecture enhancements, SA3 on security and RAN3 on NR Mobile IAB
Next steps:
  This study is completed, Rel-19 normative work will start from next meeting.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020014 | Study on management of IAB nodes | FS_NR_mobile_IAB_OAM | 12/12/2024 | 90% | SP-231729 | 100% | 
OAM Support to Network features

## Slide 43: 17. RedcapM: Study on management aspects of RedCap feature
Progress since SA#105:
  WT-1:
  Update requirements and conclusions for Use case #1 is approved.
  WT-2:
  Requirement and add potential solution for Inactive RedCap UEs are proposed and discussed.
  Conclusion and recommendation for resource load of RedCap service are proposed and discussed.
  WT-3:
  Solution and conclusion for RedCap EE KPI are approved.
  WT-4:
  Evaluation, conclusion and recommendation for RedCap Information Exposure are proposed and approved.
  Impacts and dependencies on other WGs:
  RAN1 on RedCap related requirements and Physical layer methods
  SA2 on 5GC RedCap related NF services and configurations.
Next steps:
  This study is completed, Rel-19 normative work will start from next meeting.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020017 | Study on management aspects of RedCap feature | FS_NR_RedCap_OAM | 12/12/2024 | 75% | SP-231734 | 100% | 
OAM Support to Network features

## Slide 44: 18. NWDAFM: Enhancement of Management Aspects related to NWDAF Phase 2
Progress since SA#105:
  For WT1
  S5-247207 is approved and it adds roaming exchange capability information to NWDAFFunction to TS28.541
  S5-246106: Fundamental performance measurements of NWDAF providing roaming analytics, such as numbers of
  subscription/request/notification/response are provide. The number of the successful and a partial of the failure roaming analytics subscription, as well as the time consumption of roaming analytics servics are provided.
  S5-246107: Providing use case decription related to the S5-246106.
  For WT2
  S5-247208 is approved and it updates the Use Case description on Monitoring of NWDAF data collection
  S5-247209 is approved and it adds measurements related to the NWDAF Data Collection from one NF
  S5-247210 is approved and it adds measurements related to the NWDAF data collection when DCCF is deployed
  Impacts and dependencies on other WGs:
  Collaboration with SA2 on NWDAF.
Next steps:
  Complete the work on the WT1
  Continue the work on the WT2
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020020 | Study on Enhancement of Management Aspects related to NWDAF Phase 2 | FS_NWDAF_OAM_Ph2 | 09/09/2024 | 75% | SP-231724 | 100% | 
1050031 | Enhancement of Management Aspects Related of NWDAF Phase 2 | NWDAF_OAM_Ph2 | 06/06/2025 | 0% | SP-241378 | 60% | 
OAM Support to Network features

## Slide 45: 19. NSM: Study on Management of Network Sharing Phase3
Progress since SA#105:
  For WT-1:
  Evaluation, conclusions and recommendations of Use Case #1 Service-based management architecture and access requirements for MOCN is added.
  For WT-2:
  Evaluation, conclusions and recommendations of Use Case #2 Trace job and collection requirements for POPs is added.
  For WT-3:
  Evaluation, conclusions and recommendations of Use Case #3-#6 Management of Indirect Network Sharing are added.
  Impacts and dependencies on other WGs:
  SA1 and SA2
Next steps:
  This study is completed, Rel-19 normative work will start from next meeting.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020015 | Study on Management of Network Sharing Phase3 | FS_NetShare_OAM_Ph3 | 12/12/2024 | 90% | SP-240966 | 100% | 
OAM Support to Network features

## Slide 46: 20. EE: Rel-19 - Study on energy efficiency and energy saving aspects of 5G networks and services
Progress since SA#105:
  New use cases have been introduced (e.g. renewable energy-based LBO, cell proximity-based energy saving, per-network slice gNB and 5GC NF energy consumption),
  Potential solutions have been elaborated for (existing and new) use cases (e.g. for handling of power shortages, renewable energy enabling 5GC NF re-selection),
  Conclusions and recommendations for normative work have been agreed.
  Impacts and dependencies on other WGs:
  The following WGs address aspects related to this study:
    SA1 and SA2, for aspects described in WT-2 and WT-5
    RAN1, RAN2 and RAN3, for aspects described in WT-3 and WT-5.
Next steps:
  This study is completed, Rel-19 normative work will start from next meeting.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020021 | Study on energy efficiency and energy saving aspects of 5G networks and services | FS_Energy_OAM_Ph3 | 12/12/2024 | 60% | SP-231723 | 100% | 
OAM Prime feature

## Slide 47: 21. Mexpo: Study on Enhanced OAM for management exposure to external consumers
Progress since SA#105:
  Revised SID proposes to down scope to objectives, i.e., to remove WT-2 and WT-3, as there has not been any content related to these WTs in the TR 28.879.
  TR 28.879 was enhanced to describe the scope and address comments from editHelp.
  The group agreed on the following aspects :
    For the exposure of management services through the CAPIF framework, 3GPP management system should define a functional entity to provide the API provider domain functions.
    new potential solutions (together with their evaluations) were introduced for:
      Use case #2: Publishing of management services to the CCF
      Use case #4: Authorization of the external MnS consumer to access the management service API
    All use cases now have requirement(s), potential solution(s) and evaluation of potential solution(s), with Common API Framework (CAPIF) as the selected exposure framework.
      Exception is Use Case #3: Configuring discovery policy information for an external MnS consumer, for which no impact on 3GPP management system has been identified.
    The conclusion and recommendation for the normative work for exposure of management services to external consumers has been documented.
  Impacts and dependencies on other WGs:
  Solutions proposed for identified use cases build upon R18 CAPIF features. Rel-18 CRs approved by SA6 (CAPIF stage-2), CT3 (CAPIF stage-3) and SA3 (CAPIF related security aspects) may impact these solutions; coordination will be required in such cases.
Next steps:
  This study is completed, Rel-19 normative work will start from next meeting.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020022 | Study on Enhanced OAM for management exposure to external consumers | FS_MExpo | 12/12/2024 | 60% | SP-240967 | 100% | 
OAM Prime feature

## Slide 48: 22. MonstraM: Management for MonStra
Progress since SA#105:
  agreed architecture and framework
  stage 2 and 3 are complete
  all the concepts have been agreed
  impressive productivity and teamwork
  we do have solutions satisfying the captured SA1 requirements
  Impacts and dependencies on other WGs:
  SA3 to specify the security aspects.
Next steps:
  need to fix remaining editors' notes (parameter names, etc...)
  plan to submit the TS to Madrid SA plenary for approval
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
 | Management for MonStra | Monstra-OAM | 12/12/2024 | 0% | S5-245981 | 80% | New WID submitted to SA#106 for approval
OAM Prime feature

## Slide 49: Charging

## Slide 50
SA5 CH SWG acknowledged in SA5
Forge process
  Yaml and ASN.1 code were successful made available for Rel-19
  moderators are expected to work on Forge from now
  Acknowledgment to
    Chen Shan (Huawei) – yaml code moderator
    Robert Törnkvist (Ericsson) – ASN.1 code moderator
    Miguel Angel Reina Ortega (ETSI) - MCC forge expert
SA5 SWG participations
  Good improvement on visibility based on participation of global acting MNOs and service providers as well as vendors for communication services
General information

## Slide 51: Charging (CH) WIs/SIs

## Slide 52: SA5 CH progress – Summary
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
 | Rel-19 Work Items | ------ | ----- | ------ | ---- | ---- | 
1040012 | WID on CHF Segmentation | CHFSeg | 03/03/2025 | 5 % | SP-241001 | 55 % | 
1040013 | WID on Charging Aspects of Ranging and Sidelink Positioning | Ranging_SL_CH | 03/03/2025 | 20 % | SP-241002 | 100 % | Completed This WI is a Rel-19 WI instead of Rel-18.
1040018 | WID on charging aspects for energy efficiency of 5G | EnergySys_CH | 13/06/2025 | 45 % | SP-241003 | 45 % | 
1040019 | WID on charging enhancement for indirect network sharing | NetShare_CH | 12/12/2024 | 0 % | SP-241004 | 0 % | 
1050030 | New WID on Charging for 5G ProSe Ph3 | 5G_ProSe_Ph3_CH | 12/09/2025 | 0 % | SP-241156 | 100 % | completed
 | Rel-19 Studies | ------ | ----- | ------ | ----- | ---- | 
1040014 | Study on charging aspects of satellite access Phase 3 | FS_5GSAT_Ph3_CH | 1212/2024 | 40% | SP-240980 | 75 % | Delayed, pending work in SA2 on 5GSAT_Ph3-ARC)
1040015 | SID on Charging Aspects of CAPIF | FS_CAPIF_Ph2_CH | 12/12/2024 | 35 % | SP-240981 | 75 % | Acronym needs to be updated. Delayed, additional aspects from GSMA OPG, WID is feasible based on CRs in Rel-19
1040016 | SID on Charging aspects of next generation real time communication services phase 2 | FS_NG_RTC_Ph2_CH | 12/12/2024 | 45 % | SP-240982 | 75 % | Delayed, pending work in SA2 on NG_RTC_Ph2
1040017 | SID on Charging aspects of Uncrewed Aerial Vehicle | FS_UAS_Ph2_CH | 12/12/2024 | 40 % | SP-240983 | 75 % | Acronym needs to be updated. Delayed, pending work in SA2 on UAS_Ph3
For more information, see the full Work Plan at: ftp://ftp.3gpp.org/information/WorkPlan

## Slide 53: 1. CHSEG: WID on CHF Segmentation
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1040012 | WID on CHF Segmentation | CHFSeg | 03/03/2025 | 5 % | SP-241001 | 25 % | 
Progress since SA#105
  3 CRs agreed covering:
    Addition of NRF discovery reference for SMF (32.255) and AMF (32.256)
    Clarify the query attributes for NRF based CHF discovery (32.290)
RAN impacts and dependencies:
  None identified
Next steps:
  Use of CHF Group Id for CHF selection and procedures/message flow, PCF interaction when N107 is used
CH Prime feature

## Slide 54: 2. RAGCH: WID on Charging Aspects of Ranging and Sidelink Positioning
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1040013 | WID on Charging Aspects of Ranging and Sidelink Positioning | Ranging_SL_CH | 03/03/2025 | 20 % | SP-241002 | 50 % | 
Progress since SA#105
  7 CRs agreed covering:
    Introduction of Ranging and Sidelink Positioning Charging (TS 32.271)
    Add converged charging architecture for Ranging and Sidelink Positioning, principles for Ranging and Sidelink Positioning Charging (TS 32.271)
    Add message flows of converged charging for UE positioning assisted by Sidelink Positioning and involving 5GC (TS 32.271)
    Add CDR generation and handling for converged charging of Ranging and Sidelink Positioning (TS 32.271)
    Introduction of Data Type and Binding for Ranging and Sidelink Positioning Charging (TS 32.291)
RAN impacts and dependencies:
  None identified
Next steps:
  Introduce OpenAPI extension and charging information to CDR
CH Support to Network features

## Slide 55: 3. EESCH: WID on charging aspects for energy efficiency of 5G
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1040018 | WID on charging aspects for energy efficiency of 5G | EnergySys_CH | 13/06/2025 | 0 % | SP-241003 | 45 % | 
Progress since SA#105
  3 CRs agreed covering:
    Support the energy related information per network slice (32.240, 28.201 and 28.202)
RAN impacts and dependencies:
  None identified
Next steps:
  Message flow and parameter definition
CH Support to Network features

## Slide 56: 4. NSCH: WID on charging enhancement for indirect network sharing
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1040019 | WID on charging enhancement for indirect network sharing | NetShare_CH | 12/12/2024 | 0 % | SP-241004 | 100 % | completed
Progress since SA#105
  1 CR agreed covering:
    Addition network sharing (TS 32.240)
RAN impacts and dependencies:
  None identified
Next steps:
  None
CH Support to Network features

## Slide 57: 5. PROCH: WID on Charging Aspects for 5G ProSe Ph3
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1050030 | New WID on Charging Aspects for 5G ProSe Ph3 | 5G_ProSe_Ph3_CH | 12/09/2025 | 0 % | SP-241156 | 0 % | 
Progress since SA#105
  No contribution
RAN impacts and dependencies:
  None identified
Next steps:
  Start the WID
CH Support to Network features

## Slide 58: 6. SATCH: Study (FS_5GSAT_CH_Ph3)
Progress since SA#105
  14 pCRs for TR 28.846 were approved covering
    Add the skeleton, scope and reference, background and the business roles and use cases for the roaming charging of satellite access
    Add business scenarios for roaming from terrestrial operator network to satellite operator network, for satellite resource rental between satellite network operator and terrestrial network operator and for store and forward satellite operation
    Charging for satellite resource rental between satellite network operator and terrestrial network operator and between satellite operator and satellite MVNO
    Add store and forward satellite operation charging solutions for SMS, for Control Plane CIoT
    Update charging scenario and introduce the solutions for Satellite Roaming Charging
    Clarification of topic 1,2 and 3 use cases and evaluation for store and forward satellite operation charging added
  Draft TR 28.846 for Information in S5-246952
RAN impacts and dependencies:
  None identified
Next steps:
  Drafting of requirements, key issues, solutions, evaluation and conclusion for the study
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1040014 | Study on charging aspects of satellite access Phase 3 | FS_5GSAT_Ph3_CH | 12/12/2024 | 10 % | SP-240980 | 75 % | Delayed, pending work in SA2 on 5GSAT_Ph3-ARC)
CH Support to Network features

## Slide 59: 7. CAPCH: Study (FS_CAPIF_Ph2_CH)
Progress since SA#105
  25 pCRs for TR 28.849 were approved covering
    The initial skeleton, update skeleton and document structure
    The scope, references and background
    Introduce the background of CAPIF charging
    Add Topic for CAPIF Charging Scenarios and KI and on API invocation charging
    Addition of use cases for the CAPIF Converged Charging of multiple API Providers, API Invokers, API Usage and API operation and management
    Introduce the solution for API invocation charging
    Editorial and Business Relations corrections
    New Use Case: API Invoker
    Solutions: API Service Management, Multiple API Providers, Service API Management, and API Invoker Management
  Draft TR 28.849 for Information in S5-247046
RAN impacts and dependencies:
  None identified
Next steps:
  CAPIF use cases, solutions for existing use cases, new topic (API Usage) and topic evaluations
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1040015 | SID on Charging Aspects of CAPIF | FS_CAPIF_Ph2_CH | 12/12/2024 | 15 % | SP-240981 | 75 % | Delayed, additional aspects from GSMA OPG, WID is feasible based on CRs in Rel-19
CH Support to Network features

## Slide 60: 8. RTCCH: Study (FS_NG_RTC_Ph2_CH)
Progress since SA#105
  14 pCRs for TR 28.851 were approved covering
    The initial skeleton and update skeleton with scope, references and background
    Support of standalone IMS Data Channel sessions
    Introduce the use case of charging for DC application download and usage
    New KI on support IMS network capabilities exposure and on support IMS Data Channel PS Data Off
    Adding solution on IMS converged charging for standalone IMS Data Channel
    New charging solution for IMS network capabilities exposure
    Update charging scenario for DC application usage
    New charging solution for DC application download
  Draft TR 28.851 for Information in S5-247047
RAN impacts and dependencies:
  None identified
Next steps:
  Add more use cases, key issues and corresponding solutions.
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1040016 | SID on Charging aspects of next generation real time communication services phase 2 | FS_NG_RTC_Ph2_CH | 12/12/2024 | 10 % | SP-240982 | 75 % | Delayed, pending work in SA2 on NG_RTC_Ph2
CH Support to Network features

## Slide 61: 9. UASCH: Study (FS_UAS_Ph2_CH)
Progress since SA#105
  16 pCRs for TR 28.853 were approved covering
    Add initial skeleton and update skeleton, scope, background, references and abbreviations.
    Add use cases and key issues related to UAV identifier and C2 communication.
    Add use cases, key issues and solutions on charging for Services Exposure to the USS
    Introduce the Aircraft-to-Everything for UAS Charging.
    Add UAS charging solution with UAV indication.
    Update charging solution for UAS service invocation.
  Draft TR 28.853 for Information in S5-247048
RAN impacts and dependencies:
  None identified
Next steps:
  Add possible solutions, evaluations and conclusions.
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1040017 | SID on Charging aspects of Uncrewed Aerial Vehicle | FS_UAS_Ph2_CH | 12/12/2024 | 0 % | SP-240983 | 75 % | Delayed, pending work in SA2 on UAS_Ph3
CH Support to Network features

## Slide 62
Charging TSs & TRs to be sent to SA#106
Number | Title | For
S5-246952 | Presentation of TR 28.846 for Information (for email approval) | Information
S5-247046 | Presentation of TR 28.849 for Information (for email approval) | Information
S5-247047 | Presentation of TR 28.851 for Information (for email approval) | Information
S5-247048 | Presentation of TR 28.853 for Information (for email approval) | Information

## Slide 63: Thank you!

## Slide 64: General information (time plan/meeting plan/forge)

## Slide 65
Release 19 timeline– figure with SA5 (Based on SA timeline)
Release 19 timeline
#101
#102
#103
#104
#105
#106
#107
#108
#109
#110
#111
#112
#99
RAN4
content def.
RAN Content def.
2024
2025
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Mar.
Dec.
Dec.
Dec.
2026
RAN4_Perf
Stage 3 (CT & SA including SA5)
RAN1
Stage 2 (SA2, SA6,…) Normative
RAN Completion (RAN2/3/4core)
ASN.1 & Open APIs
St.2 Content approval
#100
Jun.
2023
Now
100%
SA1 Stage 1 80%
TSGs
RAN Rel-19 workshop
SA Rel-19
Workshop
Management requirements (SA5)
Stage 2 (SA5) Normative supporting SA&RAN
OAM:
Dec 2024: finalize Rel-19 studies which plan to have corresponding normative work in Rel-19.
Sep 2025: finalize all Rel-19 work items, majority work items are preferable to be finalized in Jun 2025.
CH:
Dec 2024: finalize Rel-19 studies which plan to have corresponding normative work in Rel-19.
Sep 2025: finalize all Rel-19 work items
Note: Studies can continue until Sep.2025 if no corresponding normative work is planned for Rel-19.
3GPP SA5
Time plan

## Slide 66: 3GPP SA & SA5 meeting calendar (2024)
Meeting info | DateTime | Location | Release dates | Other WGs (potential colocation)
SA5#153 | 29 Jan 2024 – 2 Feb 2024 | Sevilla, ES |  | SA3 LI
SA#103 | 19 Mar 2024 - 22 Mar 2024 | Maastricht , NL | Rel-18 freeze | 
SA5#154 | 15 Apr 2024 - 19 Apr 2024 | Changsha , CN |  | CT WGs, SA WGs, RAN WGs
SA5#155 | 27 May 2024 - 31 May 2024 | Jeju, KR |  | SA WGs
SA#104 | 18 Jun 2024 - 21 Jun 2024 | Shanghai , CN |  | 
SA5#156 | 19 Aug 2024 - 23 Aug 2024 | Maastricht , NL |  | CT WGs, SA WGs, RAN WGs
SA#105 | 10 Sep 2024 - 13 Sep 2024 | Melbourne , AU |  | 
SA5#157 | 14 Oct 2024 - 18 Oct 2024 | Hyderabad , IN |  | SA WGs
SA5#158 | 18 Nov 2024 - 22 Nov 2024 | Orlando , US |  | CT WGs, SA WGs, RAN WGs
SA#106 | 10 Dec 2024 - 13 Dec 2024 | Madrid , ES |  | 
Please book your hotel/flight when you received official meeting invitation

## Slide 67: 3GPP SA & SA5 meeting calendar (2025)
Meeting info | DateTime | Location | Release dates | Other WGs (potential colocation)
SA5#159 | 17 Feb 2025- 21 Feb 2025 | Sophia Antipolis, FR |  | 
SA#107 | 10 Mar 2025- 14 Mar 2025 | Incheon, South Korea | 6G workshop | 
SA5#160 | 07 Apr 2025- 11 Apr 2025 | Goteborg, SE |  | SA2/3/4/5/6
SA5#161 | 19 May 2025- 23 May 2025 | Fukuoka, Japan |  | SA WGs
SA#108 | 09 Jun 2025- 13 Jun 2025 | Europe |  | 
SA5#162 | 25 Aug 2025- 29 Aug 2025 | Goteborg, SE |  | SA WGs/CT WGs
SA#109 | 15 Sep 2025- 19 Sep 2025 | China | Rel-19 freeze | 
SA5#163 | 13 Oct 2025- 17 Oct 2025 | China |  | SA2/3/4/5/6 and CT1/3/4 WGs
SA5#164 | 17 Nov 2025- 21 Nov 2025 | US |  | CT WGs, SA WGs, RAN WGs
SA#110 | 08 Dec 2025- 12 Dec 2025 | US |  | 
6 f2f SA5 meeting planned in 2025, 3 meetings in Europe, 1 in Japan, 1 in China, 1 in US.
Please book your hotel/flight when you received official meeting invitation

## Slide 68: 3GPP SA & SA5 meeting calendar (2026)
Meeting info | DateTime | Location | Release dates | Other WGs (potential colocation)
SA5#165 | 9 Feb 2026 - 13 Feb 2026 | India |  | 
SA#111 | 9 Mar 2026 - 13 Mar 2026 | Japan |  | 
SA5#166 | 13 Apr 2026 - 17 Apr 2026 | Europe |  | 
SA5#167 | 18 May 2026 - 22 May 2026 | China |  | 
SA#112 | 08 Jun 2026 - 12 Jun 2026 | Singapore |  | 
SA5#168 | 24 Aug 2026 - 28 Aug 2026 | Europe |  | 
SA#113 | 14 Sep 2026 - 18 Sep 2026 | Europe |  | 
SA5#169 | 12 Oct 2026 - 16 Oct 2026 | Europe |  | 
SA5#170 | 16 Nov 2026 - 20 Nov 2026 | North America |  | 
SA#114 | 07 Dec 2026 - 11 Dec 2026 | North America |  | 
Reference: confirmed tdoc from MHPG
6 f2f SA5 meeting planned in 2026, SA5 meetings to be collocated with other SA WG as much as possible.

## Slide 69: Rel-19 SA5 Summary Information in forge
SA5 Rel-19 ongoing topics
  Details of SA5 Rel-19 approved WIDs/SIDs : https://forge.3gpp.org/rep/sa5/MnS/-/wikis/SA5/Rel-19-Moderated-Topics
Stage 3 forge links: https://forge.3gpp.org/rep/sa5/MnS
  Management and Orchestration APIs:
    OpenAPI solution is captured in https://forge.3gpp.org/rep/all/5G_APIs (3GPP unified stage3 repository) and https://forge.3gpp.org/rep/sa5/MnS/-/tree/Rel-19/OpenAPI (SA5 stage3 repository)
    YANG solution is captured in https://forge.3gpp.org/rep/sa5/MnS/-/tree/Rel-19/yang-models (SA5 stage3 repository)
    Balazs Lengyel (Ericsson) as YANG Code moderator
    Sean Sun (Nokia) and Ruiyue Xu (Huawei) as YAML Code moderator
  Charging APIs:
    OpenAPI solution to be captured in https://forge.3gpp.org/rep/all/5G_APIs (3GPP unified stage3 repository) and https://forge.3gpp.org/rep/sa5/CH/-/tree/Rel-19/OpenAPI (SA5 stage3 repository)
    ASN.1 solution to be captured in https://forge.3gpp.org/rep/sa5/CH/-/tree/Rel-19/ (SA5 stage3 repository)
    Chen Shan (Huawei) as Charging YAML Code moderator
    Robert Törnkvist (Ericsson) as Charging ASN.1 Code moderator
  Stage 3 forge is supported by MCC and Miguel Angel Reina Ortega (ETSI) as code master.

## Slide 70: TU planning
Latest TU planning is captured in https://www.3gpp.org/ftp/Email_Discussions/SA5/SA5-level%20discussions/SA5%23157

## Slide 71: SA5 calendar with OAM TU (one track)
Time | Monday | Tuesday | Wednesday | Thursday | Friday (Closing plenary)
Q0 (If needed) |  | Breakout (opt.) | Breakout (opt.) | Breakout (opt.) | Closing plenary Start at 8:30am (may change depends on the host restriction)
Q1 (9:00 - 10:30) | Plenary Session#1 (1TU) [Single Stream] | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Closing plenary
10:30 - 11:00 | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break
Q2 (11:00 - 12:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Closing plenary
12:30 - 14:00 | Lunch | Lunch | Lunch | Lunch | Lunch
Q3 (14:00 - 15:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Closing plenary
15:30 - 16:00 | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break
Q4 (16:00 - 17:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Revision session | Closing plenary
17:30 - 17:40 | Break | Break | Break | Break | Break
Q5 (17:40 – 19:10) | Stream#1 (1TU) | Stream#1 (0.5 TU) Stop around 18:45 Social evening | Stream#1 (1TU) | Revision session | 
Assumption: Every day = 5 sessions (TUs), total TU in 1 ordinary meeting (exclude closing plenary TUs) = 18.5 TUs

## Slide 72: Rel-19 TU Budget for SA5 OAM
Assumptions for SA5 OAM :
  6 ordinary meeting per year.
  Rel-19 spans 21 months for SA5 (with early start of studies) = 10 meetings
  1 Session = 1.5 hour time window
  Max 5 sessions per meeting day
  1 Stream = 1 TU (Time Unit)
  1 TU is time (i.e., 1.5 hours) spent to discuss/handle technical contributions.
  Revisions/Drafting/offline conference call are not counted for the TU estimates.
  OAM revision sessions normally planned to be in Thursday Q4 and Q5 (initial assump.)
  1 parallel (OAM) stream per session => 18.5 TUs per meeting (incl. 2 TUs as buffer) = 185
  Assume Maintenance + Buffer = 33% => ~ 61 TU
  Resulting total TUs avail. f. SI/WI: 10 meetings x 18.5 sessions = 185 TU minus 61 => 124 TU
  With 20 SI/WI => Average 6 TU per SI/WI (0.6/meeting).
No update since SA#104

## Slide 73: SA5 Rel-19 OAM TU planning (Jan.2024~Sep.2025)
 | Maintenance+R18 | R19 | R20 preparation | Buffer (revision session)
Jan.2024~Mar.2024 SA5#153 (1 meeting) (Last meeting for Rel-18) | 1.5 TU (CR)+13 TU (Rel-18)=14.5 TU | 2 TU | NA | 2 TU
Apr. 2024~Dec.2024: SA5#154~#158 (5 meetings) | 2.5 TU*5 meetings = 12.5 TU (CRs) | 14 TU*5 meetings= 70 TU | NA | 2 TU*5=10 TU
Jan.2025~Sep.2025: SA5#159~#162 (4 meetings) | 1.5 TU*4 meetings= 6 TU (CRs) | 13 TU*4 meetings= 52 TU | 2 TU*4 meetings = 8 TU | 2 TU*4=8 TU
Total=185 TU | 33 TU | 124 TU | 8 TU | 20 TU
Assumptions:
Every meeting day = 5 quarters (= 5 TUs)
Total TUs per meeting = 18.5 TUs
  Buffer = 2 TUs
  OAM = 16.5 TUs
    Maintenance CRs + remaining Rel-18 work (TU allocation will decrease over time )
    Rel-20 preparation work (TU allocation will be zero at the beginning and will increase over time )
    All remaining time is available for Rel-19 SIDs / WIDs
Total TUs allocated to Rel-19 SIDs / WIDs = 120 TUs, implying:
  12 TUs allocated to Rel-19 SIDs / WIDs per meeting (= 120 TUs / 10 meetings)
  6 TUs allocated to each Rel-19 SID / WID in average (= 120 TUs / 20 Rel-19 SIDs/WIDs)
  0.6 TU allocated per Rel-19 SID / WID per meeting in average (= 12 TUs / 20 Rel-19 SIDs/WIDs)
No update since SA#104

## Slide 74: SA5 calendar with CH TU (one track)
Time | Monday | Tuesday | Wednesday | Thursday | Friday (Closing plenary)
Q0 (If needed) |  | Breakout (opt.) | Breakout (opt.) |  | Closing plenary Start at 8:30am (may change depends on the host restriction)
Q1 (9:00 - 10:30) | Plenary Session#1 (1TU) [Single Stream] | Stream#1 (1TU) | Stream#1 (1TU) | Revision session | Closing plenary
10:30 - 11:00 | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break
Q2 (11:00 - 12:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Revision session | Closing plenary
12:30 - 14:00 | Lunch | Lunch | Lunch | Lunch | Lunch
Q3 (14:00 - 15:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | CH Closing | Closing plenary
15:30 - 16:00 | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break
Q4 (16:00 - 17:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | CH Closing | Closing plenary
17:30 - 17:40 | Break | Break | Break | Break | Break
Q5 (17:40 – 19:10) | Stream#1 (1TU) | Stream#1 (0.5 TU) Stop around 18:45 Social evening | Stream#1 (1TU) | CH Closing(Opt.) | 
Assumption: Every day = 5 sessions (TUs), total TU in 1 ordinary meeting (exclude closing plenary TUs) = 15.5 TUs

## Slide 75: TU Budget for SA5 CH
Assumptions for SA5 CH :
  6 ordinary meeting per year.
  Rel-19 spans 18 months for SA5 (with early start of studies) = 8 meetings
  1 Session = 1.5 hour time window
  Max 5 sessions per meeting day
  1 Stream = 1 TU (Time Unit)
  1 TU is time (i.e., 1.5 hours) spent to discuss/handle technical contributions.
  Revisions/Drafting/offline conference call are not counted for the TU estimates.
  CH revision sessions normally planned to be in Thursday Q1 and Q2 (initial assump.),CH closing plenary planned to be in Thursday Q3 and Q4.
  1 (CH) stream per session => 15.5 TUs per meeting (incl. 2 TUs as buffer) = 124
  Assume Maintenance + Buffer = 33% as in SA2 => ~ 41 TU
  Resulting total TUs avail. f. SI/WI: 9 meetings x 15.5 sessions = 124 TU minus 41 => 83 TU
  => Recommended MAX no. of SI/WI = 14
  With 14 SI/WI => Average 6 TU per SI/WI (0.75/meeting).

## Slide 76: SA5 Rel-19 CH TU planning (May.2024~Sep.2025)
 | Maintenance+R18 | R19 | R20 preparation | Buffer (revision session)
May. 2024: SA5#155 (1 meeting) | 2.5 TU*1eetings = 2.5 TU (CRs) | 6 TU*1 meetings= 6 TU 5 TU: Rel-19 topic discussion | NA | 2 TU*4=8 TU
July. 2024~Dec.2024: SA5#156~#158 (3 meetings) | 2.5 TU*3 meetings = 7.5 TU (CRs) | 11 TU*3 meetings= 33 TU | NA | 2 TU*4=8 TU
Jan.2025~Sep.2025: SA5#159~#162 (4 meetings) | 1.5 TU*4 meetings= 6 TU (CRs) | 11 TU*4 meetings= 44 TU | 1 TU*4 meetings = 4 TU | 2 TU*4=8 TU
Total= 124 TU | 16 TU | 83 TU | 4 TU | 16 TU
Assumptions:
Every meeting day = 5 quarters (= 5 TUs)
Total TUs per meeting = 15.5 TUs
  Buffer = 2 TUs
  CH = 13.5 TUs
    Maintenance CRs + remaining Rel-18 work (TU allocation will decrease over time )
    Rel-20 preparation work (TU allocation will be zero at the beginning and will increase over time )
    All remaining time is available for Rel-19 SIDs / WIDs
Total TUs allocated to Rel-19 SIDs / WIDs = 83 TUs