## Slide 1: SA5 Status Report to SA#107
Zou Lan, SA5 Chair, Huawei
Thomas Tovinger, SA5 Vice Chair, Ericsson
Anatoly Andrianov, SA5 Vice Chair, Nokia
Gerald Görmer, SA5 Charging SWG Chair, MATRIXX Software
Antoine Mouquet, MCC, ETSI

## Slide 2: SA5 leadership
SA5
Zou Lan (Huawei) Chair since 08/2023
Thomas Tovinger (Ericsson) Vice Chair since 08/2023 Anatoly Andrianov (Nokia) Vice Chair since 08/2023
Antoine Mouquet MCC since 11/2023
  Charging Sub-Working Group (SWG)
Gerald Görmer (MATRIXX Software) SWG Chair since 08/2021 Chen Shan (Huawei) SWG Vice Chair since 05/2016

## Slide 3: Contents
General aspects of SA5
SA5 overall progress since SA#106
Management Feature relations with other WGs
Management and Orchestration
Charging

## Slide 4: SA5 general information since SA#106
  Statistics SA5#159, 17 – 21 February, 2025 Sophia Antipolis , France
    70 delegates ‘attended’ (checked-in) 31 registered for ‘On-Line’ participation
    1052 documents (including revisions) including:
      581 CRs submitted (including revisions)，Total CRs agreed: 246
      22 Incoming LSs, 2 postponed
      15 Outgoing LSs Approved
    SA5 CH SWG statistics:
      participation to this meeting
        14 delegates participated to Charging session
        4 delegates from remote
      documents to this meeting
        102 submitted contributions
        78 agreed contributions including
          4 contributions from the CH plenary
          8 Rel-19 WIDs (1 revised, 7 new agreed)
          5 CRs for Rel-19 WIDs, 45 pCRs for Rel-19 SIDs, 4 TRs for Rel-19 SIDs, 12 CRs for Maintenance
One f2f meeting in 1Q2025

## Slide 5: SA5 meeting statistics (2024/2025)
Chart: Number of delegates in SA5
| SA5#153 | SA5#154 | SA5#155 | SA5#156 | SA5#157 | SA5#158 | SA5#159
F2F delegates | 76 | 170 | 140 | 188 | 129 | 172 | 114
Online delegates | 28 | 21 | 20 | 29 | 53 | 28 | 31
Chart: LS exchange
| SA5#153 | SA5#154 | SA5#155 | SA5#156 | SA5#157 | SA5#158 | SA5#159
incoming LS | 45 | 32 | 14 | 27 | 19 | 17 | 22
Outgoing LS | 21 | 21 | 7 | 14 | 7 | 11 | 15
Chart: Total number and agreed tdoc numbers
| SA5#153 | SA5#154 | SA5#155 | SA5#156 | SA5#157 | SA5#158 | SA5#159
Total number of tdocs | 1092 | 1122 | 1137 | 1515 | 1078 | 1062 | 1052
Number of agreed tdocs | 447 | 379 | 460 | 698 | 447 | 408 | 386
Chart: Allocation of agreed tdocs
| SA5#153 | SA5#154 | SA5#155 | SA5#156 | SA5#157 | SA5#158 | SA5#159
R15 CR | 1 | 4 | 1 | 9 | 3 | 1 | 0
R16 CR | 13 | 12 | 15 | 32 | 12 | 7 | 6
R17 CR | 37 | 37 | 43 | 76 | 29 | 24 | 13
R18 CR | 215 | 133 | 163 | 154 | 62 | 70 | 55
R19 CR | 22 | 32 | 108 | 100 | 118 | 173
others | 181 | 164 | 205 | 311 | 241 | 188 | 139

## Slide 6: SA5 meeting statistics (Rel-19 OAM topics)
Observation: AIML/CMO/NDT/EE/IDM/CCL/MDA are top 7 contribution topics in Rel-19
Chart: Rel-19 OAM submited tdocs
| AIML | MADCOL | SEPM | PM | AdNRM | TMQ | NTNM | IABM | RedcapM | NWDAFM | NSM | MDA | EE | Mexpo | MonstraM | IDM | CCL | NDT | CMO | MSEC | SBMA | PTM
#153 | 7 | 3 | 12 | 6 | 13 | 5
#154 | 29 | 9 | 5 | 18 | 8 | 6 | 13 | 7 | 6 | 8 | 5 | 14 | 16 | 13 | 19 | 19 | 14 | 25 | 6 | 5
#155 | 28 | 5 | 6 | 13 | 12 | 3 | 10 | 2 | 9 | 7 | 3 | 23 | 17 | 15 | 19 | 15 | 19 | 26 | 13 | 8
#156 | 50 | 2 | 4 | 27 | 15 | 6 | 16 | 5 | 14 | 9 | 8 | 21 | 22 | 15 | 25 | 24 | 29 | 25 | 4 | 23 | 11
#157 | 54 | 8 | 1 | 11 | 11 | 6 | 10 | 4 | 9 | 2 | 8 | 9 | 23 | 12 | 13 | 25 | 21 | 35 | 12 | 13
#158 | 43 | 4 | 0 | 9 | 9 | 7 | 13 | 0 | 4 | 4 | 6 | 13 | 24 | 14 | 15 | 14 | 7 | 14 | 28 | 3 | 7 | 8
#159 | 63 | 6 | 2 | 10 | 11 | 5 | 7 | 1 | 10 | 2 | 5 | 22 | 19 | 9 | 25 | 23 | 29 | 16 | 23 | 9
total | 267 | 34 | 18 | 88 | 66 | 33 | 69 | 19 | 52 | 32 | 35 | 102 | 128 | 81 | 15 | 127 | 119 | 139 | 160 | 7 | 84 | 54
Topics | Submitted tdocs
AIML | 267
MADCOL | 34
SEPM | 18
PM | 88
AdNRM | 66
TMQ | 33
NTNM | 69
IABM | 19
RedcapM | 52
NWDAFM | 32
NSM | 35
MDA | 102
EE | 128
Mexpo | 81
MonstraM | 15
IDM | 127
CCL | 119
NDT | 139
CMO | 160
MSEC | 7
SBMA | 84
PTM | 54

## Slide 7: Action from SA#106
Rel-19 Ambient IoT : SA5 is expected to bring the related work item (including charging) for approval in TSG#107 (ref: SP-241980 Way forward proposal on Architecture support of Ambient power-enabled Internet of Things)
  SA5 has agreed updated of Rel-19 AdNRM_Ph3 WID (SP-250123) to include OAM support to Ambient IoT, and a new Charging AmbientIoT_CH WID (SP-250121) was agreed and submit to SA#107 for approval.
For 5G APIs, if there are URI query parameters defined as array or JSON object, the format of the query parameters shall be documented in the corresponding yaml file (see clause 5.3.13 of TS 29.501).(ref: SP-241892 Status report of TSG CT#106 Slide 21)
  SA5 has checked related specifications and agreed the following CRs to align with the URI query parameters.
    S5‑250155 Rel19 CR TS28.532 OpenAPI correction related to format of URI query parameters
    S5‑250156 Rel19 CR TS28.550 OpenAPI correction related to format of URI query parameters
Trial on a tool developed by MCC to identify OpenAPIs which are changed due to a change of a definition which is imported from a different TS/OpenAPI (ref: SP-241892 Status report of TSG CT#106 Slide 22)
  The tool has been informed to SA5, detail procedure on how to use the tool in SA5 working procedure will be discussed in future meeting.

## Slide 8
New Rel-19 Study / Work Items
TDoc | Title | Type | UID | (Suggested) Acronym
SP-250117 | New WID on charging aspects of satellite access Phase 3 | WID new | 1070014 | 5GSAT_Ph3_CH
SP-250118 | New WID on Charging aspects of CAPIF | WID new | 1070015 | CAPIF_Ph2_CH
SP-250119 | New WID on Charging aspects of next generation real time communication services phase 2 | WID new | 1070016 | NG_RTC_Ph2_CH
SP-250120 | New WID on Charging for Uncrewed Aerial Systems Phase 2 | WID new | 1070017 | UAS_Ph2_CH
SP-250125 | New WID on Charging Aspects of 5GC LoCation Services | WID new | 1070019 | 5G_eLCS_Ph3_CH
SP-250121 | New WID on Charging for Ambient power-enabled Internet of Things | WID new | 1070018 | AmbientIoT_CH
SP-250126 | New WID on charging enhancement for MOCN network sharing | WID new | 1070020 | CHNetShare
7 new Rel-19 work items sent for SA approval, including 7 CH work items (6 CH support to network features and 1 CH prime feature)

## Slide 9
Revised Rel-19 Study / Work Items
Tdoc | Type | Release | Title | Comment
SP-250115 | WID revised | Rel-19 | Revised WID on Subscriber and Equipment Trace and QoE Collection | Including additional Trace/MDT/QoE enhancement in the scope
SP-250123 | WID revised | Rel-19 | Revised WID on 5G Advanced NRM features phase 3 | Include NRM support for Ambient IoT feature, LTM mobility feature, NR-WAB
SP-250116 | WID revised | Rel-19 | Revised WID on Data management phase 2 | Update rapporteur information
SP-250124 | WID revised | Rel-19 | Revised WID on charging aspects for energy efficiency of network slice | Update title, expected time scale and supporting company
SP-250122 | WID revised | Rel-19 | Revised WID on CHF Segmentation | Update expected time scale and supporting company
5 revised study/work items sent for SA approval including 3 OAM and 2 CH

## Slide 10: Overview of Rel-19 SA5 OAM topics
 |  | Abbr. | Acronym | Title | UID | rapp | Tdoc | TS/TR | Type
Intelligence and Automation | 1 | AIML | FS_AIML_MGT_Ph2 | Study on AI and ML management phase 2 | 1020007 | Intel, NEC | SP-231780 | TR 28.908 | SID
 |  |  | -> AIML_MGT_Ph2 | AI/ML management phase 2 | 1060011 | NEC, Intel | SP-241944 | TS 28.105/552/554/541 | WID
 | 2 | MDA | FS_eMDAS_Ph3 | Study on Management Data Analytics (MDA) – Phase 3 | 1020019 | Huawei | SP-231726 | TR 28.866 | SID
 |  |  | -> eMDAS_Ph3 | Management Data Analytics phase 3 | 1060014 | Huawei | SP-241947 | TS 28.104 | WID
 | 3 | IDM | FS_IDMS_MN_Ph3 | Study on intent driven management services for mobile networks phase 3 | 1020008 | Huawei, Ericsson | SP-231737 | TR 28.914 | SID
 |  |  | -> IDMS_MN_Ph3 | Intent driven management services for mobile network phase 3 | 1060013 | Huawei, Ericsson | SP-241946 | TS 28.312 | WID
 | 4 | CCL | FS_CCLM | Study on Closed Control loop management | 1020009 | Samsung, Nokia | SP-231735 | TR 28.867 | SID
 |  |  | -> CCLM | Closed Control Loop Management | 1060010 | Samsung, Nokia | SP-241943 | TS 28.567/535/536/622/32.161 | WID
 | 5 | NDT | FS_NDT | Study on Management aspect of Network Digital Twin | 1020018 | CMCC | SP-231727 | TR 28.915 | SID
 |  |  | -> NDT | Management aspects of Network Digital Twins | 1060005 | CMCC | SP-241938 | TS 28.561 | WID
Management Architecture and Mechanisms | 6 | CMO | FS_Cloud_OAM | Study on cloud aspects of management and orchestration | 1020010 | CMCC | SP-241566 | TR 28.869 | SID
 | 7 | MSEC | FS_SECM | Study on Enablers for Security Monitoring | 1020016 | Nokia | SP-231736 | TR 28.870 | SID
 | 8 | SBMA | FS_SBMA_Ph3 | Study on SBMA enhancement phase 3 | 1020011 | Huawei, Ericsson | SP-231725 | TR 28.871 | SID
 |  |  | ->SBMA_Ph3 | Service Based Management Architecture enhancement phase 3 | 1060006 | Huawei, Ericsson | SP-241939 | TS 28.533/… | WID
 | 9 | PTM | FS_PlanM | Study on Plan management | 1020033 | Nokia, Ericsson | SP-231721 | TR 28.872 | SID
 |  |  | -> PlanM | Management of planned configurations | 1050032 | Nokia | SP-241379 | TS 28.572 | WID
 | 10 | MADCOL | MADCOL_Ph2 | Data Management phase 2 | 1020025 | Nokia | SP-231746 | TS 28.622 | WID
 | 11 | SEPM | FS_Data_SREP | Study on data management, regarding subscriptions and reporting | 1020012 | Ericsson | SP-231732 | TR 28.873 | SID
 |  |  | -> Data_SREP | Data management, regarding subscriptions and reporting | 1050033 | Ericsson | SP-241380 | 28.537/28.550/28.532/32.421/32.422/32.423/28.404/28.405/28.622/28.623 | WID
 | 12 | PM | PM_KPI_5G_Ph4 | 5G performance measurements and KPIs phase 4 | 1020026 | China Telecom, ZTE | SP-231747 | TS 28.552/554 | WID
 | 13 | AdNRM | AdNRM_Ph3 | 5G Advanced NRM features phase 3 | 1020027 | Nokia, Huawei | SP-231745 | TS 28.541/622 | WID
 | 14 | TMQ | TraceQoE_OAM | Subscriber and Equipment Trace and QoE collection management | 1020028 | Ericsson | SP-231748 | TS 32.422/405 | WID
 | 15 | NTNM | FS_ NTN_OAM_Ph2 | Study on Management Aspects of NTN Phase 2 | 1020013 | China Unicom, CATT | SP-231733 | TR 28.874 | SID
 |  |  | ->NTN_OAM_Ph2 | Management Aspects of NTN Phase 2 | 1060016 | China Unicom, CATT | SP-241949 | TS 28.541/552/554/658/662/540/530 | WID
 | 16 | IABM | FS_NR_mobile_IAB_OAM | Study on Management of IAB Nodes | 1020014 | Ericsson | SP-231729 | TR 28.875 | SID
 |  |  | -> NR_mobile_IAB_OAM | Management of IAB nodes | 1060015 | Ericsson | SP-241948 | TS 28.541/540/531/314/315 | WID
 | 17 | RedcapM | FS_NR_RedCap_OAM | Study on management aspects of RedCap feature | 1020017 | China Unicom, Asiainfo | SP-231734 | TR 28.876 | SID
 |  |  | ->NR_RedCap_OAM | Management Aspects of RedCap features | 1060008 | China Unicom, Asiainfo | SP-241941 | TS 28.540/541/552/554 | WID
 | 18 | NWDAFM | FS_NWDAF_OAM_Ph2 | Study on Enhancement of Management Aspects related to NWDAF Phase 2 | 1020020 | China Telecom | SP-231724 | TR 28.877 | SID
 |  |  | -> NWDAF_OAM_Ph2 | Enhancement of Management Aspects related to NWDAF Phase 2 | 1050031 | China Telecom | SP-241378 | 28.552/28.541 | WID
 | 19 | NSM | FS_NetShare_OAM_Ph3 | Study on Management of Network Sharing Phase 3 | 1020015 | China Unicom | SP-231731 | TR 28.878 | SID
 |  |  | ->NetShare_OAM_Ph3 | Management of Network Sharing Phase 3 | 1060017 | China Unicom, China Telecom | SP-241950 | TS 28.552/32.130/28.541 | WID
Support of New Services | 20 | EE | FS_Energy_OAM_Ph3 | Study on energy efficiency and energy saving aspects of 5G networks and services | 1020021 | Huawei, Samsung | SP-231723 | TR 28.880 | SID
 |  |  | ->Energy_OAM_Ph3 | Energy efficiency and energy saving aspects of 5G networks and services | 1060007 | Huawei, Samsung | SP-241940 | TS 28.310/622/623/541/554/104 | WID
 | 21 | Mexpo | FS_MExpo | Study on Enhanced OAM for management exposure to external consumers | 1020022 | Nokia | SP-231728 | TR 28.879 | SID
 |  |  | ->MExpo | Enhanced OAM for management service exposure to external consumers through CAPIF | 1060009 | Nokia | SP-241942 | TS 28.579 | WID
 | 22 | MonStra | Monstra-OAM | Management for MonStra | 1060012 | Vodafone, Ericsson | SP-241945 | TS 28.560 | WID
22 topics including: 14 OAM prime features and 8 OAM support to network features (in red background). 16 topics completed the study, 1 normative WI completed, 18 ongoing normative WIs.

## Slide 11
Overview of Rel-19 CH topics
 | Abbr. | Acronym | Title | UID | Rapp | Tdoc | TS/TR | Type
1 | CHSEG | CHFSeg | WID on CHF Segmentation | 1040012 | Verizon | SP-241001 | TS 32.290/291 | WID
2 | SATCH | FS_5GSAT_Ph3_CH | SID on Charging aspects of satellite access Phase 3 | 1040014 | CATT | SP-240980 | TR 28.846 | SID
3 | CAPCH | FS_CAPIF_Ph2_CH | SID on Charging Aspects of CAPIF | 1040015 | Nokia | SP-240981 | TR 28.849 | SID
4 | RTCCH | FS_NG_RTC_Ph2_CH | SID on Charging aspects of next generation real time communication services phase 2 | 1040016 | CMCC | SP-240982 | TR 28.851 | SID
5 | UASCH | FS_UAS_Ph2_CH | SID on Charging aspects of Uncrewed Aerial Vehicle | 1040017 | CMCC | SP-240983 | TR 28.853 | SID
6 | RAGCH | Ranging_SL_CH | WID on Charging Aspects of Ranging and Sidelink Positioning | 1040013 | China Telecom | SP-241002 | TS 32.240/290/ 271/291/298 | WID
7 | EESCH | EnergySys_CH | WID on Charging Aspects for Energy Efficiency of network slice | 1040018 | Huawei | SP-241003 | TS 28.201/202 TS 32.240/291/298 | WID
8 | NSCH | NetShare_CH | WID on Charging enhancement for indirect network sharing | 1040019 | Ericsson | SP-241004 | TS 32.240/255/256 | WID
9 | PROCH | 5G_ProSe_Ph3_CH | WID on Charging Aspects for 5G ProSe Phase 3 | 1050030 | China Telecom | SP-241377 | TS 32.277/291/298 | WID
10 | SATCH | 5GSAT_Ph3_CH | WID on Charging aspects of satellite access Phase 3 (for SA approval) | 1070014 |  | SP-250117 | TS32.240/251/255/257/260/291/298 | New WID
11 | CAPCH | CAPIF_Ph2_CH | WID on Charging aspects of CAPIF (for SA approval) | 1070015 |  | SP-250118 | TS32.240/254/291/298 | New WID
12 | RTCCH | NG_RTC_Ph2_CH | WID on Charging aspects of next generation real time communication services phase 2 (for SA approval) | 1070016 |  | SP-250119 | TS32.254/255/260/291/298 | New WID
13 | UASCH | UAS_Ph2_CH | WID on Charging for Uncrewed Aerial Systems Phase 2 (for SA approval) | 1070017 |  | SP-250120 | TS32.240/255/256/291/298 | New WID
14 | LCSCH | 5G_eLCS_Ph3_CH | WID on Charging Aspects of 5GC LoCation Services (for SA approval) | 1070019 |  | SP-250125 | TS32.271/290/291/298 | New WID
15 | AIOCH | AmbientIoT_CH | WID on Charging for Ambient power-enabled Internet of Things (for SA approval) | 1070018 |  | SP-250121 | TS32.240/254/291/298 | New WID
16 | CHNSH | CHNetShare | WID on charging enhancement for MOCN network sharing (for SA approval) | 1070020 |  | SP-250126 | TS32.130/240/254/291/298 | New WID
16 CH topics including: 2 CH prime feature and 14 CH support to network features (in red background, 2 normative WIs in progress, 3 normative WIs and 4 SIs completed – marked in green color). 7 new normative WIs wait for SA approval.

## Slide 12: Update of SA5 Rel-19 ongoing WI/SI progress
UID | Name | Acronym | Target date | Old % | UID | New % | Change or comment
1040018 | Charging Aspects for Energy Efficiency of network slice | EnergySys_CH | 06/06/2025 | 45% | SP-241003 | 100% | 
1060007 | Energy efficiency and energy saving aspects of 5G networks and services | Energy_OAM_Ph3 | 09/09/2025 | 0% | SP-241940 | 20% | 
1060011 | AI/ML Management Phase 2 | AIML_MGT_Ph2 | 09/09/2025 | 0% | SP-241944 | 15% | 
1060008 | Management Aspects of RedCap features | NR_RedCap_OAM | 09/09/2025 | 0% | SP-241941 | 50% | 
1060016 | Management Aspects of NTN Phase 2 | NTN_OAM_Ph2 | 06/06/2025 | 0% | SP-241949 | 25% | 
1040014 | Study on charging aspects of satellite access Phase 3 | FS_5GSAT_Ph3_CH | 03/03/2025 | 75% | SP-240980 | 100% | 
1060017 | Management of Network Sharing Phase 3 ?? | NetShare_OAM_Ph3 | 06/06/2025 | 0% | SP-241950 | 50% | 
1040015 | Study on Charging Aspects of CAPIF | FS_CAPIF_Ph2_CH | 12/12/2024 | 75% | SP-240981 | 100% | 
1060009 | Enhanced OAM for management service exposure to external consumers through CAPIF | MExpo | 09/09/2025 | 0% | SP-241942 | 15% | 
1040012 | CHF Segmentation | CHFSeg | 03/03/2025 | 55% | SP-241001 | 60% | 
1050033 | Data management regarding subscriptions and reporting | Data_SREP | 09/09/2025 | 0% | SP-241380 | 0% | 
1060012 | Management for MonStra | Monstra-OAM | 12/12/2024 | 80% | SP-241945 | 80% | 
1040016 | Study on Charging aspects of next generation real time communication services phase 2 | FS_NG_RTC_Ph2_CH | 03/03/2025 | 75% | SP-240982 | 100% | 
1040017 | Study on Charging aspects of Uncrewed Aerial Systems | FS_UAS_CH | 03/03/2025 | 75% | SP-240983 | 100% | 
1050030 | Charging for 5G ProSe Ph3 | 5G_ProSe_Ph3_CH | 09/09/2025 | 75% | SP-241377 | 100% | 
1060006 | Service Based Management Architecture enhancement phase 3 | SBMA_Ph3 | 09/09/2025 | 0% | SP-241939 | 40% | 
1060014 | Management Data Analytics phase 3 | eMDAS_Ph3 | 09/09/2025 | 0% | SP-241947 | 30% | 
1060013 | Intent driven management services for mobile network phase 3 | IDMS_MN_Ph3 | 06/06/2025 | 0% | SP-241946 | 65% | 
1060005 | Management aspects of Network Digital Twins | NDT | 09/09/2025 | 0% | SP-241938 | 10% | 
1020010 | Study on Cloud Aspects of Management and Orchestration | FS_Cloud_OAM | 12/12/2024 | 90% | SP-241566 | 85% | 
1050032 | Management of planned configurations | PlanM | 09/09/2025 | 60% | SP-241379 | 75% | 
1060010 | Closed Control Loop Management | CCLM | 09/09/2025 | 0% | SP-241943 | 10% | 
1020025 | Data management phase 2 | MADCOL_Ph2 | 06/06/2025 | 88% | SP-240877 | 88% | Rapporteur updated to: Sreekumar Pothera Kalloor (Nokia), sreekumar.pk@nokia.com
1020026 | 5G performance measurements and KPIs phase 4 | PM_KPI_5G_Ph4 | 06/06/2025 | 65% | SP-241155 | 75% | 
1020027 | 5G Advanced NRM features phase 3 | AdNRM_Ph3 | 06/06/2025 | 60% | SP-241565 | 75% | 
1020028 | Subscriber and Equipment Trace and QoE collection management | TraceQoE_OAM | 06/06/2025 | 75% | SP-231748 | 80% | 
1060015 | Management of IAB nodes | NR_MOBILE_IAB_OAM | 09/09/2025 | 0% | SP-241948 | 0% | 
1050031 | Enhancement of Management Aspects Related of NWDAF Phase 2 | NWDAF_OAM_Ph2 | 06/06/2025 | 60% | SP-241378 | 65% | 

## Slide 13
Acronym | OAM | Not covered by SA5 OAM yet | CH | Not covered by SA5 CH yet
5GSAT_Ph3_ARCH | NTN_OAM_Ph2 |  | 5GSAT_Ph3_CH | 
NG_RTC_Ph2 | NA | NA | NG_RTC_Ph2_CH | 
XRMPh2 | PM_KPI_5G_Ph4(CMCC) | OAM (NRM)?? |  | CH?? (CH indicated in SA2 WID)
MPS4msg | NA | NA |  | CH?? (CH indicated in SA2 WID)
VMR_Ph2 | AdNRM_Ph3(Samsung) | (PM??) |  | CH?? (CH indicated in SA2 WID)
5G_ProSe_Ph3 | AdNRM_Ph3 (CATT) | (PM??) | 5G_ProSe_Ph3_CH | 
UIA_ARC | NA | NA |  | CH?? (CH indicated in SA2 WID)
eEDGE_5GC_Ph3 |  | OAM (NRM+PM)?? |  | CH?? (CH indicated in SA2 WID)
UAS_Ph3 | NA | NA | UAS_Ph2_CH (to be checked) | UAS_Ph2_CH only targets UAS_Ph2
UPEAS_Ph2 |  | OAM (NRM+PM)?? |  | CH?? (CH indicated in SA2 WID)
5G_Femto | NA | NA | NA | NA
MASSS |  | OAM (NRM)?? PM (not related) | NA | NA
AIML_CN | AIML_MGT_Ph2 NWDAF_OAM_Ph2 |  |  | Potential Rel-20 topic
EnergySys | Energy_OAM_Ph3 MExpo |  | EnergySys_CH | 
TEI19_NetShare | NetShare_OAM_Ph3 |  | NetShare_CH | 
AmbientIoT | AdNRM_Ph3(Huawei) |  | AmbientIoT_CH | 
Summary of SA5 Rel-19 management support to SA2 features
OAM Summary
The following features, there are no extra management standardization support identified so far:
  NG_RTC_Ph2
  MPS4msg
  UIA_ARC
  UAS_Ph3
  5G_Femto
The following features, need to check whether OAM support are needed in Rel-19.
  XRMPh2
  VMR_Ph2
  5G_ProSe_Ph3
  eEDGE_5GC_Ph3
  UPEAS_Ph2
  MASSS
CH Summary
The following features, there are no extra CH management standardization support identified so far:
  5G_Femto
  MASSS
The following features, need to check whether Charging support are needed in Rel-19.
  XRMPh2
  MPS4msg
  VMR_Ph2
  UIA_ARC
  eEDGE_5GC_Ph3
  UAS_Ph3
  UPEAS_Ph2
  AIML_CN
  FS_AmbientIoT
  FS_EnergySys
The content of this slides is to be updated based on working progress

## Slide 14
Acronym | OAM | Not covered by SA5 yet
NR_MIMO_Ph5-Core | NA | NA
FS_NR_7_24GHz_CHmod | NA | NA
NR_MIMO_Ph5-Core | NA | NA
Netw_Energy_NR_enh-Core | NA | NA
FS_Sensing_NR |  | OAM (TBD)
NR_AIML_air-Core | AIML_MGT_Ph2 | other OAM (TBD)
NR_duplex_evo-Core | NA | NA
NR_LPWUS-Core |  | OAM (NRM+PM)？？
IoT_NTN_TDD-Core |  | OAM (NRM+PM)？？
NR_MC_enh2-Core |  | OAM (NRM+PM)？？
LTE_terr_bcast_Ph2-Core |  | OAM (NRM+PM)？？
Ambient_IoT_Solutions-Core | AdNRM_Ph3(Huawei) | 
FS_NR_AIML_Mob | AIML_MGT_Ph2 | other OAM (TBD)
NR_Mob_Ph4-Core | PM_KPI_5G_Ph4 AdNRM_Ph3 | 
NR_NTN_Ph3-Core | NTN_OAM_Ph2 | 
IoT_NTN_Ph3-Core | NTN_OAM_Ph2 | 
NR_XR_Ph3-Core | NA | NA
LTE_TN_NR_NTN_mob-Core | NTN_OAM_Ph2 | 
NR_SL_relay_multihop-Core |  | OAM (NRM+PM)？？
LCS_BDS_B2b_LTE_NR-Core |  | OAM (NRM+PM)？？
LCS_NAVIC_L1_SPS_NR_LTE-Core |  | OAM (NRM+PM)？？
NR_ENDC_SON_MDT_Ph4-Core | PM_KPI_5G_Ph4 AdNRM_Ph3 TraceQoE_OAM | 
NR_WAB_5GFemto | AdNRM_Ph3 | 
NR_AIML_NGRAN_enh-Core | AIML_MGT_Ph2 Energy_OAM_Ph3 | 
Summary of SA5 Rel-19 management support to RAN1/2/3 features
RAN1
RAN2
RAN3
OAM Summary:
RAN1:
1. The following features, there are no extra management standardization support identified so far:
NR_MIMO_ph5-Core
FS_NR_7_24GHz_CHmod
NR_MIMO_Ph5
Netw_Energy_NR_enh-Core
NR_duplex_evo
2. The following features, need to check whether OAM support are needed in Reld-19.
FS_Sensing_NR
NR_LPWUS-Core
IoT_NTN_TDD-Core
NR_MC_enh2-Core
LTE_terr_bcast_Ph2-Core
RAN2:
1. The following features, there are no extra management standardization support identified so far:
NR_XR_Ph3-Core
CH Summary: There are no extra CH features related to RAN features.
The content of this slides is to be updated based on working progress

## Slide 15
SA5 Rel-19 topics relation to other WGs (OAM)
Abbreviation | Acronym | SA1 | SA2 | SA3 | SA4 | SA6 | RAN1 | RAN2 | RAN3 | CT3 | CT4 | Other related groups
AIML | AIML_MGT_Ph2 | TS 22.261 (AIML) | AIML_CN(R19) | X |  | X | NR_AIML_air-Core (R19) | FS_NR_AIML_Mob(R19) | NR_AIML_NGRAN_enh-Core(R19) |  |  | 3GPP SA (TR 22.850)
MDA | eMDAS_Ph3 |  |  |  |  |  |  |  | X (EE cost index) |  |  | 
IDM | IDMS_MN_Ph3 | TS 22.125 (UAV pre-flight) |  |  |  |  |  |  |  |  |  | GSMA/CAMARA/ETSI ZSM/TMF
CCL | CCLM |  |  |  |  |  |  |  |  |  |  | ETSI ZSM
NDT | NDT |  | X |  |  |  |  |  |  |  |  | ETSI ZSM
CMO | FS_Cloud_OAM |  |  |  |  |  |  |  |  |  |  | ETSI NFV
MSEC | FS_SECM |  |  | X |  |  |  |  |  |  |  | 
SBMA | SBMA_Ph3 |  |  |  |  |  |  |  |  |  |  | 
PTM | PlanM |  |  |  |  |  |  |  |  |  |  | 
MADCOL | MADCOL_Ph2 |  |  |  |  |  |  |  |  |  |  | 
SREP | Data_SREP |  |  |  |  |  |  |  |  |  |  | 
PM | PM_KPI_5G_Ph4 | TS 22.137 (Sensing KPI) (TBD) | XRMPh2 (R19) |  |  |  | FS_Sensing_NR (TBD) | NR_Mob_Ph4-Core (R19) | NR_ENDC_SON_MDT_Ph4-Core (R19) |  |  | 
AdNRM | AdNRM_Ph3 |  | VMR_Ph2 (R19) 5G_ProSe_Ph3 (R19) AmbientIoT (R19) |  |  | eEDGE_5GC_Ph3 (R19) | FS_Sensing_NR?? Ambient_IoT_Solutions-Core(R19) | NR_Mob_Ph4-Core(R19) | NR_ENDC_SON_MDT_Ph4-Core (R19) NR_WAB_5GFemto(R19) |  | SBIProtoc19 (R19) | GSMA (GST)
TMQ | TraceQoE_OAM |  | X |  | X |  |  | X | X |  | X | 
NTNM | NTN_OAM_Ph2 |  | 5GSAT_Ph3_ARCH (R19) |  |  |  |  | NR_NTN_Ph3-Core(R19) IoT_NTN_Ph3-Core(R19) | LTE_TN_NR_NTN_mob(R19) |  |  | 
IABM | NR_mobile_IAB_OAM |  |  |  |  |  |  |  | X |  |  | 
RedcapM | NR_RedCap_OAM |  | NR_REDCAP_Ph2 (R18) |  |  |  | NR_redcap_enh-Core (R18) |  |  |  |  | 
NWDAFM | NWDAF_OAM_Ph2 |  | TS 23.288, eNA_Ph 2 (R17) |  |  |  |  |  |  |  |  | 
NSM | NetShare_OAM_Ph3 | TS 22.261 | TEI19_NetShare(R19) |  |  |  |  |  |  |  | X | 
EE | Energy_OAM_Ph3 | TS 22.261 (EE as a service) | EnergySys (R19) |  |  |  |  |  | NR_AIML_NGRAN_enh-Core (R19) |  |  | NGMN/ETSI NFV/ETSI EE/ITU-T SG5
Mexpo | Mexpo | TS 22.261 (EE as a service) |  | TS 33.222 (CAPIF) |  | TS 23.222(CAPIF) |  |  |  | TS 29.222 (CAPIF) |  | GSMA OPG/CAMARA/TMF
MonStra | Monstra-OAM | TS 22.261-6.51 (MonStra) |  |  |  |  |  |  |  |  |  | 
The content of this slides is to be updated based on working progress

## Slide 16
SA5 Rel-19 topics relation to other WGs (CH)
Abbreviation | Acronym | SA1 | SA2 | SA6 | CT1 | CT3 | CT4 | Other related groups
SATCH | 5GSAT_Ph3_CH | 5GSAT_Ph3 (R19) (TS 22.261) | 5GSAT_Ph3_ARCH (TS 23.501; TS 23.502; TS 23.503; TS 23.682; TS 23.228; TS 23.401 ) | 5GSAT_Ph3_App (TS 23.558; TS 23.434; TS 23.289 ) |  |  |  | 
CAPCH | CAPIF_Ph2_CH |  |  | CAPIF(R15)?? eCAPIF(R16)?? FS_CAPIF_Ph3 |  |  |  | 
RTCCH | NG_RTC_Ph2_CH |  | NG_RTC_Ph2?? (TS 23.228; TS 23.502 ) FS_NG_RTC_Ph2 (TR 23.700-77) |  |  |  |  | 
UASCH | UAS_Ph2_CH | ID_UAS (R17) (TS 22.125) UAS_Ph3(R19)?? | ID_UAS (R17) (23.501; 23.502; 23.503; 23.401) UAS_Ph2 (R18) (23.256) UAS_Ph3 (R19) ?? (TS 23.256; TS 23.288; TS 23.503; TS 23.502; TS 23.401 ) | UASAPP_Ph3?? |  | UASAPP_Ph3?? ID_UAS（R17） UAS_Ph2（R18) (TS 29.502；TS 29.503；TS 29.504；TS 29.505；TS 29.510；TS 29.518；TS 29.571；TS 29.274；TS 29.256；TS 23.008） | ID_UAS（R17） UAS_Ph2（R18) (TS 29.502；TS 29.503；TS 29.504；TS 29.505；TS 29.510；TS 29.518；TS 29.571；TS 29.274；TS 29.256；TS 23.008） | 
CHSEG | CHFSeg |  |  |  |  |  |  | 
RAGCH | Ranging_SL_CH | Ranging (R18) (TS 22.261) | Ranging_SL(R18) (23.304; 23.287; 23.273; 23.502; 23.503 ; 23.586) |  | Ranging_SL (R18) (24.501; 24.554; 24.555; 24.571; 24.587; 24.588; 24.514) | Ranging_SL (R18) (29.513; 29.122; 29.522; 29.591; 29.525; 29.519) | Ranging_SL (R18) (24.080; 29.503; 29.504; 29.505; 29.510; 29.515; 29.518; 29.571; 29.572; 29.586) | 
EESCH | EnergySys_CH | EnergyServ (R19) (TS 22.261) | FS_EnergySys (R19) (TR 23.700-66) |  |  |  |  | 
NSCH | NetShare_CH | NetShare (R19) (TS 22.261) | TEI19_NetShare (R19) (TS 23.501; TS 23.502 ) |  | TEI19_NetShare (24.501) |  | TEI19_NetShare (29.502; 29.503; 29.509; 29.510; 29.531) | 
PROCH | 5G_ProSe_Ph3_CH |  | 5G_ProSe_Ph3 (R19) |  |  |  |  | 
The content of this slides is to be updated based on working progress

## Slide 17
Release 20 timeline– figure with SA5 (recommended by SA5 leaders)
Reference：S5-250787
2024
#103
Mar.
#111
Mar.
#107
Mar.
#104
Jun.
#108
Jun.
#112
Jun.
#105
Sep.
#109
Sep.
#102
Dec.
#106
Dec.
#110
Dec.
Now
TSGs
SA1 5GA SID definition
Workshop 6G TSGs
100%
SA1 5GA Studies + Norm 80%
100%
St. 2 (SA2, SA6, …) 5GA St.+Norm 80%
Stage 3 5GA St + Norm
Stage 3 6G SID def.
#113
Sep.
#114
Dec.
#115
Mar.
Jun
Workshop IMT-2030 use cases
RAN1
RAN Completion (RAN2/3/4core)
#116
SA1 6G Study(ies)
RAN4 C.def.
RAN4 Perf
RP Content def.
SA1 6G SID def.
RP IMT-2030 disc.
RP ITU Study
RP 6G Study(ies)
RAN1 6G Study(ies)
SA2 6G Study(ies)
Stage 3 6G Study(ies)
Rel-20 – FS_6G part
2025
2026
2027
SA2 & RAN WGs 6G SID def.
SA3/4/6 SID def. and compl. TBD
5GA ASN.1 & Open APIs
RAN2/3/4 6G Study(ies)
St.2 SID def. TBD
St.3 SID def. TBD
Release 20 timeline
or
TBD
Note: All starting dates are indicative
Workshop 5GA RAN
Workshop 5GA SA
3GPP SA5
Time plan
SA5 6G SID def.
SA5 6G Study(ies)
Rel-20 - 5GA part
SA5 (5GA OAM/CH Prime) management St.+Norm Stage1/2/3
OAM/CH Prime
SID def.
SA5 (OAM/CH Stage 2/Stage3 supporting) SA&RAN (SA5)
OAM/CH Supporting
SID def.(if needed)
5GA Rel-20:
OAM/CH prime feature:
All prime SIDs to be agreed no later than May.2025(SA5#161) and target for approval in Jun.2025 (SA#108).
It’s recommended to take max 6~9 months for study phase if normative work is planned for Rel-20.
Start of Rel-20 prime study: right after Jun.2025 (SA#108/SA5#161)
End of Rel-20 prime normative: Dec.2026 (SA#114/SA5#170)
OAM/CH supporting to network feature(SA5 is ready to support network features pending the availability of inputs from other WGs)
All supporting studies/normative WIDs to be agreed no later than May.2026 (SA5#167) and target for approval in Jun.2026 (SA#112).
Start of Rel-20 supporting study (if needed): right after Jun.2026 (SA#112/SA5#167)
End of Rel-20 supporting normative: Mar.2027 (SA#115/SA5#171)
6G Rel-20 study:
Start of Rel-20 study: Sep.2025 (SA#109/SA5#163)
End of Rel-20 study: Mar.2027 (SA#115/SA5#171)
Note: 6G time line needs more discussion based on inputs from SA 6G workshop

## Slide 18: SA5 Rel-20 capacity summary
SA5 capacity:
  Max TUs: 124 (OAM) / 80 (Charging)
    Additional buffer TUs: 61(OAM)/40(CH)
  Max number of SIs/WIs: 10~15 (OAM) / 6~10 (Charging)
    Note: one feature made up of SI+WI is counted as one item
  Max TUs per Feature: 12~8 TU
Assumptions
  Start: Jun 2025, End: Mar 2027 (21 months)
  One track for OAM and One track for Charging
  Number of meetings: 10
  Expected total TUs per meeting (for all releases): 18.5 (OAM) / 12 (Charging)
  Total TUs (for all releases): 185 (OAM) / 120 (Charging)
  TUs for maintenance of past releases: 35 (OAM) / 18 (Charging)
No change after SA#106

## Slide 19: TU allocation portion of 5GA part/6G part in Rel-20
SA5 has discussed the following 3 options for TU allocation portion of 5GA part/6G part in Rel-20
TU allocation portion of 5GA part/6G part |  | 
5GA | 6G | No. of supporting companies
50% | 50% | 6
1/3 | 2/3 | 6
2/3 | 1/3 | 6

## Slide 20
SA5 Rel-20 5G-A candidate topics
See S5-250168 for the consolidated list.
NOTE: A Topic may result in one or more SIDs.
S.No. | Rel-20 OAM Prime Topics | Rel-20 OAM Support Topics | Rel-20 CH Prime Topics | Rel-20 CH Support Topics
1 | AIML management enhancement | ISAC management | Charging reliability enhancement (failure handling) | AIML charging
2 | Energy efficiency enhancement | NTN management enhancement | Inter CHF communication continuation | AIoT charging
3 | Intent driven management enhancement | AIoT management | Charging profile enhancement | 5GSAT_Ph4 charging
4 | NDT enhancement | Management and SON for 5G Femto | CCS architecture evolution | 5G Femto + WAB Charging
5 | CCL enhancement | PM/KPI |  | CAPCH
6 | SBMA enhancement | AdNRM |  | EE charging - continuation
7 | Cloud-native management and orchestration | NWDAFM |  | NG_RTC charging –continuation ISAC charging
8 | MDA enhancement | Management of Network Sharing Phase 4 |  | 
9 | Knowledge-assisted management/Semantics – Based Network Management | XR management |  | 
10 | Mexpo enhancement | Vehicle Mounted Relays management |  | 
11 | MADCOL/Data Management | Management of WAB |  | 
12 | Trace/MDT/QoE/SON enhancement |  |  | 
13 | Security Monitoring |  |  | 
SA5 has recognized the above potential candidate topics for 5GA in Rel-20, prioritization is planned to be done in SA5#160/#161

## Slide 21: SA5 Liaisons to SA
Tdoc | Reply To | Title | Doc-type | Source | To | Cc | Action from SA
SP-250249 | S5-246415 | Reply to LS on establishment of new Focus Group on Artificial Intelligence Native for Telecommunication Networks (FG-AINN) | LS in | SA5 | ITU-T Study Group 13 | 3GPP SA | No action required from SA
SP-250251 | S5-250294 (S2-2501217: LS on energy information collection from OAM to EIF) | LS reply to LS on energy information collection from OAM to EIF | LS in | SA5 | SA2 | 3GPP SA | No action required from SA
SP-250248 | S5-250293 (S2-2413035: LS on A-IoT Conclusions in SA WG2) | Reply to LS on A-IoT Conclusions in SA WG2 | LS in | SA5 | RAN2, RAN1 | RAN, SA, RAN3 | No action required from SA
SP-250250 | S5‑250289 (RP-243316 on AI/ML UE sided data collection) | LS from SA WG5: Reply LS on AI/ML UE sided data collection | LS in | SA5 | RAN, RAN2 | SA, SA2, SA3 | No action required from SA

## Slide 22: TRs / TSs to SA#107 for information/approval
Tdoc | Title | For
SP-250144 | Presentation of TR 28.846 Study on charging aspects of satellite access phase 3 for Approval | For approval
SP-250145 | Presentation of TR 28.849 Study on charging aspects of Common API Framework for Northbound APIs (CAPIF) phase 2 for Approval | For approval
SP-250146 | Presentation of TR 28.851 Study on charging aspects of next generation real time communication services phase 2 for Approval | For approval
SP-250147 | Presentation of TR 28.853 Study on charging aspects of uncrewed aerial systems for Approval | For approval
4 CH TRs send to SA for approval

## Slide 23: List of SA5 CR pack to SA#106
List of Rel-19 CRs:
SP-250148 CR Pack on TEI19 - Pack 1/2
SP-250149 CR Pack on TEI19 - Pack 2/2
SP-250150 CR Pack on TEI18 - Pack 1/2
SP-250151 CR Pack on TEI18 - Pack 2/2
SP-250152 CR Pack on IDMS_MN_Ph3 - Pack 1/2
SP-250153 CR Pack on IDMS_MN_Ph3 - Pack 2/2
SP-250159 CR Pack on eMDAS_Ph3
SP-250160 CR Pack on SBMA_Ph3
SP-250162 CR Pack on AdNRM_Ph3
SP-250164 CR Pack on NTN_OAM_Ph2
SP-250166 CR Pack on PM_KPI_5G_Ph4
SP-250167 CR Pack on NetShare_OAM_Ph3
SP-250168 CR Pack on NR_RedCap_OAM
SP-250170 CR Pack on Energy_OAM_Ph3
SP-250171 CR Pack on 5G_ProSe_Ph3_CH
SP-250172 CR Pack on TraceQoE_OAM
SP-250176 CR Pack on EnergySys_CH
SP-250178 CR Pack on NWDAF_OAM_Ph2
SP-250179 CR Pack on FS_eMDAS_Ph3
SP-250180 CR Pack on Monstra-OAM
List of Rel-17/Rel-18 CRs:
SP-250154 CR Pack on TEI16 - Pack 1/2
SP-250155 CR Pack on TEI16 - Pack 2/2
SP-250156 CR Pack on AIML_MGT - Pack 1/2
SP-250157 CR Pack on AIML_MGT - Pack 2/2
SP-250158 CR Pack on TEI17
SP-250161 CR Pack on PM_KPI_5G_Ph3
SP-250163 CR Pack on AdNRM_ph2
SP-250165 CR Pack on OAM_NTN
SP-250169 CR Pack on TEI17_NIESGU
SP-250173 CR Pack on eMDAS_Ph2
SP-250174 CR Pack on eECM
SP-250175 CR Pack on MSAC
SP-250177 CR Pack on IDMS_MN_ph2

## Slide 24: Management and Orchestration

## Slide 25: 1. AIML：AI/ML management - phase 2
Progress since SA#106: The following topics were addressed:
  Work Plan & Guidelines
    AIML Management – Phase 2 work plan and guidelines
  Data Transfer Over User Plane Transfer of data over UP for RAN-defined option 3
  ML Model Training Approaches
    Pre-training and Fine-tuning
    Federated Learning
    Reinforcement Learning
    Distributed Training
    Knowledge-Based Transfer Learning
  Sustainability in AI/ML
    Sustainable AIML for ML training
  ML Model Performance and Reliability
    Model Confidence
    Authentication
    Training Data Effectiveness
    Training Data Statistics
  ML Model Training for Multiple Contexts
    ML model training for multiple contexts
  Inference Emulation
    AIML inference emulation and environment selection
  Other Enhancements
    OpenAPI specification description
    New symbols and abbreviations
    Enhancement on AIMLInferenceFunction NRM
    AI/ML capabilities management for RAN, 5GC, and MDA
  ML Model Delivery and Transfer
    Clarification of ML model delivery in RAN vs. ML model loading in SA5
    Enhancements to ML model loading use case
  Both Stage 1 (use cases/requirements) and Stage 2 (NRM) documents were thoroughly discussed through formal sessions, breakout sessions, and offline discussions. Good progress was made, particularly in ML model training approaches, namely for Federated Learning, Reinforcement Learning, Distributed Training, Pre-training, and Fine-tuning, laying the groundwork for potential agreements in the upcoming meetings.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020007 | Study on AI/ML management - phase 2 | FS_AIML_MGT_Ph2 | 12/12/2024 | 55% | SP-240965 | 100% | 
1060011 | AI/ML Management Phase 2 | AIML_MGT_Ph2 | 09/09/2025 | 0% | SP-241944 | 15% | 
OAM Prime feature
A total of 13 documents were approved, addressing the aspects listed below. The approved documents include agreements on key topics including Reinforcement Learning, Pre-specialised training/Fine-tuning, Distributed Training, and Federated Learning use cases and requirements. More discussions are needed to further enhance Stage 1 and also address NRM aspects:
  ML-Knowledge-based Transfer Learning
  New use case on ML inference emulation environment selection
  Training Data Effectiveness clarification
  Reinforcement Learning UC and Requirements
  Add Pre-training Use case
  Add overview of management of AI/ML capabilities for RAN 5GC and MDA
  Enhance OpenAPI specification description
  Update the requirement and solution to enhance the ML model loading use case
  Use case on training data statistics• Solution on training data statistics
  Use Case and Requirements for ML model training for multiple contexts
  Use case on federated learning.
Further discussions are needed to clarify the use cases and requirements, which should clear the way to converge on the corresponding Stage 2 (NRM).
A discussion paper on the transfer of data over UP for Option 3 was also discussed and endorsed, leading to the development of a reply LS from SA5 to RAN2 and TSG RAN, which included some highlights of SA5’s understanding of the scenarios while also addressing RAN’s request for clarification. SA5 concludes that, assuming the UP tunnel is between UE and gNB, it is feasible to develop the OAM solution for UE-side data transfer and seeks confirmation of this assumption from TSG RAN and RAN2. The LS is approved in S5-250828.
To achieve the September 2025 completion target, a work plan will be implemented to address specific work items in each meeting, stabilize Stage 1 and Stage 2 content by the end of August, and complete Stage 3 development by October. Additionally, the group will adopt a Draft CR approach for upcoming meetings, temporarily withholding Rel-19 CR submissions, with an assessment of maturity at the end of May 2025 to determine which content will be submitted as CRs.
  Impacts and dependencies on other WGs:
  Collaboration with SA1 on AI/ML related requirements, SA2 on 5GC AIML, SA3 on AIML security, SA6 on Application enablement layer AIML and RAN WGs for related requirements.
  Next steps: To accelerate progress, the group provisionally agreed to hold a series of conference calls before SA5#160.

## Slide 26: 2. MDA：Management Data Analytics (MDA) – Phase 3
Progress since SA#106:
  Data correlation analytics
    Adding new capability to perform analysis and provide recommendations related to data correlation.
    Enhancing the existing MDA capability for handover optimization analysis.
  ATSSS performance analytics
    Adding new capability to perform analysis and provide recommendations related to traffic steering.
  UE throughput analytics
    Adding new capability to perform analysis and provide recommendations related to traffic congestion.
  Fault management related analytics
    Adding new capability to perform analysis and provide report related to threshold crossing events.
    Adding new capability to perform analysis and provide recommendations related to service failure recovery.
    Enhancing the existing MDA capability for failure prediction.
  Software upgrade validation
    Adding new capability to perform analysis and provide recommendations related to validating a software upgrade.
  Control plane congestion analytics
    Enhancing the existing MDA capability for 5GC Control plane congestion analysis.
  Impacts and dependencies on other WGs:
  Coordination with SA1 on service requirements, SA2 on NWDAF, RAN3 on data collection.
Next steps:
  Add new capability to perform analysis and provide recommendations related to edge computing. Enhance the existing capability for energy saving analysis.Provide detailed solutions for new and enhanced capabilities...
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020019 | Study on Management Data Analytics (MDA) Phase 3 | FS_eMDAS_Ph3 | 12/12/2024 | 90% | SP-241157 | 100% | 
1060014 | Management Data Analytics phase 3 | eMDAS_Ph3 | 09/09/2025 | 0% | SP-241947 | 30% | 
OAM Prime feature

## Slide 27: 3. IDM: intent driven management services for mobile network phase 3
Progress since SA#106:
  WT-1: The use case and solution for Enablers for Intent Fulfilment is agreed, which proposes the capability to allow MnS consumer to subscribe and obtain the information of enablers for intent fulfilment.
  WT-2: Following enhancements are agreed to support new scenarios for intent driven management for mobile network, including:
    Enhance the RadioServiceExpectation to support the scenario of delivering a radio service in a scheduled time scenario.
    Enhance the RadioNetworkExpectation to support RAN energy saving scenario and Radio network traffic assurance for scheduled events scenario.
  WT-3: Following new intent driven management functionalities are agreed, including:
    Intent negotiation functionalities, including Intent feasibility check, Intent exploration, checking for fulfillable outcomes, checking for best possible outcome, recommending fulfillable intent targets and contexts, advises on preferred alternatives.
    Use case and requirements for intent utility function.
    Implicit intent report subscription with customized requirements.
    Intent handling capability enhancement to provide a description of the supported scenario specific intents.
    The capability to allow MnS consumer to express its preference on expectation and target
  WT-5: Use case and solution for Intent driven management of network maintenance
  WT-6: Guidelines for intent driven management, specially includes:
    Guidelines for using intent generic information model to support new scenario which is not standardized
    Update the description for Investigation phase to include functionalities of intent handling capability obtaining and intent pre-evaluation.
  Impacts and dependencies on other WGs:
  Provide radio network management support to SA1 on UAV pre-flight preparation requirements
Next steps:
  WT-2: Enhance the RadioNetworkExpectation to support scenario of radio network support for UAV pre-flight preparation
  WT-3: Consolidated solution for intent negotiation and corresponding procedures.
  WT-4: Intent driven approach for delivering communication service.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020008 | Study on intent driven management services for mobile network phase 3 | FS_IDMS_MN_Ph3 | 12/12/2024 | 95% | SP-231737 | 100% | 
1060013 | Intent driven management services for mobile network phase 3 | IDMS_MN_Ph3 | 06/06/2025 | 0% | SP-241946 | 65% | 
OAM Prime feature

## Slide 28: 4. CCL: closed control loop management
Progress since SA#106:
  Agreed TS structure.
  Agreed UC and Requirements for Dynamic composition of CCL, Historical CCL, CCL performance management.
  Discussed basic NRM with considering backward compatibility. WG could not reach consensus. Discussion will continue
  Impacts and dependencies on other WGs:
  None
Next steps:
  Offline coordination to be done to agree on the basic solution for conflict management, coordination functionality.
  Basic NRM need to keep backward compatibility with existing ACCL NRM
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020009 | Study on closed control loop management | FS_CCLM | 12/12/2024 | 90% | SP-231735 | 100% | 
1060010 | Closed Control Loop Management | CCLM | 09/09/2025 | 0% | SP-241943 | 10% | 
OAM Prime feature

## Slide 29: 5. NDT: management aspects of Network Digital Twin
Progress since SA#106:
  WT-1: The terms and concepts of Network Digital Twin in the 3GPP management system are agreed, proposing to describe the capabilities of NDT, its relationship with existing network automation functions, deployment locations, and NDT life-cycle management.
  WT2: The use cases, requirements for Network Digital Twin in 3GPP management system have been discussed during this meeting and agreed to merge the all UCs into 5 categories. the categories are: Network Automation, Verification, Data generation, Lifecycle Management, Advanced Issues, which will become the“umbrella”for the corresponding application specific use cases.
  WT3: No solutions for NDT to support above use cases have been addressed during this meeting.
  Impacts and dependencies on other WGs:
  Coordination with SA1 on terminology.
Next steps:
  WT-2: Consolidated use cased and corresponding requirements.
  WT-3: Forming a compromise method for the solutions for NDT to support above use cases, including the generic operations and generic information model for NDT and the application specific solution.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020018 | Study on management aspects of Network Digital Twin | FS_NDT | 12/12/2024 | 95% | SP-231727 | 100% | 
1060005 | Management aspects of Network Digital Twins | NDT | 09/09/2025 | 0% | SP-241938 | 10% | 
OAM Prime feature

## Slide 30: 6. CMO: Study on Cloud Aspects of Management and Orchestration
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020010 | Study on Cloud Aspects of Management and Orchestration | FS_Cloud_OAM | 12/12/2024 | 90% | SP-231781 | 85% | 
OAM Prime feature
Progress since SA#106:
  General：Add clarification to terminology NF deployment;
  WT-1:Three contributions have been discussed : one is about the “umbrella” for the related use cases in clause 5.1, other configuration documents refine the use cases and analyze detail updates on the 3GPP management and have achieved some progress.
  WT-2:Four contributions have been discussed on solution for 3GPP management architecture, specification impacts and Annex D, Six contributions have been discussed on data streaming use cases and declarative descriptor, and have achieved some progress.have discussion on a new use case “add Observability for CNFs” and it is approved.
  Impacts and dependencies on other WGs:
  None
Next steps:
  Focus on refining the WT-1 and WT-2 use cases and adding related evaluations. (given the limited TU, the WT-3 has a low priority).

## Slide 31: 7. MSEC: Study on Enablers for Security Monitoring
Progress since SA#106:
  None.
  Impacts and dependencies on other WGs:
  The events/use cases which can lead to security risks/threats and the related data that needs to be exposed need to be primarily defined by SA3
Next steps:
  This study is completed in SA#106, no normative Rel-19 work is planned so far.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020016 | Study on Enablers for Security Monitoring | FS_SECM | 12/12/2024 | 90% | SP-231736 | 100% | 
OAM Prime feature

## Slide 32: 8. SBMA: Service Based Management Architecture enhancement phase 3
Progress since SA#106:
  The following topics were approved:
  WT-1: SBMA definitions enhancement
  WT-3: Enhancing 3GPP TS 28.537 and 3GPP TS 28.622 to improve the overview information for each generic management capability
  WT-5: Clarifying SupportIOC instances are not used when an MnS is designed based on a model driven approach using a NRM and CRUD operations
  WT-6: Update the ProvMnS schema to decouple the ProvMnS schema and supported feature schema
  WT-9: Addition of definition of the common notification header
  WT-10: Addition of input parameters for filtering on alarm conditions
  The following topics were discussed:
  WT-2: Enhancing NRM TSs
  WT-4: Enhancing MnSInfo IOC to provide capabilities allowing MnS consumers to retrieve the MnS information for MnS instances based on specified areas
  WT-7: overview of management capabilities and corresponding Solution Sets.
  WT-8: Addition of generic MnS version handling
  Impacts and dependencies on other WGs:
  None
Next steps:
  WT-2: Enhancing NRM/PM TSsWT-4: Enhancing MnSInfo IOC to provide capabilities allowing MnS consumers to retrieve the MnS information for MnS instances based on specified areasWT-7: overview of management capabilities and corresponding Solution Sets.WT-8: Addition of generic MnS version handling.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020011 | Study on Service Based Management Architecture enhancement phase 3 | FS_SBMA_Ph3 | 12/12/2024 | 75% | SP-231725 | 100% | 
1060006 | Service Based Management Architecture enhancement phase 3 | SBMA_Ph3 | 09/09/2025 | 0% | SP-241939 | 40% | 
OAM Prime feature

## Slide 33: 9. PTM: Management of planned configurations
Progress since SA#106:
  Improvements were agreed for stage 2 of:
  planned configurations.
  planned configuration groups.
  fallback configurations
  trigger conditions
  validating planned configurations.
  activating planned configurations.
  Impacts and dependencies on other WGs:
  None
Next steps:
  Continue according to the plan
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020033 | Study on Management of planned configurations | FS_PlanM | 09/09/2024 | 60% | SP-231721 | 100% | 
1050032 | Management of planned configurations | PlanM | 09/09/2025 | 60% | SP-241379 | 75% | 
OAM Prime feature

## Slide 34: 10. MADCOL: Data management phase 2
Progress since SA#106:
  Agreed to convert from draft CR to CR in next meeting
  Agreed to have online discussion and rapporteur call to update the draft CR.
  Impacts and dependencies on other WGs:
  None
Next steps:
  continue according to the plan.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020025 | Data management phase 2 | MADCOL_Ph2 | 06/06/2025 | 88% | SP-240877 | 88% | 
OAM Prime feature

## Slide 35: 11. SREP: Data management regarding subscriptions and reporting
Progress since SA#106:
  The following topics need more discussion:
  QoE Reference Uniqueness
  Trace Reference Uniqueness
  Impacts and dependencies on other WGs:
  None
Next steps:
  Continue as plan
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020012 | Study on data management regarding subscriptions and reporting | FS_Data_SREP | 09/09/2024 | 60% | SP-231732 | 100% | 
1050033 | Data management regarding subscriptions and reporting | Data_SREP | 09/09/2025 | 0% | SP-241380 | 0% | 
OAM Prime feature

## Slide 36: 12. PM: 5G performance measurements and KPIs phase 4
Progress since SA#106:
  10 contributions were submitted and treated at this meeting, 2 CRs for WT-1, 7 CR for WT-2, and 1 discussion paper purposed to update the measurement template. Some of them were agreed at this meeting. The progress for each WT is described as follows.
  WT-1 (Rel19 PM/KPI):
    Add MA PDU session establishment time of network slice KPI for ATSSS in TS 28.554
    Update the handover related measurements in TS 28.552 (agreed)
  WT-2 (Rel18 PM/KPI):
    enhance the RAN UE throughput definition in TS 28.552 and TS 28.554(not pursued)
    Update the reference for reliability related KPIs in TS 28.554 (agreed)
    Corrections of Monitoring of NWDAF data collection Reference in TS 28.552(agreed)
    Correction of Mean time and max time of PDU session establishment in TS 28.552 (agreed)
    Add cell Unavailable Time performance measurement in TS 28.552
    Enhanced the PRB usage with subcounter S-NSSAI in TS 28.552
  WT-3 No contribution for UE level measurements in this meeting.
  WT-4 No contribution for PM streaming framework enhancement was submitted in this meeting.
  .
  Impacts and dependencies on other WGs:
  Potential coordination: providing performance measurements to network features defined in SA2, RAN2 and RAN3.
Next steps:
  Continue the work per the plan, some WTs may need to be expedited.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020026 | 5G performance measurements and KPIs phase 4 | PM_KPI_5G_Ph4 | 06/06/2025 | 65% | SP-241155 | 75% | 
OAM Support to Network features

## Slide 37: 13. AdNRM: 5G Advanced NRM features phase 3
Progress since SA#106:
  The following topics are discussed and approved:
  WT-1 (5GC NRM):
    Further enhancements on NFService in NRFFunction IOC agreed.
    NRM enhancements to NFProfile agreed.
    Adding support 5G Prose multi-hop relay services agreed.
  WT-2 (NR NRM):
    Additional NRM extensions for VMR Ph2 discussed, two new attributes agreed.
    Adding usecase and requirements for WAB-gNB management and corrections for MR-DC agreed.
  WT-5 (Stage3 enhancement):
    Enhance the OpenAPI related to isUnique and multiplicity for 5GcNrm.
  WT-6 (Edge)
    ManagedEdgeNFService enhancement agreed.
  Revising the WID related to AmbientIoT has been discussed and agreed.
  Impacts and dependencies on other WGs:
  Potential coordination: providing network resource model for network features defined in SA2, CT4, RAN3 and RAN4.
Next steps:
  5GC/NR/Edge/Stage3 NRM enhancement.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020027 | 5G Advanced NRM features phase 3 | AdNRM_Ph3 | 06/06/2025 | 60% | SP-240875 | 75% | 
OAM Support to Network features

## Slide 38: 14. TMQ: Subscriber and Equipment Trace and QoE collection management
Progress since SA#106:
  Corrections on VS Trace Record
  Add RRC report in missing IOCs
  Impacts and dependencies on other WGs:
  SA2, SA4, CT1, CT4, RAN2 and RAN3.
  RAN has proposals for work that might impact Trace, MDT and QoE in RP-232624.
  Studies in SA2 might impact Trace, MDT and QoE in Rel-19.
  If Signalling Based Activation is affected, CT4, RAN2 and RAN3 are affected.
Next steps:
  Corrections on Trace Record Format
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020028 | Subscriber and Equipment Trace and QoE collection management | TraceQoE_OAM | 06/06/2025 | 75% | SP-231748 | 80% | 
OAM Support to Network features

## Slide 39: 15. NTNM: Management Aspects of NTN Phase 2
Progress since SA#106:
  WT-1:
  CRs on adding requirements for configuring AMF with TAIs supported by NTN gNB
  CRs on adding NTN time-based configuration support
  CRs on enhancing NR NRM to support 5GS functions on board the NTN.
  WT-2:
  CRs on adding requirements for NTN neighbour cell management.
  WT-4:
  CRs on adding new requirements for NTN management
  Impacts and dependencies on other WGs:
  Co-ordination with SA2, RAN2, RAN3 where appropriate.
Next steps:
  Plan to submit contributions for use case, requirements and procedures to support NTN for WT-1，WT-2，WT-3.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020013 | Study on Management Aspects of NTN Phase 2 | FS_NTN_OAM_Ph2 | 12/12/2024 | 90% | SP-231733 | 100% | 
1060016 | Management Aspects of NTN Phase 2 | NTN_OAM_Ph2 | 06/06/2025 | 0% | SP-241949 | 25% | 
OAM Support to Network features

## Slide 40: 16. IABM: management of IAB nodes
Progress since SA#106:
  There is one contribution for WT-1 submitted in this meeting, can't reach consent on one issue related to location information that is used to obtain IP configuration for OAM connectivity. Need further discuss in next meeting.
  Impacts and dependencies on other WGs:
  Collaboration with SA2 on architecture enhancements, SA3 on security and RAN3 on NR Mobile IAB
Next steps:
  Plan to submit contributions for use case, requirements and procedures to support IAB-node OAM connectivity for WT-1.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020014 | Study on management of IAB nodes | FS_NR_mobile_IAB_OAM | 12/12/2024 | 90% | SP-231729 | 100% | 
1060015 | Management of IAB nodes | NR_MOBILE_IAB_OAM | 09/09/2025 | 0% | SP-241948 | 0% | 
OAM Support to Network features

## Slide 41: 17. RedcapM: management aspects of RedCap feature
Progress since SA#106:
  WT-1:
  CRs on adding requirements for management of RedCap feature are discussed and approved.
  CRs on enhancing NR NRM to support management of RedCap feature are discussed and approved.
  WT-2:
  CRs on enhancing measurements for RedCap feature are discussed.
  Impacts and dependencies on other WGs:
  RAN1 on RedCap related requirements and Physical layer methods
  SA2 on 5GC RedCap related NF services and configurations.
Next steps:
  The remaining requirements, NRM considerations, and PM aspects associated with the RedCap feature are scheduled for discussion at the upcoming meeting.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020017 | Study on management aspects of RedCap feature | FS_NR_RedCap_OAM | 12/12/2024 | 75% | SP-231734 | 100% | 
1060008 | Management Aspects of RedCap features | NR_RedCap_OAM | 09/09/2025 | 0% | SP-241941 | 50% | 
OAM Support to Network features

## Slide 42: 18. NWDAFM: Enhancement of Management Aspects related to NWDAF Phase 2
Progress since SA#106:
  WT1 is completed:
  S5-250964 was S5-250165 is a Rel-19 CR for 28.552. It adds a new measurement related to number of failed NWDAF roaming analytics service subscriptions considering 2 phases where the failure may happen and improve the description of the existed measurements on the failed analytics services to provide distinction.
  S5-250167 is a Rel-19 CR for 28.552. It adds new measurements related to failed rate of NWDAF roaming analytics service subscriptions. They are more handy and provide complimentary for the existed measurements.
  Impacts and dependencies on other WGs:
  Collaboration with SA2 on NWDAF.
Next steps:
  Keep working on WT2
    providing UC description
    providing new measurements based on TR
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020020 | Study on Enhancement of Management Aspects related to NWDAF Phase 2 | FS_NWDAF_OAM_Ph2 | 09/09/2024 | 75% | SP-231724 | 100% | 
1050031 | Enhancement of Management Aspects Related of NWDAF Phase 2 | NWDAF_OAM_Ph2 | 06/06/2025 | 60% | SP-241378 | 65% | 
OAM Support to Network features

## Slide 43: 19. NSM: Management of Network Sharing Phase3
Progress since SA#106:
  For WT-1
  Enhancements for deployment example of Service-based Management Architecture for MOCN are discussed but more time is needed
  Add access requirements for management of shared NG-RAN is agreed
  For WT-2
  Concepts and background for Indirect Network Sharing is agreed.
  Requirements for management of Indirect Network Sharing is agreed.
  Add requirements for RAN and CN management of Indirect Network Sharing is agreed.
  Impacts and dependencies on other WGs:
  SA1 and SA2
Next steps:
  For WT-1
  Enhancements for deployment example of Service-based Management Architecture for MOCN are planned to re-submit.
  For WT-2
  Enhancements supporting configuration for Indirect Network Sharing are planned to submit.
  PLMN-granularity performance measurements of CN functions are planned to submit..
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020015 | Study on Management of Network Sharing Phase3 | FS_NetShare_OAM_Ph3 | 12/12/2024 | 90% | SP-240966 | 100% | 
1060017 | Management of Network Sharing Phase 3 ?? | NetShare_OAM_Ph3 | 06/06/2025 | 0% | SP-241950 | 50% | 
OAM Support to Network features

## Slide 44: 20. EE: energy efficiency and energy saving aspects of 5G networks and services
Progress since SA#106:
  The following update are agreed
    Provide management support to RAN3 on Enhancements to energy cost mapping rule for split gNB
    Add Carbon emission and Renewable energy related definitions and abbreviations
    Update EE KPIs overview
  An LS out to ETSI EE/ITU-T SG5/NGMN GFN (Green Future Networks)/ETSI NFV for coordination on Multi-Domain EE.
  The following topics need more discussion
    Introducing EIFFunction IOC in 5GC NRM
    Modelling energy supply, carbon emission and renewable energy information elements
    Add GenericCollection to support grouping of objects - Stage 2
    multi-dimensional energy efficiency use case and requirements
    Procedure for renewable energy based LBO
  Impacts and dependencies on other WGs:
  The following WGs address aspects related to this study:
    SA1 and SA2, for aspects described in WT-2 and WT-5
    RAN1, RAN2 and RAN3, for aspects described in WT-3 and WT-5.
Next steps:
  Need contributions for WT-2 (highest priority), as several other WTs have dependency on WT-2.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020021 | Study on energy efficiency and energy saving aspects of 5G networks and services | FS_Energy_OAM_Ph3 | 12/12/2024 | 60% | SP-231723 | 100% | 
1060007 | Energy efficiency and energy saving aspects of 5G networks and services | Energy_OAM_Ph3 | 09/09/2025 | 0% | SP-241940 | 20% | 
OAM Prime feature

## Slide 45: 21. Mexpo: Enhanced OAM for management exposure to external consumers
Progress since SA#106:
  Revised SID proposes to down scope to objectives, i.e., to remove WT-2 and WT-3, as there has not been any content related to these WTs in the TR 28.879.
  TR 28.879 was enhanced to describe the scope and address comments from editHelp.
  The group agreed on the following aspects :
    An LS to SA3 requesting for the access token scope to accommodate more service-related information (e.g., resources and operations) other than the service name.
    General concepts and background information related to the exposure of management services.
    Definition of the API provider domain for management services (i.e., MSED) and its functionalities.
    The use case descriptions for two out of the four use cases
    For the next meeting, these will be our targets:
    Description and requirements for all use cases
    Solutions for some of the use cases
    Annexes showing the possible MSED deployment options.
  Impacts and dependencies on other WGs:
  Solutions proposed for identified use cases build upon R18 CAPIF features. Rel-18 CRs approved by SA6 (CAPIF stage-2), CT3 (CAPIF stage-3) and SA3 (CAPIF related security aspects) may impact these solutions; coordination will be required in such cases.
Next steps:
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020022 | Study on Enhanced OAM for management exposure to external consumers | FS_MExpo | 12/12/2024 | 60% | SP-240967 | 100% | 
1060009 | Enhanced OAM for management service exposure to external consumers through CAPIF | MExpo | 09/09/2025 | 0% | SP-241942 | 15% | 
OAM Prime feature

## Slide 46: 22. MonstraM: Management for MonStra
Progress since SA#106:
  No progress.
  Impacts and dependencies on other WGs:
  SA3 to specify the security aspects.
Next steps:
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1060012 | Management for MonStra | Monstra-OAM | 12/12/2024 | 80% | S5-245981 | 80% | 
OAM Prime feature

## Slide 47: Charging SWG

## Slide 48
SA5 SWG participations
  Quite stable number of participating and active delegates presenting mobile/satellite operators and mobile communication vendors interests
Charging Work progress on Rel-19
  Rel-19 Study Phase has been completed and corresponding WIDs are for approval
  Ongoing Rel-19 WIDs completion is in good progress with 7 new WID proposals
  Joined Session with OAM for new Rel-19 WID on Charging enhancement for MOCN network sharing
Charging Work for Rel-20 started
  4 CH prime topics and 7 CH network support topics identified
  2 CH topics selected to start Moderated Email Discussions
General information

## Slide 49: Charging (CH) WIs/SIs

## Slide 50: 1. CHSEG: WID on CHF Segmentation
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1040012 | WID on CHF Segmentation | CHFSeg | 03/03/2025 -> 12/09/2025 | 55 % | SP-241001 | 60 % | WID revised to adapt the schedule for completion because of dependency to SA2
CH Prime feature
Progress since SA#106
  no CR contributed for this meeting:
    Discussion paper on Introduction of features for domains for the way forward
    Exchange for a LS which addresses the need to have the CHF Set and CHG Group ID in the UDM
RAN impacts and dependencies:
  None identified
Next steps:
  Further discussions on use of CHF Group Id for CHF selection and procedures/message flow, PCF interaction when N107 is used and use of Charging Characteristics for other NF consumer

## Slide 51: 2. RAGCH: WID on Charging Aspects of Ranging and Sidelink Positioning
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1040013 | WID on Charging Aspects of Ranging and Sidelink Positioning | Ranging_SL_CH | 03/03/2025 | 100 % | SP-241002 | 100 % | completed
CH Support to Network features
Progress since SA#106
  Completed
RAN impacts and dependencies:
  None identified
Next steps:
  None

## Slide 52: 3. EESCH: WID on charging aspects for energy efficiency of network slice
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1040018 | WID on charging aspects for energy efficiency of 5G | EnergySys_CH | 06/06/2025 | 45 % | SP-241003 | 100 % | Completed Revised WID on renaming
Progress since SA#106
  2 CR agreed covering:
    Addition of network slice energy information (TS 32.291, TS 32.298)
RAN impacts and dependencies:
  None identified
Next steps:
  None
CH Support to Network features

## Slide 53: 4. NSCH: WID on charging enhancement for indirect network sharing
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1040019 | WID on charging enhancement for indirect network sharing | NetShare_CH | 12/12/2024 | 100 % | SP-241004 | 100 % | completed
Progress since SA#106
  completed
RAN impacts and dependencies:
  None identified
Next steps:
  None
CH Support to Network features

## Slide 54: 5. PROCH: WID on Charging Aspects for 5G ProSe Ph3
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1050030 | New WID on Charging Aspects for 5G ProSe Ph3 | 5G_ProSe_Ph3_CH | 12/09/2025 | 0 % | SP-241377 | 25 % | 
Progress since SA#106
  3 CRs agreed covering stage 2 aspects in TS 32.277:
    Add charging-related information in support of ProSe Multi-Hop UE-to-Network communication
    Update Message flows for ProSe Direct Discovery over PC5 reference point
    Update Message flows for ProSe UE-to-Network Direct Communication
RAN impacts and dependencies:
  None identified
Next steps:
  Complete message flow description and start the parameter description
CH Support to Network features

## Slide 55: 6. SATCH: Study on charging aspects of satellite access Phase 3
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1040014 | Study on charging aspects of satellite access Phase 3 | FS_5GSAT_Ph3_CH | 03/03/2025 | 75 % | SP-240980 | 100 % | completed
CH Support to Network features
Progress since SA#106
  16 pCRs for TR 28.846 were approved covering
    Update of architecture and Business scenarioss
    Add store and forward satellite operation charging solutions for User Plane CIoT
    Update evaluation and conclusion for store & forward satellite operation charging
    Solution update for topic 3
    Add References, Evaluation and Conclusion for satellite resource usage charging
    Add charging solutions, evaluation and conclusion for UE-SAT-UE communication
    Add conclusions and recommendations
  Presentation of TR 28.846 for Approval
RAN impacts and dependencies:
  None identified
Next steps:
  Start normative work

## Slide 56: 7. CAPCH: SID on Charging Aspects of CAPIF
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1040015 | SID on Charging Aspects of CAPIF | FS_CAPIF_Ph2_CH | 03/03/2025 | 75 % | SP-240981 | 100 % | completed
CH Support to Network features
Progress since SA#106
  12 pCRs for TR 28.849 were approved covering
    Editorial corrections
    New Solutions: Service API Management, API Invoker Management
    Evaluations/Conclusions: API Service Management, Multiple API Providers, Service API Management, and API Invoker Management
  Presentation of TR 28.849 for Approval
RAN impacts and dependencies:
  None identified
Next steps:
  Start normative work

## Slide 57: 8. RTCCH: SID on Charging aspects of next generation real time communication services phase 2
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1040016 | SID on Charging aspects of next generation real time communication services phase 2 | FS_NG_RTC_Ph2_CH | 03/03/2025 | 75 % | SP-240982 | 100 % | completed
CH Support to Network features
Progress since SA#106
  11 pCRs for TR 28.851 were approved covering
    New charging solutions for DC application usage by volume and download by volume
    Update evaluation for Topic 2 and add conclusion for Topic 1, Topic 2, Topic 3, Topic 4
    New KI on Support of Avatar communication
    Adding solution on Support of Avatar communication
    Conclusions and recommendations
  Presentation of TR 28.851 for Approval
RAN impacts and dependencies:
  None identified
Next steps:
  Start normative work including preliminary work on Avatar communication based on revised WID for NG_RTC_Ph2_CH

## Slide 58: 9. UASCH: SID on Charging aspects of Uncrewed Aerial Vehicle
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1040017 | SID on Charging aspects of Uncrewed Aerial Vehicle | FS_UAS_PH2_CH | 03/03/2025 | 75 % | SP-240983 | 100 % | completed
CH Support to Network features
Progress since SA#106
  6 pCRs for TR 28.853 were approved covering
    Add new solution for UAV information.
    Add evaluation and conclusion for UAS charging topic 1, topic 2 and topic 3.
    Update Conclusions and Recommendations.
  Presentation of TR 28.853 for Approval
RAN impacts and dependencies:
  None identified
Next steps:
  Start normative work

## Slide 59: 10.SATCH: WID on Charging aspects of satellite access Phase 3
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1070014 | WID on Charging aspects of satellite access Phase 3 | 5GSAT_Ph3_CH | 12/09/2025 | 0 % | SP-250117 |  | (for SA approval)
Progress since SA#106
  New WID proposal
RAN impacts and dependencies:
  None identified
Next steps:
  Start the WID
CH Support to Network features

## Slide 60: 11.CAPCH: WID on Charging aspects of CAPIF
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1070015 | WID on Charging aspects of CAPIF | CAPIF_Ph2_CH | 12/09/2025 | 0 % | SP-250118 |  | (for SA approval)
Progress since SA#106
  New WID proposal
RAN impacts and dependencies:
  None identified
Next steps:
  Start the WID
CH Support to Network features

## Slide 61: 12. RTCCH: WID on Charging aspects of next generation real time communication services phase 2
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1070016 | WID on Charging aspects of next generation real time communication services phase 2 | NG_RTC_Ph2_CH | 12/09/2025 | 0 % | SP-250119 |  | (for SA approval)
Progress since SA#106
  New WID proposal
RAN impacts and dependencies:
  None identified
Next steps:
  Start the WID, probably with preliminary work on Avatar communication after e-mail approval of the remaining pCRs from the study based on revised WID proposal
CH Support to Network features

## Slide 62: 13.UASCH: WID on Charging for Uncrewed Aerial Systems Phase 2
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1070017 | WID on Charging for Uncrewed Aerial Systems Phase 2 | UAS_Ph2_CH | 12/09/2025 | 0 % | SP-250120 |  | (for SA approval)
Progress since SA#106
  New WID proposal
RAN impacts and dependencies:
  None identified
Next steps:
  Start the WID
CH Support to Network features

## Slide 63: 14. LCSCH: WID on Charging Aspects of 5GC LoCation Services
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1070019 | WID on Charging Aspects of 5GC LoCation Services | 5G_eLCS_CH | 12/09/2025 | 0 % | SP-250125 |  | (for SA approval)
Progress since SA#106
  New WID proposal
RAN impacts and dependencies:
  None identified
Next steps:
  Start the WID
CH Support to Network features

## Slide 64: 15.AIOCH: WID on Charging for Ambient power-enabled Internet of Things
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1070018 | WID on Charging for Ambient power-enabled Internet of Things | AmbientIoT_CH | 12/09/2025 | 0 % | SP-250121 |  | (for SA approval)
Progress since SA#106
  New WID proposal
RAN impacts and dependencies:
  None identified
Next steps:
  Start the WID
CH Support to Network features

## Slide 65: 16. CHNSH: WID on Charging enhancement for MOCN network sharing
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1070020 | WID on Charging enhancement for MOCN network sharing | CHNetShare | 12/09/2025 | 0 % | SP-250126 |  | (for SA approval)
Progress since SA#106
  New WID proposal
RAN impacts and dependencies:
  Not known
Next steps:
  Start the WID
CH Prime feature

## Slide 66: Thank you!

## Slide 67: General information (time plan/meeting plan/forge)

## Slide 68
Release 19 timeline– figure with SA5 (Based on SA timeline)
Release 19 timeline
#101
#102
#103
#104
#105
#106
#107
#108
#109
#110
#111
#112
#99
RAN4
content def.
RAN Content def.
2024
2025
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Mar.
Dec.
Dec.
Dec.
2026
RAN4_Perf
Stage 3 (CT & SA including SA5)
RAN1
Stage 2 (SA2, SA6,…) Normative
RAN Completion (RAN2/3/4core)
ASN.1 & Open APIs
St.2 Content approval
#100
Jun.
2023
Now
100%
SA1 Stage 1 80%
TSGs
RAN Rel-19 workshop
SA Rel-19
Workshop
Management requirements (SA5)
Stage 2 (SA5) Normative supporting SA&RAN
OAM:
Dec 2024: conclude Rel-19 studies which plan to have corresponding normative work in Rel-19.
Sep 2025: conclude all Rel-19 work items, majority work items are preferable to be finalized in Jun 2025.
CH:
Dec 2024->Mar 2025: conclude Rel-19 studies which plan to have corresponding normative work in Rel-19.
Sep 2025: conclude all Rel-19 work items
Note: Studies can continue until Sep.2025 if no corresponding normative work is planned for Rel-19.
3GPP SA5
Time plan

## Slide 69: 3GPP SA & SA5 meeting calendar (2025)
Meeting info | DateTime | Location | Release dates | Other WGs (potential colocation)
SA5#159 | 17 Feb 2025- 21 Feb 2025 | Sophia Antipolis, FR | 5GA SA5 workshop | 
SA#107 | 10 Mar 2025- 14 Mar 2025 | Incheon, South Korea | 6G workshop | 
SA5#160 | 07 Apr 2025- 11 Apr 2025 | Goteborg, SE |  | SA2/3/4/5/6
SA5#161 | 19 May 2025- 23 May 2025 | Fukuoka, Japan |  | SA WGs
SA#108 | 09 Jun 2025- 13 Jun 2025 | Prague, Czech Republic |  | 
SA5#162 | 25 Aug 2025- 29 Aug 2025 | Goteborg, SE |  | SA WGs/CT WGs
SA#109 | 15 Sep 2025- 19 Sep 2025 | China | Rel-19 freeze | 
SA5#163 | 13 Oct 2025- 17 Oct 2025 | China |  | SA2/3/4/5/6 and CT1/3/4 WGs
SA5#164 | 17 Nov 2025- 21 Nov 2025 | DALLAS, TEXAS |  | CT WGs, SA WGs, RAN WGs
SA#110 | 08 Dec 2025- 12 Dec 2025 | BALTIMORE, MARYLAND |  | 
6 f2f SA5 meeting planned in 2025
This slide is only for information, please book your hotel/flight after you received official meeting invitation

## Slide 70
6 f2f SA5 meeting planned in 2026, SA5 meetings to be collocated with other SA WG as much as possible.
This slide is only for information, please book your hotel/flight after you received official meeting invitation
Reference: confirmed tdoc from MHPG
Meeting info | DateTime | Location | Release dates | Other WGs (potential colocation)
SA5#165 | 9 Feb 2026 - 13 Feb 2026 | India |  | 
SA#111 | 9 Mar 2026 - 13 Mar 2026 | Japan |  | 
SA5#166 | 13 Apr 2026 - 17 Apr 2026 | Europe |  | 
SA5#167 | 18 May 2026 - 22 May 2026 | China |  | 
SA#112 | 08 Jun 2026 - 12 Jun 2026 | Singapore |  | 
SA5#168 | 24 Aug 2026 - 28 Aug 2026 | Europe |  | 
SA#113 | 14 Sep 2026 - 18 Sep 2026 | Madrid |  | 
SA5#169 | 12 Oct 2026 - 16 Oct 2026 | Prague |  | 
SA5#170 | 16 Nov 2026 - 20 Nov 2026 | North America |  | 
SA#114 | 07 Dec 2026 - 11 Dec 2026 | North America |  | 
3GPP SA & SA5 meeting calendar (2026)

## Slide 71: Rel-19 SA5 Summary Information in forge
SA5 Rel-19 ongoing topics
  Details of SA5 Rel-19 approved WIDs/SIDs : https://forge.3gpp.org/rep/sa5/MnS/-/wikis/SA5/Rel-19-Moderated-Topics
Stage 3 forge links: https://forge.3gpp.org/rep/sa5/MnS
  Management and Orchestration APIs:
    OpenAPI solution is captured in https://forge.3gpp.org/rep/all/5G_APIs (3GPP unified stage3 repository) and https://forge.3gpp.org/rep/sa5/MnS/-/tree/Rel-19/OpenAPI (SA5 stage3 repository)
    YANG solution is captured in https://forge.3gpp.org/rep/sa5/MnS/-/tree/Rel-19/yang-models (SA5 stage3 repository)
    Balazs Lengyel (Ericsson) as YANG Code moderator
    Sean Sun (Nokia) and Ruiyue Xu (Huawei) as YAML Code moderator
  Charging APIs:
    OpenAPI solution to be captured in https://forge.3gpp.org/rep/all/5G_APIs (3GPP unified stage3 repository) and https://forge.3gpp.org/rep/sa5/CH/-/tree/Rel-19/OpenAPI (SA5 stage3 repository)
    ASN.1 solution to be captured in https://forge.3gpp.org/rep/sa5/CH/-/tree/Rel-19/ (SA5 stage3 repository)
    Chen Shan (Huawei) as Charging YAML Code moderator
    Robert Törnkvist (Ericsson) as Charging ASN.1 Code moderator
  Stage 3 forge is supported by SA5 MCC and Miguel Angel Reina Ortega (ETSI) as code master.

## Slide 72: TU planning
Latest TU planning is captured in https://www.3gpp.org/ftp/Email_Discussions/SA5/SA5-level%20discussions/SA5%23157

## Slide 73: SA5 calendar with OAM TU (one track)
Time | Monday | Tuesday | Wednesday | Thursday | Friday (Closing plenary)
Q0 (If needed) |  | Breakout (opt.) | Breakout (opt.) | Breakout (opt.) | Closing plenary Start at 8:30am (may change depends on the host restriction)
Q1 (9:00 - 10:30) | Plenary Session#1 (1TU) [Single Stream] | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Closing plenary
10:30 - 11:00 | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break
Q2 (11:00 - 12:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Closing plenary
12:30 - 14:00 | Lunch | Lunch | Lunch | Lunch | Lunch
Q3 (14:00 - 15:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Closing plenary
15:30 - 16:00 | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break
Q4 (16:00 - 17:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Revision session | Closing plenary
17:30 - 17:40 | Break | Break | Break | Break | Break
Q5 (17:40 – 19:10) | Stream#1 (1TU) | Stream#1 (0.5 TU) Stop around 18:45 Social evening | Stream#1 (1TU) | Revision session | 
Assumption: Every day = 5 sessions (TUs), total TU in 1 ordinary meeting (exclude closing plenary TUs) = 18.5 TUs

## Slide 74: Rel-19 TU Budget for SA5 OAM
Assumptions for SA5 OAM :
  6 ordinary meeting per year.
  Rel-19 spans 21 months for SA5 (with early start of studies) = 10 meetings
  1 Session = 1.5 hour time window
  Max 5 sessions per meeting day
  1 Stream = 1 TU (Time Unit)
  1 TU is time (i.e., 1.5 hours) spent to discuss/handle technical contributions.
  Revisions/Drafting/offline conference call are not counted for the TU estimates.
  OAM revision sessions normally planned to be in Thursday Q4 and Q5 (initial assump.)
  1 parallel (OAM) stream per session => 18.5 TUs per meeting (incl. 2 TUs as buffer) = 185
  Assume Maintenance + Buffer = 33% => ~ 61 TU
  Resulting total TUs avail. f. SI/WI: 10 meetings x 18.5 sessions = 185 TU minus 61 => 124 TU
  With 20 SI/WI => Average 6 TU per SI/WI (0.6/meeting).
No update since SA#104

## Slide 75: SA5 Rel-19 OAM TU planning (Jan.2024~Sep.2025)
 | Maintenance+R18 | R19 | R20 preparation | Buffer (revision session)
Jan.2024~Mar.2024 SA5#153 (1 meeting) (Last meeting for Rel-18) | 1.5 TU (CR)+13 TU (Rel-18)=14.5 TU | 2 TU | NA | 2 TU
Apr. 2024~Dec.2024: SA5#154~#158 (5 meetings) | 2.5 TU*5 meetings = 12.5 TU (CRs) | 14 TU*5 meetings= 70 TU | NA | 2 TU*5=10 TU
Jan.2025~Sep.2025: SA5#159~#162 (4 meetings) | 1.5 TU*4 meetings= 6 TU (CRs) | 13 TU*4 meetings= 52 TU | 2 TU*4 meetings = 8 TU | 2 TU*4=8 TU
Total=185 TU | 33 TU | 124 TU | 8 TU | 20 TU
Assumptions:
Every meeting day = 5 quarters (= 5 TUs)
Total TUs per meeting = 18.5 TUs
  Buffer = 2 TUs
  OAM = 16.5 TUs
    Maintenance CRs + remaining Rel-18 work (TU allocation will decrease over time )
    Rel-20 preparation work (TU allocation will be zero at the beginning and will increase over time )
    All remaining time is available for Rel-19 SIDs / WIDs
Total TUs allocated to Rel-19 SIDs / WIDs = 120 TUs, implying:
  12 TUs allocated to Rel-19 SIDs / WIDs per meeting (= 120 TUs / 10 meetings)
  6 TUs allocated to each Rel-19 SID / WID in average (= 120 TUs / 20 Rel-19 SIDs/WIDs)
  0.6 TU allocated per Rel-19 SID / WID per meeting in average (= 12 TUs / 20 Rel-19 SIDs/WIDs)
No update since SA#104

## Slide 76: SA5 calendar with CH TU (one track)
Time | Monday | Tuesday | Wednesday | Thursday | Friday (Closing plenary)
Q0 (If needed) |  | Breakout (opt.) | Breakout (opt.) |  | Closing plenary Start at 8:30am (may change depends on the host restriction)
Q1 (9:00 - 10:30) | Plenary Session#1 (1TU) [Single Stream] | Stream#1 (1TU) | Stream#1 (1TU) | Revision session | Closing plenary
10:30 - 11:00 | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break
Q2 (11:00 - 12:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Revision session | Closing plenary
12:30 - 14:00 | Lunch | Lunch | Lunch | Lunch | Lunch
Q3 (14:00 - 15:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | CH Closing | Closing plenary
15:30 - 16:00 | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break
Q4 (16:00 - 17:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | CH Closing | Closing plenary
17:30 - 17:40 | Break | Break | Break | Break | Break
Q5 (17:40 – 19:10) | Stream#1 (1TU) | Stream#1 (0.5 TU) Stop around 18:45 Social evening | Stream#1 (1TU) | CH Closing(Opt.) | 
Assumption: Every day = 5 sessions (TUs), total TU in 1 ordinary meeting (exclude closing plenary TUs) = 15.5 TUs

## Slide 77: TU Budget for SA5 CH
Assumptions for SA5 CH :
  6 ordinary meeting per year.
  Rel-19 spans 18 months for SA5 (with early start of studies) = 8 meetings
  1 Session = 1.5 hour time window
  Max 5 sessions per meeting day
  1 Stream = 1 TU (Time Unit)
  1 TU is time (i.e., 1.5 hours) spent to discuss/handle technical contributions.
  Revisions/Drafting/offline conference call are not counted for the TU estimates.
  CH revision sessions normally planned to be in Thursday Q1 and Q2 (initial assump.),CH closing plenary planned to be in Thursday Q3 and Q4.
  1 (CH) stream per session => 15.5 TUs per meeting (incl. 2 TUs as buffer) = 124
  Assume Maintenance + Buffer = 33% as in SA2 => ~ 41 TU
  Resulting total TUs avail. f. SI/WI: 9 meetings x 15.5 sessions = 124 TU minus 41 => 83 TU
  => Recommended MAX no. of SI/WI = 14
  With 14 SI/WI => Average 6 TU per SI/WI (0.75/meeting).

## Slide 78: SA5 Rel-19 CH TU planning (May.2024~Sep.2025)
 | Maintenance+R18 | R19 | R20 preparation | Buffer (revision session)
May. 2024: SA5#155 (1 meeting) | 2.5 TU*1eetings = 2.5 TU (CRs) | 6 TU*1 meetings= 6 TU 5 TU: Rel-19 topic discussion | NA | 2 TU*4=8 TU
July. 2024~Dec.2024: SA5#156~#158 (3 meetings) | 2.5 TU*3 meetings = 7.5 TU (CRs) | 11 TU*3 meetings= 33 TU | NA | 2 TU*4=8 TU
Jan.2025~Sep.2025: SA5#159~#162 (4 meetings) | 1.5 TU*4 meetings= 6 TU (CRs) | 11 TU*4 meetings= 44 TU | 1 TU*4 meetings = 4 TU | 2 TU*4=8 TU
Total= 124 TU | 16 TU | 83 TU | 4 TU | 16 TU
Assumptions:
Every meeting day = 5 quarters (= 5 TUs)
Total TUs per meeting = 15.5 TUs
  Buffer = 2 TUs
  CH = 13.5 TUs
    Maintenance CRs + remaining Rel-18 work (TU allocation will decrease over time )
    Rel-20 preparation work (TU allocation will be zero at the beginning and will increase over time )
    All remaining time is available for Rel-19 SIDs / WIDs
Total TUs allocated to Rel-19 SIDs / WIDs = 83 TUs