## Slide 1: SA5 Status Report to SA#108
Zou Lan, SA5 Chair, Huawei
Thomas Tovinger, SA5 Vice Chair, Ericsson
Anatoly Andrianov, SA5 Vice Chair, Nokia
Gerald Görmer, SA5 Charging SWG Chair, MATRIXX Software
Antoine Mouquet, MCC, ETSI

## Slide 2: SA5 leadership
SA5
Zou Lan (Huawei) Chair since 08/2023
Thomas Tovinger (Ericsson) Vice Chair since 08/2023 Anatoly Andrianov (Nokia) Vice Chair since 08/2023
Antoine Mouquet MCC since 11/2023
  Charging Sub-Working Group (SWG)
Gerald Görmer (MATRIXX Software) SWG Chair since 08/2021 Chen Shan (Huawei) SWG Vice Chair since 05/2016

## Slide 3: Contents
General aspects of SA5
SA5 overall progress since SA#107
Management Feature relations with other WGs
Management and Orchestration
Charging

## Slide 4: SA5 general information since SA#107
Two f2f meeting in 2Q2025
  Statistics SA5#160, 7 – 11 April, 2025 Goteborg, Sweden
    152 delegates ‘attended’ (checked-in) 44 registered for ‘On-Line’ participation
    912 documents (including revisions) including:
      540 CRs submitted (including revisions)，Total CRs agreed: 223
      13 Incoming LSs, 2 postponed
      7 Outgoing LSs Approved
    SA5 CH SWG statistics:
    Meeting registration and participation
      32 registered delegates
      24 delegates participated
      6 delegates from remote
    Documents to this meeting
      86 submitted contributions
      60 agreed contributions including
        3 contributions from the CH plenary
        2 revised Rel-19 WIDs
        45 CRs for Rel-19 WIDs, 10 CRs for Maintenance
  Statistics SA5#161, 19 – 23 May, 2025 Fukuoka, Japan
    169 delegates ‘attended’ (checked-in) 29 registered for ‘On-Line’ participation
    909 documents (including revisions) including:
      490 CRs submitted (including revisions)，Total CRs agreed: 202
      20 Incoming LSs, 4 postponed
      8 Outgoing LSs Approved
    SA5 CH SWG statistics:
      Meeting registration and participation
        25 registered delegates
        15 delegates participated
        5 delegates from remote
      Documents to this meeting
        75 submitted contributions
        57 agreed contributions including
          3 contributions from the CH plenary
          1 LSin and 2 LSout
          1 new Rel-19 WID and 1 revised Rel-19 WID
          37 agreed CRs for Rel-19 WIDs
          12 CRs for Maintenance

## Slide 5: SA5 meeting statistics (2024/2025)
Chart: Number of delegates in SA5
| SA5#153 | SA5#154 | SA5#155 | SA5#156 | SA5#157 | SA5#158 | SA5#159 | SA5#160 | SA5#161
F2F delegates | 76 | 170 | 140 | 188 | 129 | 172 | 70 | 152 | 169
Online delegates | 28 | 21 | 20 | 29 | 53 | 28 | 31 | 44 | 29
Chart: LS exchange
| SA5#153 | SA5#154 | SA5#155 | SA5#156 | SA5#157 | SA5#158 | SA5#159 | SA5#160 | SA5#161
incoming LS | 45 | 32 | 14 | 27 | 19 | 17 | 22 | 13 | 12
Outgoing LS | 21 | 21 | 7 | 14 | 7 | 11 | 15 | 7 | 5
Chart: Total number and agreed tdoc numbers
| SA5#153 | SA5#154 | SA5#155 | SA5#156 | SA5#157 | SA5#158 | SA5#159 | SA5#160 | SA5#161
Total number of tdocs | 1092 | 1122 | 1137 | 1515 | 1078 | 1062 | 1052 | 912 | 909
Number of agreed tdocs | 447 | 379 | 460 | 698 | 447 | 408 | 386 | 296 | 305
Chart: Allocation of agreed tdocs
| SA5#153 | SA5#154 | SA5#155 | SA5#156 | SA5#157 | SA5#158 | SA5#159 | SA5#160 | SA5#161
R15 CR | 1 | 4 | 1 | 9 | 3 | 1 | 0 | 0 | 0
R16 CR | 13 | 12 | 15 | 32 | 12 | 7 | 6 | 1 | 8
R17 CR | 37 | 37 | 43 | 76 | 29 | 24 | 13 | 4 | 9
R18 CR | 215 | 133 | 163 | 154 | 62 | 70 | 55 | 27 | 24
R19 CR | 22 | 32 | 108 | 100 | 118 | 172 | 192 | 161
others | 181 | 164 | 205 | 311 | 241 | 188 | 140 | 73 | 103

## Slide 6: SA5 meeting statistics (Rel-19 OAM topics)
Observation: AIML/CMO/NDT/IDM/CCL/EE/MDA/SBMA are top 8 contribution topics in Rel-19
Topics | Total Submitted tdocs | total agreed tdocs
AIML | 357 | 128
MADCOL | 52 | 32
SEPM | 32 | 19
PM | 109 | 64
AdNRM | 92 | 70
TMQ | 39 | 27
NTNM | 89 | 81
IABM | 24 | 22
RedcapM | 61 | 45
NWDAFM | 38 | 30
NSM | 49 | 48
MDA | 134 | 107
EE | 153 | 76
Mexpo | 102 | 61
MonstraM | 15 | 9
IDM | 174 | 132
CCL | 160 | 108
NDT | 196 | 89
CMO | 203 | 80
MSEC | 7 | 6
SBMA | 124 | 79
PTM | 63 | 57
Chart: Rel-19 OAM submitted tdocs
| AIML | MADCOL | SEPM | PM | AdNRM | TMQ | NTNM | IABM | RedcapM | NWDAFM | NSM | MDA | EE | Mexpo | MonstraM | IDM | CCL | NDT | CMO | MSEC | SBMA | PTM
total submitted | 357 | 52 | 32 | 109 | 92 | 39 | 89 | 24 | 61 | 38 | 49 | 134 | 153 | 102 | 15 | 174 | 160 | 196 | 203 | 7 | 124 | 63
total agreed | 128 | 32 | 19 | 64 | 70 | 27 | 81 | 22 | 45 | 30 | 48 | 107 | 76 | 61 | 9 | 132 | 108 | 89 | 80 | 6 | 79 | 57

## Slide 7
Release 19 timeline– figure with SA5 (Based on SA timeline)
Release 19 timeline
#101
#102
#103
#104
#105
#106
#107
#108
#109
#110
#111
#112
#99
RAN4
content def.
RAN Content def.
2024
2025
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Mar.
Dec.
Dec.
Dec.
2026
RAN4_Perf
Stage 3 (CT & SA including SA5)
RAN1
Stage 2 (SA2, SA6,…) Normative
RAN Completion (RAN2/3/4core)
ASN.1 & Open APIs
St.2 Content approval
#100
Jun.
2023
Now
100%
SA1 Stage 1 80%
TSGs
RAN Rel-19 workshop
SA Rel-19
Workshop
Management requirements (SA5)
Stage 2 (SA5) Normative supporting SA&RAN
OAM:
Dec 2024: conclude Rel-19 studies which plan to have corresponding normative work in Rel-19.
Sep 2025: conclude all Rel-19 work items, majority work items are preferable to be finalized in Jun 2025.
CH:
Mar 2025: conclude Rel-19 studies which plan to have corresponding normative work in Rel-19.
Sep 2025: conclude all Rel-19 work items
Note: Studies can continue until Sep.2025 if no corresponding normative work is planned for Rel-19.
3GPP SA5
Time plan

## Slide 8
New Rel-19 Study / Work Items
TDoc | Title | Type | UID | (Suggested) Acronym
SP-250509 | New WID on Converged Charging Aspects of CAPIF Phase 3 | WID new | 1080019 | CAPIF_Ph3_con-CH
1 new CH Rel-19 work items sent for SA approval (1 CH support to network features)

## Slide 9
Revised Rel-19 Study / Work Items
5 revised work items sent for SA approval including 3 CH WIDs and 2 OAM WIDs
Tdoc | Type | Release | Title | Comment
SP-250510 | WID revised | Rel-19 | Revised WID on Charging enhancement for MOCN network sharing | Reassign charging trigger from TS 32.255 to TS 28.201
SP-250512 | WID revised | Rel-19 | Revised WID on Charging for Uncrewed Aerial Systems Phase 3 | Add Rel-19 Charging support feature for C2 communication reliability.
SP-250513 | WID revised | Rel-19 | Revised WID on Charging aspects of next generation real time communication services phase 2 | Add Rel-19 Charging support feature for avatar communication in TS 32.260
SP-250514 | WID revised | Rel-19 | Revised WID on Management Aspects of NTN Phase 2 | Update impacted TS information
SP-250511 | WID revised | Rel-19 | Revised WID on 5G performance measurements and KPIs phase 4 | Update impacted TS information

## Slide 10: Overview of Rel-19 SA5 OAM topics (ongoing SI+ All WIs)
 |  | Abbr. | Acronym | Title | UID | rapp | Tdoc | TS/TR | Type
Intelligence and Automation | 1 | AIML | AIML_MGT_Ph2 | AI/ML management phase 2 | 1060011 | NEC, Intel | SP-241944 | TS 28.105/552/554/541 | WI
 | 2 | MDA | eMDAS_Ph3 | Management Data Analytics phase 3 | 1060014 | Huawei | SP-241947 | TS 28.104 | WI
 | 3 | IDM | IDMS_MN_Ph3 | Intent driven management services for mobile network phase 3 | 1060013 | Huawei, Ericsson | SP-241946 | TS 28.312 | WI
 | 4 | CCL | CCLM | Closed Control Loop Management | 1060010 | Samsung, Nokia | SP-241943 | TS 28.567/535/536/622/32.161 | WI
 | 5 | NDT | NDT | Management aspects of Network Digital Twins | 1060005 | CMCC | SP-241938 | TS 28.561 | WI
Management Architecture and Mechanisms | 6 | CMO | FS_Cloud_OAM | Study on cloud aspects of management and orchestration | 1020010 | CMCC | SP-241566 | TR 28.869 | SI
 | 8 | SBMA | SBMA_Ph3 | Service Based Management Architecture enhancement phase 3 | 1060006 | Huawei, Ericsson | SP-241939 | TS 28.533/… | WI
 | 9 | PTM | PlanM | Management of planned configurations | 1050032 | Nokia | SP-241379 | TS 28.572 | WI
 | 10 | MADCOL | MADCOL_Ph2 | Data Management phase 2 | 1020025 | Nokia | SP-250116 | TS 28.622 | WI
 | 11 | SREP | Data_SREP | Data management, regarding subscriptions and reporting | 1050033 | Ericsson | SP-241380 | 28.537/28.550/28.532/32.421/32.422/32.423/28.404/28.405/28.622/28.623 | WI
 | 12 | PM | PM_KPI_5G_Ph4 | 5G performance measurements and KPIs phase 4 (update WID for SA approval) | 1020026 | China Telecom, ZTE | SP-250511 | TS 28.552/554 | WI
 | 13 | AdNRM | AdNRM_Ph3 | 5G Advanced NRM features phase 3 | 1020027 | Nokia, Huawei | SP-250123 | TS 28.541/622 | WI
 | 14 | TMQ | TraceQoE_OAM | Subscriber and Equipment Trace and QoE collection management | 1020028 | Ericsson | SP-250115 | TS 32.422/405 | WI
 | 15 | NTNM | NTN_OAM_Ph2 | Management Aspects of NTN Phase 2 (update WID for SA approval) | 1060016 | China Unicom, CATT | SP-250514 | TS 28.541/552/554/658/662/540/530 | WI
 | 16 | IABM | NR_mobile_IAB_OAM | Management of IAB nodes | 1060015 | Ericsson | SP-241948 | TS 28.541/540/531/314/315 | WI
 | 17 | RedcapM | NR_RedCap_OAM | Management Aspects of RedCap features | 1060008 | China Unicom, Asiainfo | SP-241941 | TS 28.540/541/552/554 | WI
 | 18 | NWDAFM | NWDAF_OAM_Ph2 | Enhancement of Management Aspects related to NWDAF Phase 2 | 1050031 | China Telecom | SP-241378 | 28.552/28.541 | WI
 | 19 | NSM | NetShare_OAM_Ph3 | Management of Network Sharing Phase 3 | 1060017 | China Unicom, China Telecom | SP-241950 | TS 28.552/32.130/28.541 | WI
Support of New Services | 20 | EE | Energy_OAM_Ph3 | Energy efficiency and energy saving aspects of 5G networks and services | 1060007 | Huawei, Samsung | SP-241940 | TS 28.310/622/623/541/554/104 | WI
 | 21 | MExpo | Mexpo | Enhanced OAM for management service exposure to external consumers through CAPIF | 1060009 | Nokia | SP-241942 | TS 28.579 | WI
 | 22 | MonStra | Monstra-OAM | Management for MonStra | 1060012 | Vodafone, Ericsson | SP-241945 | TS 28.560 | WI
22 topics including: 14 OAM prime features and 8 OAM support to network features (in red background).
16 topics completed the study, 1 normative WI completed, 19 ongoing normative Wis, 1 ongoing study.

## Slide 11
Overview of Rel-19 CH topics
17 CH topics including: 2 CH prime feature (in white background) and 15 CH support to network features (in red background)
8 normative WIs in progress, 4 normative WIs and 4 SIs completed – marked in green color). 1 new normative WIs wait for SA approval.
 | Abbr. | Acronym | Title | UID | Rapp | Tdoc | TS/TR | Type
1 | CHSEG | CH_FSeg | WID on CHF Segmentation | 1040012 | Verizon | SP-250122 | TS 32.290/291 | WI
2 | SATCH | FS_5GSAT_Ph3_CH | SID on Charging aspects of satellite access Phase 3 | 1040014 | CATT | SP-240980 | TR 28.846 | SI
3 | CAPCH | FS_CAPIF_Ph2_CH | SID on Charging Aspects of CAPIF | 1040015 | Nokia | SP-240981 | TR 28.849 | SI
4 | RTCCH | FS_NG_RTC_Ph2_CH | SID on Charging aspects of next generation real time communication services phase 2 | 1040016 | CMCC | SP-240982 | TR 28.851 | SI
5 | UASCH | FS_UAS_Ph2_CH | SID on Charging aspects of Uncrewed Aerial Vehicle | 1040017 | CMCC | SP-240983 | TR 28.853 | SI
6 | RAGCH | Ranging_SL-CH | WID on Charging Aspects of Ranging and Sidelink Positioning | 1040013 | China Telecom | SP-241002 | TS 32.240/290/ 271/291/298 | WI
7 | EESCH | EnergySys-CH | WID on Charging Aspects for Energy Efficiency of network slice | 1040018 | Huawei | SP-250124 | TS 28.201/202 TS 32.240/291/298 | WI
8 | NSCH | NetShare-CH | WID on Charging enhancement for indirect network sharing | 1040019 | Ericsson | SP-241004 | TS 32.240/255/256 | WI
9 | PROCH | 5G_ProSe_Ph3-CH | WID on Charging Aspects for 5G ProSe Phase 3 | 1050030 | China Telecom | SP-241377 | TS 32.277/291/298 | WI
10 | SATCH | 5GSAT_Ph3-CH | WID on Charging aspects of satellite access Phase 3 | 1070014 | CATT | SP-250365 | TS32.240/251/255/257/260/291/298 | WI
11 | CAPCH | CH_CAPIF_EXT | WID on Charging aspects of CAPIF | 1070015 | Nokia | SP-250366 | TS32.240/254/291/298 | WI
12 | RTCCH | NG_RTC_Ph2-CH | WID on Charging aspects of next generation real time communication services phase 2 (update WID for SA approval) | 1070016 | CMCC | SP-250513 | TS32.254/255/260/291/298 | WI
13 | UASCH | UAS_Ph2-CH | WID on Charging for Uncrewed Aerial Systems Phase 2 (update WID for SA approval) | 1070017 | CMCC | SP-250512 | TS32.240/255/256/291/298 | WI
14 | LCSCH | CH_5G_eLCS_Ph3 | WID on Charging Aspects of 5GC LoCation Services | 1070019 | China Telecom | SP-250370 | TS32.271/290/291/298 | WI
15 | AIOCH | AmbientIoT-CH | WID on Charging for Ambient power-enabled Internet of Things | 1070018 | Huawei | SP-250369 | TS32.240/254/291/298 | WI
16 | CHNSH | CH_MOCN_NetShare | Charging aspects for Multi-Operator Core Network (MOCN) Network Sharing (update WID for SA approval) | 1070020 | Ericsson | SP-250510 | TS28.101/32.130/240/254/291/298 | WI
17 | CAPCCH | CAPIF_Ph3_con-CH | WID on Converged Charging Aspects of CAPIF Phase 3 (new WID for SA approval) | 10800xx | tbd | SP-250509 | TS 32.254/291/298 | WI

## Slide 12: Update of SA5 Rel-19 ongoing WI/SI progress
UID | Name | Acronym | Target date | Old % | Reference | New % | Change or comment
1060007 | Energy efficiency and energy saving aspects of 5G networks and services | Energy_OAM_Ph3 | 9/9/2025 | 20% | SP-241940 | 70% | 
1060011 | AI/ML Management Phase 2 | AIML_MGT_Ph2 | 9/9/2025 | 15% | SP-241944 | 52% | 
1070018 | Charging for Ambient power-enabled Internet of Things | AmbientIoT-CH | 9/9/2025 | 0% | SP-250369 | 100% | 
1060008 | Management Aspects of RedCap features | NR_RedCap_OAM | 9/9/2025 | 50% | SP-241941 | 90% | 
1060016 | Management Aspects of NTN Phase 2 | NTN_OAM_Ph2 | 6/6/2025 | 25% | SP-241949 | 100% | 
1070014 | Charging aspects of satellite access Phase 3 | 5GSAT_Ph3-CH | 6/6/2025 | 0% | SP-250365 | 90% | 
1060017 | Management of Network Sharing Phase 3 ?? | NetShare_OAM_Ph3 | 6/6/2025 | 50% | SP-241950 | 95% | 
1070015 | Charging aspects of CAPIF | CH_CAPIF_EXT | 9/9/2025 | 0% | SP-250366 | 70% | 
1060009 | Enhanced OAM for management service exposure to external consumers through CAPIF | MExpo | 9/9/2025 | 15% | SP-241942 | 80% | 
1040012 | CHF Segmentation | CHFSeg | 9/9/2025 | 60% | SP-250122 | 90% | 
1050033 | Data management regarding subscriptions and reporting | Data_SREP | 9/9/2025 | 0% | SP-241380 | 40% | 
1060012 | Management for MonStra | Monstra-OAM | 12/10/2024 | 80% | SP-241945 | 100% | 
1070016 | Charging aspects of next generation real time communication services phase 2 | NG_RTC_Ph2-CH | 9/9/2025 | 0% | SP-250367 | 70% | 
1070017 | Charging for Uncrewed Aerial Systems Phase 3 | UAS_Ph3-CH | 9/9/2025 | 0% | SP-250396 | 45% | Pending guidance from CT groups
1070020 | Charging aspects for Multi-Operator Core Network (MOCN) Network Sharing | CH_MOCN_NetShare | 9/9/2025 | 0% | SP-250371 | 75% | 
1060006 | Service Based Management Architecture enhancement phase 3 | SBMA_Ph3 | 9/9/2025 | 40% | SP-241939 | 90% | 
1060014 | Management Data Analytics phase 3 | eMDAS_Ph3 | 9/9/2025 | 30% | SP-241947 | 85% | 
1060013 | Intent driven management services for mobile network phase 3 | IDMS_MN_Ph3 | 6/6/2025 | 65% | SP-241946 | 100% | 
1060005 | Management aspects of Network Digital Twins | NDT | 9/9/2025 | 10% | SP-241938 | 95% | 
1020010 | Study on Cloud Aspects of Management and Orchestration | FS_Cloud_OAM | 9/9/2025 | 85% | SP-241566 | 90% | 
1050032 | Management of planned configurations | PlanM | 6/6/2025->9/9/2025 | 75% | SP-241379 | 75% | Target data to be updated.
1060010 | Closed Control Loop Management | CCLM | 9/9/2025 | 10% | SP-241943 | 80% | 
1020025 | Data management phase 2 | MADCOL_Ph2 | 6/6/2025->9/9/2025 | 88% | SP-250116 | 98% | Target data to be updated.
1020026 | 5G performance measurements and KPIs phase 4 | PM_KPI_5G_Ph4 | 12/30/2024->9/9/2025 | 75% | SP-241155 | 90% | Target data to be updated.
1020027 | 5G Advanced NRM features phase 3 | AdNRM_Ph3 | 6/6/2025 | 75% | SP-250123 | 100% | 
1020028 | Subscriber and Equipment Trace and QoE collection management | TraceQoE_OAM | 12/30/2024->9/9/2025 | 80% | SP-250115 | 80% | Target data to be updated.
1060015 | Management of IAB nodes | NR_MOBILE_IAB_OAM | 9/9/2025 | 0% | SP-241948 | 70% | 
1050031 | Enhancement of Management Aspects Related of NWDAF Phase 2 | NWDAF_OAM_Ph2 | 6/6/2025 | 65% | SP-241378 | 100% | 
1070019 | Charging aspects of 5GC LoCation Services | CH_5G_eLCS_Ph3 | 9/9/2025 | 0% | SP-250370 | 100% | 

## Slide 13
Acronym | OAM | CH
5GSAT_Ph3_ARCH | NTN_OAM_Ph2 (China Unicom/CATT) | 5GSAT_Ph3_CH (CATT)
NG_RTC_Ph2 | No need for extra OAM support | NG_RTC_Ph2_CH (CMCC)
XRMPh2 | PM_KPI_5G_Ph4(CMCC) Enhanced NRM/PM support Potential to be discussed in Rel-20 5GA (ZTE) | CH?? (CH indicated in SA2 WID)
MPS4msg | No need for extra OAM support | CH?? (CH indicated in SA2 WID)
VMR_Ph2 | AdNRM_Ph3(Samsung) (PM??) | CH?? (CH indicated in SA2 WID)
5G_ProSe_Ph3 | AdNRM_Ph3 (CATT) (PM??) | 5G_ProSe_Ph3_CH (China Telecom)
UIA_ARC | No need for extra OAM support | CH?? (CH indicated in SA2 WID)
eEDGE_5GC_Ph3 | No need for extra OAM Configuration support (PM??) | CH?? (CH indicated in SA2 WID)
UAS_Ph3 | No need for extra OAM support | UAS_Ph3_CH (CMCC)
UPEAS_Ph2 | NRM (ZTE) +PM?? | (CH indicated in SA2 WID) -> No need for extra CH support
5G_Femto | NRM/PM potential to be discussed in Rel-20 (DCM) | No need for extra CH support
MASSS | PM_KPI_5G_Ph4(ATSSS) OAM (NRM)?? | No need for extra CH support
AIML_CN | AIML_MGT_Ph2 (NEC/Intel) NWDAF_OAM_Ph2 (China Telecom) | Potential Rel-20 topic
EnergySys | Energy_OAM_Ph3 (Huawei) Mexpo (Nokia) | EnergySys_CH(Huawei)
TEI19_NetShare | NetShare_OAM_Ph3 (China Unicom) | NetShare_CH (Ericsson)
AmbientIoT | AdNRM_Ph3 (Huawei) PM (potential to be discussed in Rel-20) | AmbientIoT_CH (Huawei)
Summary of SA5 Rel-19 management support to SA2 features
The content of this slides is to be updated based on working progress, and to be finalized in SA#109
Feedback are welcome in NWM link: https://nwm-trial.etsi.org/#/documents/9140 : SA5 Rel-19 management support to SA2 features mapping table

## Slide 14
Acronym | OAM
NR_MIMO_Ph5-Core | No need for extra OAM support
Netw_Energy_NR_enh-Core | No need for extra OAM support
NR_AIML_air-Core | AIML_MGT_Ph2 (NEC/Intel)
NR_duplex_evo-Core | No need for extra OAM support
NR_LPWUS-Core | No need for extra OAM support
IoT_NTN_TDD-Core | No need for extra OAM support
NR_MC_enh2-Core | No need for extra OAM support
LTE_terr_bcast_Ph2-Core | No need for extra OAM support
Ambient_IoT_Solutions-Core | AdNRM_Ph3 (Huawei)
FS_NR_7_24GHz_CHmod | OAM (TBD)
FS_Sensing_NR | OAM (TBD)
FS_NR_AIML_Mob | AIML_MGT_Ph2 (NEC/intel)
NR_Mob_Ph4-Core | PM_KPI_5G_Ph4 AdNRM_Ph3
NR_NTN_Ph3-Core | NTN_OAM_Ph2
IoT_NTN_Ph3-Core | NTN_OAM_Ph2
NR_XR_Ph3-Core | No need for extra OAM support
LTE_TN_NR_NTN_mob-Core | NTN_OAM_Ph2
NR_SL_relay_multihop-Core | No need for extra OAM support
LCS_BDS_B2b_LTE_NR-Core | No need for extra OAM support
LCS_NAVIC_L1_SPS_NR_LTE-Core | No need for extra OAM support
NR_ENDC_SON_MDT_Ph4-Core | PM_KPI_5G_Ph4 AdNRM_Ph3 TraceQoE_OAM
NR_WAB_5GFemto | AdNRM_Ph3 (Huawei)
NR_AIML_NGRAN_enh-Core | AIML_MGT_Ph2 (Huawei) Energy_OAM_Ph3
Summary of SA5 Rel-19 management support to RAN1/2/3 features
RAN1
RAN2
RAN3
The content of this slides is to be updated based on working progress, and to be finalized in SA#109
Feedback are welcome in NWM link: https://nwm-trial.etsi.org/#/documents/9141:SA5 Rel-19 management support to RAN1/RAN2/RAN3 feature

## Slide 15
New Rel-20 Study / Work Items (for SA approval)
TDoc | Title | Type | UID | (Suggested) Acronym
SP-250496 | New SID Study on intent driven management services for mobile network phase 4 | SID new | 1080006 | FS_IDMS_MN_Ph4
SP-250502 | New Study on AI/ML management phase 3 | SID new | 1080012 | FS_AIML_MGT_Ph3
SP-250501 | New SID on Management aspect of Network Digital Twins phase 2 | SID new | 1080011 | FS_NDT_Ph2
SP-250498 | New SID on SBMA enhancement phase 4 | SID new | 1080008 | FS_SBMA_Ph4
SP-250495 | New SID on energy efficiency and energy saving aspects of 5G Advanced | SID new | 1080005 | FS_Energy-OAM_Ph4
SP-250497 | New SID on Study on Management Data Analytics (MDA) – Phase 4 | SID new | 1080007 | FS_eMDAS_Ph4
SP-250500 | New SID on Study for Data management phase 3 | SID new | 1080010 | FS_MADCOL_Ph3
SP-250499 | New SID on Enhanced exposure of management services | SID new | 1080009 | FS_EnExpo
SP-250503 | New SID on Closed Control Loop Management phase 2 | SID new | 1080013 | FS_CCLM_Ph2
SP-250508 | New WID on 5G Advanced NRM features phase 4 | WID new | 1080018 | AdNRM_Ph4
SP-250505 | New WID on 5G performance measurements&KPIs and Trace&MDT&QoE | WID new | 1080015 | PM_KPI_Trace_MDT_QoE-OAM
SP-250507 | New WID on Enhancement of Management Aspects related to NWDAF Phase 3 | WID new | 1080017 | NWDAF-OAM_Ph3
SP-250506 | New WID on OAM for Extended Reality and Media service (XRM) Phase 2 | WID new | 1080016 | XRM_Ph2-OAM
SP-250504 | New SID on Charging Aspects of CAPIF Phase 3 | SID new | 1080014 | FS_CAPIF_Ph3-CH
14 new Rel-20 topics sent for SA approval, including 9 OAM prime study items, 4 OAM support work items, 1 CH support study item

## Slide 16: Action from SA#107
Trial on a tool developed by MCC to identify OpenAPIs which are changed due to a change of a definition which is imported from a different TS/OpenAPI (ref: SP-241892 Status report of TSG CT#106 Slide 22)
  The following guidance has been added to SA5 working procedure:
    23.1.1b Using tools for OpenAPI YAML data type definition check
      Change of a data type definition may have potential impacts, for example, the definition may be imported by a different TS/OpenAPI. For contributions which intend to update the definition of the OpenAPI, the delegate is requested to generate the list of YAML files using the definition using the data type finder tool. The tool can be accessed via “Data Type Finder” link under “Tools” section in the following hyperlink https://forge.3gpp.org/rep/all/5G_APIs/-/blob/REL-19/README.md. This is to check the impact before making any update.
      Delegates are required to follow the procedure below:
      1) Check the related definitions with the data type finder tool (Accessed via “Data Type Finder” link under “Tools” section in the following hyperlink https://forge.3gpp.org/rep/all/5G_APIs/-/blob/REL-19/README.md).
      2) Add the list generated from the tool on the CR cover page (in other comments field) or to the rationale of the pCR.
Follow-up discussion of Selecting the Release for Charging/OAM aspects (ref: SP-250327 selecting the right Release for Charging aspects of a Feature)
  SA5#161 has discussed this topic and capture the discussion in tdoc S5-252826
  A proposal is submitted to SA#108 for further discussion in SA.

## Slide 17: SA5 Liaisons to SA
Tdoc | Reply To | Title | Doc-type | Source | To | Cc | Action from SA
SP-250432 |  | LS to SA for guidance of maintenance of specifications | LS in | SA5 | SA |  | SA5 asks SA for guidance on whether it is possible to reduce the number of CRs on old releases without violating the FASMO criteria.

## Slide 18: TRs / TSs to SA#108 for information/approval
Tdoc | Title | For
SP-250493 | Presentation of TS 28.561 Management and orchestration; Management aspects of Network Digital Twins to TSG SA for Information | For information
SP-250494 | Presentation of TS 28.579 Management and orchestration; Management services exposure to external consumers through CAPIF to TSG SA for Information | For information
2 TSs send to SA for information

## Slide 19: List of SA5 CR pack to SA#108
List of Rel-19 CRs:
SP-250516 CR pack on 5G_ProSe_Ph3_CH
SP-250517 CR pack on 5GMDT_Ph2
SP-250518 CR pack on 5GSAT_Ph3-CH
SP-250520 CR pack on AdNRM_Ph3
SP-250521 CR pack on AIML_MGT_Ph2
SP-250522 CR pack on AmbientIoT-CH
SP-250523 CR pack on CH_5G_eLCS_Ph3
SP-250524 CR pack on CH_CAPIF_EXT
SP-250525 CR pack on CH_MOCN_NetShare
SP-250526 CR pack on CHFSeg
SP-250527 CR pack on Data_SREP
SP-250528 CR pack on eMDAS_Ph3 (1/2)
SP-250529 CR pack on eMDAS_Ph3 (2/2)
SP-250530 CR pack on Energy_OAM_Ph3
SP-250532 CR pack on FS_CAPIF_Ph2_CH
SP-250533 CR pack on FS_NG_RTC_Ph2_CH
SP-250534 CR pack on FS_UAS_CH
SP-250536 CR pack on IDMS_MN_Ph3 (1/2)
SP-250537 CR pack on IDMS_MN_Ph3 (2/2)
SP-250538 CR pack on MADCOL_Ph2
SP-250539 CR pack on Monstra-OAM
SP-250540 CR pack on NetShare_CH
SP-250541 CR pack on NetShare_OAM_Ph3
SP-250542 CR pack on NG_RTC_Ph2-CH
SP-250543 CR pack on NR_MOBILE_IAB_OAM
SP-250544 CR pack on NR_RedCap_OAM
SP-250546 CR pack on NTN_OAM_Ph2
SP-250547 CR pack on NWDAF_OAM_Ph2
SP-250551 CR pack on PM_KPI_5G_Ph4
SP-250553 CR pack on SBMA_Ph3
SP-250558 CR pack on TEI19 (1/2)
SP-250559 CR pack on TEI19 (2/2)
SP-250560 CR pack on TraceQoE_OAM
SP-250561 CR pack on UAS_Ph3-CH
List of Rel-16/Rel-17/Rel-18 CRs:
SP-250515 CR pack on 5G_ProSe
SP-250519 CR pack on AdNRM_ph2
SP-250531 CR pack on eSBMA
SP-250535 CR pack on IDMS_MN_ph2
SP-250545 CR pack on NSOEU
SP-250548 CR pack on OAM_NPN_Ph2
SP-250549 CR pack on OAM_NTN
SP-250550 CR pack on PM_KPI_5G_Ph3
SP-250552 CR pack on RANSC
SP-250554 CR pack on TEI16 (1/2)
SP-250555 CR pack on TEI16 (2/2)
SP-250556 CR pack on TEI17
SP-250557 CR pack on TEI18

## Slide 20: Management and Orchestration

## Slide 21: 1. AIML：AI/ML management - phase 2
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020007 | Study on AI/ML management - phase 2 | FS_AIML_MGT_Ph2 | 12/12/2024 | 55% | SP-240965 | 100% | 
1060011 | AI/ML Management Phase 2 | AIML_MGT_Ph2 | 09/09/2025 | 15% | SP-241944 | 52% | 
OAM Prime feature
  Impacts and dependencies on other WGs:
  Collaboration with SA1 on AI/ML related requirements, SA2 on 5GC AIML, SA3 on AIML security, SA6 on Application enablement layer AIML and RAN WGs for related requirements.
  Next steps: The group plans to hold a number of conference calls in the lead-up to SA5#162 (August) to address these topics and accelerate progress. Agenda planning and logistical arrangements will be initiated by the rapporteur.
  Other Enhancements
    AI/ML capabilities management for RAN, 5GC, and MDA
  ML Model Delivery and Transfer
    Enhancements to ML model loading use case
  Topics Requiring Further Discussion
  Model confidence – use cases and solutions
  Sustainable AI/ML training and inference
  Coordination between ML capabilities
  Emulation use cases & solutions (NRMs)
  AI/ML prediction latency during training and inference
  Use cases and solutions for Explainability management in AI/ML training
  Solutions (NRMs) for Lifecycle Management in Federated Learning
  Procedures to support AI/ML capabilities
Progress since SA#107: The following topics were approved:
  Support of 5GC，the following contributions were agreed, and a liaison statement (LS) was sent to SA2:
    Enhancement of AIMLSupportedFunction to support inference in the LMF.
    Enhancement of the LMF NRM to support inference functionality.
  Explainability Management
    Explanation of inference outputs was introduced through new use cases and supported by NRM solutions.
  Model Lifecycle and Training Across Multiple Contexts
    Model training across contexts.
    Performance monitoring of Network Functions with ML trained models in live networks.
    Lifecycle clarifications and updates on transfer learning.
  ML Model Training Approaches
    Pre-specialised Training & Fine-tuning
      Use cases and requirements for fine-tuning were approved.
      Related terminology and NRM solutions were approved.
    Reinforcement Learning (RL)
      Use case enhancements and clarifications were approved, including complementary flow diagrams explaining the online and offline RL processes.
      NRM solutions for RL were agreed.
    Federated Learning (FL)
      Agreement on the NRM for FL could not be reached due to ongoing debate regarding the inclusion of energy-related attributes in the RL client selection criteria data type.
      Some proposals suggest deferring energy-related aspects to Rel-20.
      Further discussions are planned for the August meeting or through dedicated conference calls arranged by the rapporteurs.
    Distributed Training
      Solution allowing a consumer to suggest nodes which are involved in distributed training was approved.
    Knowledge-Based Transfer Learning

## Slide 22: 2. MDA：Management Data Analytics (MDA) – Phase 3
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020019 | Study on Management Data Analytics (MDA) Phase 3 | FS_eMDAS_Ph3 | 12/12/2024 | 90% | SP-241157 | 100% | 
1060014 | Management Data Analytics phase 3 | eMDAS_Ph3 | 09/09/2025 | 30% | SP-241947 | 85% | 
OAM Prime feature
Progress since SA#107:
  Data correlation analytics
    Adding new capability to perform analysis and provide recommendations related to data correlation.
    Enhancing the existing MDA capability for handover optimization analysis.
  ATSSS performance analytics
    Adding new capability to perform analysis and provide recommendations related to traffic steering.
  UE throughput analytics
    Adding new capability to perform analysis and provide recommendations related to traffic congestion.
  Fault management related analytics
    Adding new capability to perform analysis and provide report related to threshold crossing events.
    Adding new capability to perform analysis and provide recommendations related to service failure recovery.
    Enhancing the existing MDA capability for failure prediction.
  Software upgrade validation
    Adding new capability to perform analysis and provide recommendations related to validating a software upgrade.
  Control plane congestion analytics
    Enhancing the existing MDA capability for 5GC Control plane congestion analysis.
  Corrections to technical issues.
  Corrections to editorial issues.
  Improvements to stage 3 solution set.
  Impacts and dependencies on other WGs:
  Coordination with SA1 on service requirements, SA2 on NWDAF, RAN3 on data collection.
Next steps:
  Provide WT-1 use cases, requirements and solutions.

## Slide 23: 3. IDM: intent driven management services for mobile network phase 3
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020008 | Study on intent driven management services for mobile network phase 3 | FS_IDMS_MN_Ph3 | 12/12/2024 | 95% | SP-231737 | 100% | 
1060013 | Intent driven management services for mobile network phase 3 | IDMS_MN_Ph3 | 06/06/2025 | 65% | SP-241946 | 100% | 
OAM Prime feature
Progress since SA#107:
  New scenarios solution (including information model and openAPI definition), including:
    Enhance the RadioNetworkExpectation to support radio network support for UAV pre-flight preparation
    Enhance the RadioNetworkExpectation to support MOCN undifferentiated radio service in a specified area
    Enhance the RadioServiceExpectation to support radio service delivering and assurance for specific UE group and area
    Introduce the MaintenanceExpectation for network maintenance (e.g. network upgrade)
  New intent driven management functionalities(including information model and openAPI definition), including:
    Intent utility function to allow the consumer express preference for the intent fulfulment.
    Intent negotiation during fulfilment phase to enable the MnS producer and the MnS consumer to agree on the best way to fulfil an intent
    Procedures for intent exploration, intent fulfilment negotiation, intent feasibility check and implicit intent report subscription with customized requirements.
  Impacts and dependencies on other WGs:
  Provide radio network management support to SA1 on UAV pre-flight preparation requirements
Next steps:
  R19 IDMS_MN_Ph3 WI is completed.

## Slide 24: 4. CCL: closed control loop management
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020009 | Study on closed control loop management | FS_CCLM | 12/12/2024 | 90% | SP-231735 | 100% | 
1060010 | Closed Control Loop Management | CCLM | 09/09/2025 | 10% | SP-241943 | 80% | 
OAM Prime feature
Progress since SA#107:
  Agreed TS structure.
  Agreed UC and Requirements for Dynamic composition of CCL, Historical CCL, CCL performance management.
  Discussed basic NRM with considering backward compatibility. WG could not reach consensus. Discussion will continue
  The contributions were agreed on the functionality of conflict management, coordination management. No consensus reached on CCL having concept of Goals/Targets.
  Impacts and dependencies on other WGs:
  None
Next steps:
  Make progress on the remaining solutions. Finish the work in next meeting. WT will be removed if it will not be possible to finish them by next meeting

## Slide 25: 5. NDT: management aspects of Network Digital Twin
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020018 | Study on management aspects of Network Digital Twin | FS_NDT | 12/12/2024 | 95% | SP-231727 | 100% | 
1060005 | Management aspects of Network Digital Twins | NDT | 09/09/2025 | 10% | SP-241938 | 95% | 
OAM Prime feature
Progress since SA#107:
  WT-1: The terms and concepts of Network Digital Twin in the 3GPP management system are agreed, capabilities of NDT, deployment scenario of NDT function, and NDT life-cycle management were approved. The relationship between NDT and existing network automation functions needs more discussion.
  WT2: NDT UCs are categorized into 5 categories: Control and lifecycle Management, Network Automation, Verification, Data generation and Advanced NDT capabilities.
  WT3: The generic and use case specific solutions have been approved. These solutions are based on a new NDT management service and associated information model, including: NDT jobs, NDT functions, NDT reports, and supported NDT capabilities.
  Impacts and dependencies on other WGs:
  Coordination with SA1 on terminology.
Next steps:
  The relation with existing network automation functions need to reach the final consensus
  Stage 3 of NDT need to be complete based on the progress of Stage 2

## Slide 26: 6. CMO: Study on Cloud Aspects of Management and Orchestration
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020010 | Study on Cloud Aspects of Management and Orchestration | FS_Cloud_OAM | 12/12/2024 | 85% | SP-231781 | 90% | 
OAM Prime feature
Progress since SA#107:
  WT-1:
    Add another potential solution for cloud native VNF configuration to use the existing 3GPP MnS with vendor extension mechanism.
    Add an explanation of the relationship between VNF generic OAM functions and PaaS Services.
  WT2:
    Update the Annex related example implementations using management data streaming solution based on message bus and add evaluation for the data streaming use case.
    Add Annex related example implementation of LCM for NF Deployments using Kubernetes Custom Resource Definitions.
    Update the requirements and add potential solution for observability usecase.
  WT3:
    The solutions for different cloud deployment use case submitted at several meetings were not approved after many discussions, so add statement of there is no solution on that.
  General：
    Add a general summary conclusion on this TR, while some evaluations and recommendations are missing.
  Impacts and dependencies on other WGs:
  None
Next steps:
  Supplement the missing evaluations and conclusions for the TR 28.869.

## Slide 27: 7. MSEC: Study on Enablers for Security Monitoring
Progress since SA#107:
  None.
  Impacts and dependencies on other WGs:
  The events/use cases which can lead to security risks/threats and the related data that needs to be exposed need to be primarily defined by SA3
Next steps:
  This study is completed in SA#106, no normative Rel-19 work is planned so far.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020016 | Study on Enablers for Security Monitoring | FS_SECM | 12/12/2024 | 90% | SP-231736 | 100% | 
OAM Prime feature

## Slide 28: 8. SBMA: Service Based Management Architecture enhancement phase 3
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020011 | Study on Service Based Management Architecture enhancement phase 3 | FS_SBMA_Ph3 | 12/12/2024 | 75% | SP-231725 | 100% | 
1060006 | Service Based Management Architecture enhancement phase 3 | SBMA_Ph3 | 09/09/2025 | 40% | SP-241939 | 90% | 
OAM Prime feature
Progress since SA#107:
  The following topics were approved:
  Update table in annex E of TS 28.533 to capture the overall 5G management features, supporting management capabilities and related specification information
  Enhancing 3GPP TS 28.537 and 3GPP TS 28.622 to improve the overview information for each generic management capability
  Enhancing MnSInfo IOC to provide capabilities allowing MnS consumers to retrieve the MnS information for MnS instances based on specified areas
  Addition of definition of the common notification header
  Addition of entry point information for enhancing NRM TSs and PM TSs
  Addition of new notifications for reliability and description of reliable notification transfer to NtfSubscriptionControl
  Only use the "allowedValues" property if it represents a real restriction beyond the basic definition of a data type.
  The following topics need more discussion:
  WT-8: Addition of generic MnS version handling
  Impacts and dependencies on other WGs:
  None
Next steps:
  WT-8: Addition of generic MnS version handling.

## Slide 29: 9. PTM: Management of planned configurations
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020033 | Study on Management of planned configurations | FS_PlanM | 09/09/2024 | 60% | SP-231721 | 100% | 
1050032 | Management of planned configurations | PlanM | 09/09/2025 | 75% | SP-241379 | 75% | 
OAM Prime feature
Progress since SA#107:
  Improvements were agreed for stage 2 of:
  planned configurations.
  planned configuration groups.
  fallback configurations
  trigger conditions
  validating planned configurations.
  activating planned configurations.
  Many improvements were agreed for stage 2 information model
  New stage 3 examples were added
  Impacts and dependencies on other WGs:
  None
Next steps:
  Continue according to the plan

## Slide 30: 10. MADCOL: Data management phase 2
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020025 | Data management phase 2 | MADCOL_Ph2 | 06/06/2025 | 88% | SP-240877 | 98% | 
OAM Prime feature
Progress since SA#107:
  Add use cases description for “ExternalDataType” to support external management data, and “ExternalDataType” changes from a data type to an IOC to express the interface configuration more appropriately
  Add Management data information in usage of MnS Registry for different deployment scenarios
  Add solution description including Stage 2 definition and Stage 3 definition for discovery of management data
  Impacts and dependencies on other WGs:
  None
Next steps:
  continue according to the plan.

## Slide 31: 11. SREP: Data management regarding subscriptions and reporting
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020012 | Study on data management regarding subscriptions and reporting | FS_Data_SREP | 09/09/2024 | 60% | SP-231732 | 100% | 
1050033 | Data management regarding subscriptions and reporting | Data_SREP | 09/09/2025 | 0% | SP-241380 | 40% | 
OAM Prime feature
Progress since SA#107:
  The following topics need more discussion:
  QoE Reference Uniqueness
  Trace Reference Uniqueness
  Trace/MDT and QoE uniqueness solutions were agreed.
  Failure notification solution was agreed for QoE, but not for Trace/MDT.
  Impacts and dependencies on other WGs:
  None
Next steps:
  Continue as plan

## Slide 32: 12. PM: 5G performance measurements and KPIs phase 4
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020026 | 5G performance measurements and KPIs phase 4 | PM_KPI_5G_Ph4 | 06/06/2025 | 75% | SP-241155 | 90% | 
OAM Support to Network features
Progress since SA#107:
  WT-1 (Rel19 PM/KPI):
    Update number of active UEs related measurements in TS 28.552 (agreed)
    Add average DL PDU set delay for XR measurement in TS 28.552 (not pursued)
    Measurements related to LTM cell-switch in TS 28.552 (not pursued)
    Measurements related to LTM cell-switch with almost invalid TA in TS 28.552 (not pursued)
    Add measurement of coverage ratio in TS 28.554 (not pursued)
  WT-2 (Rel18 PM/KPI):
    PM Counter Metadata in TS 32.404 and Performance Measurement Method in TS 28.552 (not pursued)
    correction on paging record measurement in TS 28.552 (agreed)
    DRB measurement with filter in TS 28.552 (agreed)
    JobID delimiters in TS 28.532(agreed)
    PM Counter Metadata in TS 32.401 and TS 32.404 (not pursued)
    PM File extension in TS 28.532 (agreed)
  WT-3 UE level measurements:
    Fix UE level measurements unit in TS 28.558 (agreed)
    Enhance the Example of 5GC UE level measurements in TS 32.432(agreed)
    Correct the misaligned 5GC UE level measurement procedure in TS 28.558 (agreed)
  Impacts and dependencies on other WGs:
  Potential coordination: providing performance measurements to network features defined in SA2, RAN2 and RAN3.
Next steps:
  Continue the work per the new plan.

## Slide 33: 13. AdNRM: 5G Advanced NRM features phase 3
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020027 | 5G Advanced NRM features phase 3 | AdNRM_Ph3 | 06/06/2025 | 75% | SP-240875 | 100% | 
OAM Support to Network features
Progress since SA#107:
  The following topics are discussed and approved:
  WT-1 (5GC NRM):
    Enhancements on NFProfile
    Enhancement to 5GC NF Provisioning
    NRM enhancements on ManagedNFProfile and NFService.
    Management support for AIoT (CN aspects)
      Add AIOTF and ADM IOC to support management of Ambient IoT
      Add EP_AIOT NRMs to support AIOT
  WT-2 (NR NRM):
    Management support for AIoT (RAN aspects)
      Discussion paper on basic configuration management to support AIOT in Deployment Scenario 1 and Topology 1 (BS↔ Ambient IoT device) was endorsed
      Add AIOT reader IOC to support NG-RAN AIOT feature management
    Enhancement to naming convention for NR NRM
    Enhance description of WAB-gNB management
    Add UPF capabilities configuration
  WT-3 (Slice NRM enhancement):
    Solution agnostic request for service provisioning
  Impacts and dependencies on other WGs:
  Potential coordination: providing network resource model for network features defined in SA2, CT4, RAN3 and RAN4.
Next steps:
  This work item is completed.

## Slide 34: 14. TMQ: Subscriber and Equipment Trace and QoE collection management
Progress since SA#107:
  Enhancement on Trace Record Header
  Impacts and dependencies on other WGs:
  SA2, SA4, CT1, CT4, RAN2 and RAN3.
  RAN has proposals for work that might impact Trace, MDT and QoE in RP-232624.
  Studies in SA2 might impact Trace, MDT and QoE in Rel-19.
  If Signalling Based Activation is affected, CT4, RAN2 and RAN3 are affected.
Next steps:
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020028 | Subscriber and Equipment Trace and QoE collection management | TraceQoE_OAM | 06/06/2025 | 80% | SP-231748 | 80% | 
OAM Support to Network features

## Slide 35: 15. NTNM: Management Aspects of NTN Phase 2
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020013 | Study on Management Aspects of NTN Phase 2 | FS_NTN_OAM_Ph2 | 12/12/2024 | 90% | SP-231733 | 100% | 
1060016 | Management Aspects of NTN Phase 2 | NTN_OAM_Ph2 | 06/06/2025 | 25% | SP-241949 | 100% | 
OAM Support to Network features
Progress since SA#107:
  WT-1:
  CRs on adding requirements and solutions for configuring AMF with TAIs supported by NTN gNB is endorsed. Related CRs may be submitted depends on the agreement between SA2 and RAN3.
  Adding NTN time-based configuration support
  Adding NTN regenerative concepts and requirements.
  WT-2:
  Adding requirements and solutions to support broadcast multiple TACs for NTN.
  WT-3:
  Adding requirements and solutions to support S&F satellite operation
  WT-5:
  Adding requirements and solutions for managing NTN secure backhaul, enhances the existing N2 IP configuration with time-based OAM solution
  Impacts and dependencies on other WGs:
  Co-ordination with SA2, RAN2, RAN3 where appropriate.
Next steps:
  No.

## Slide 36: 16. IABM: management of IAB nodes
Progress since SA#107:
  Requirements for IAB-node configuration
  Use case IAB-node configuration.
  Impacts and dependencies on other WGs:
  Collaboration with SA2 on architecture enhancements, SA3 on security and RAN3 on NR Mobile IAB
Next steps:
  Submit contributions for WT-2 supporting IAB-node configuration: procedure
  Submit NRM impact to support both IAB-node configuration and IAB-node OAM connectivity
  Submit NRM impact to support NCI reconfiguration by IAB-donor-CU in case of NCI collision
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020014 | Study on management of IAB nodes | FS_NR_mobile_IAB_OAM | 12/12/2024 | 90% | SP-231729 | 100% | 
1060015 | Management of IAB nodes | NR_MOBILE_IAB_OAM | 09/09/2025 | 0% | SP-241948 | 70% | 
OAM Support to Network features

## Slide 37: 17. RedcapM: management aspects of RedCap feature
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020017 | Study on management aspects of RedCap feature | FS_NR_RedCap_OAM | 12/12/2024 | 75% | SP-231734 | 100% | 
1060008 | Management Aspects of RedCap features | NR_RedCap_OAM | 09/09/2025 | 50% | SP-241941 | 90% | 
OAM Support to Network features
Progress since SA#107:
  WT-1:
  CRs on adding solutions for RedCap UE access control is discussed.
  WT-2:
  CRs on enhancing measurements for RedCap feature are discussed.
  Impacts and dependencies on other WGs:
  RAN1 on RedCap related requirements and Physical layer methods
  SA2 on 5GC RedCap related NF services and configurations.
Next steps:
  The remaining NRM considerations and PM aspects associated with the RedCap feature are scheduled for discussion at the upcoming meeting.

## Slide 38: 18. NWDAFM: Enhancement of Management Aspects related to NWDAF Phase 2
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020020 | Study on Enhancement of Management Aspects related to NWDAF Phase 2 | FS_NWDAF_OAM_Ph2 | 09/09/2024 | 75% | SP-231724 | 100% | 
1050031 | Enhancement of Management Aspects Related of NWDAF Phase 2 | NWDAF_OAM_Ph2 | 06/06/2025 | 65% | SP-241378 | 100% | 
OAM Support to Network features
Progress since SA#107:
  Provide summary for the achievement of this work item:
    Management enhancement for NWDAFs deployed in the roaming scenarios. This work item enhances configuration management to support Roaming Exchange Capability. It also specifies performance measurements for NWDAFs with this capability, based on key metrics such as the number of service requests, responses, subscriptions, and notifications.
    Management enhancement related to NWDAF Data Collection. This work item defines performance metrics that reflect the volume of data collected by NWDAF and outlines efficiency measurements for data collection. More specifically, these efficiency measurements consider the relationship between the amount of data collected and the associated transmission overhead, as well as the time required for data transmission.
  Impacts and dependencies on other WGs:
  Collaboration with SA2 on NWDAF.
Next steps:
  This work item is completed.

## Slide 39: 19. NSM: Management of Network Sharing Phase3
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020015 | Study on Management of Network Sharing Phase3 | FS_NetShare_OAM_Ph3 | 12/12/2024 | 90% | SP-240966 | 100% | 
1060017 | Management of Network Sharing Phase 3 ?? | NetShare_OAM_Ph3 | 06/06/2025 | 50% | SP-241950 | 95% | 
OAM Support to Network features
Progress since SA#107:
  Add PLMN granularity performance measurement of UDM, PDU session for SMF, and initial registration for AMF in the Indirect Network Sharing Scenario are agreed.
  Add PLMN granularity performance measurement of UDM in the Indirect Network Sharing Scenario is agreed.
  Add figures of Indirect Network Sharing is agreed.
  Enhancements for deployment example of Service-based Management Architecture for MOCN are agreed
  Clarify MOCN and GWCN scenarios description is agreed.
  Requirements for management of Indirect Network Sharing is agreed.
  Categorize requirements for the management support for Indirect Network Sharing scenario is agreed
  Separate business-level requirements from specification-level requirements is agreed
  Update abbreviations for Indirect Network Sharing
  Add solution to support RAN configurations for Indirect Network Sharing is agreed
  Add PLMN granularity performance measurement requirements for Indirect Network Sharing is agreed
  Impacts and dependencies on other WGs:
  SA1 and SA2
Next steps:
  More PLMN-granularity performance measurements of CN functions are planned to discuss.

## Slide 40: 20. EE: energy efficiency and energy saving aspects of 5G networks and services
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020021 | Study on energy efficiency and energy saving aspects of 5G networks and services | FS_Energy_OAM_Ph3 | 12/12/2024 | 60% | SP-231723 | 100% | 
1060007 | Energy efficiency and energy saving aspects of 5G networks and services | Energy_OAM_Ph3 | 09/09/2025 | 20% | SP-241940 | 70% | 
OAM Prime feature
Progress since SA#107:
  The following update are agreed
    Modelling energy supply, carbon emission and renewable energy information
    Add Carbon emission KPI definition
    Add new EE KPIs with consideration of network availability and network quality performance dimension
  The following topics need more discussion
    Solution for multi-carrier RAN Energy saving
    MDA assisted Energy Saving for handling of power shortage scenario
    VNF energy consumption measurements
  Impacts and dependencies on other WGs:
  The following WGs address aspects related to this study:
    SA1 and SA2, for aspects described in WT-2 and WT-5
    RAN1, RAN2 and RAN3, for aspects described in WT-3 and WT-5.
Next steps:
  The remaining solutions for other work tasks i.e. WT -1 , WT-8 to be discussed in next meetings.

## Slide 41: 21. Mexpo: Enhanced OAM for management exposure to external consumers
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020022 | Study on Enhanced OAM for management exposure to external consumers | FS_MExpo | 12/12/2024 | 60% | SP-240967 | 100% | 
1060009 | Enhanced OAM for management service exposure to external consumers through CAPIF | MExpo | 09/09/2025 | 15% | SP-241942 | 80% | 
OAM Prime feature
Progress since SA#107:
  The following topics were approved:
    Add introduction content
    Adding MSED deployment options
    Use case definition, requirements and solution for registration of MSED into the CCF.
    Use case requirements and solution for publishing management services to the CCF.
    Use case requirements and solution for logging management service API invocation s to the CCF.
  The following topics were discussed but there was no agreement:
    Adding use case definition and requirements for authorizing external MnS consumers at the CCF to consume management services
    Adding use case solution for authorizing external MnS consumers at the CCF to consume management services.
  Impacts and dependencies on other WGs:
  Solutions proposed for identified use cases build upon R18 CAPIF features. Rel-18 CRs approved by SA6 (CAPIF stage-2), CT3 (CAPIF stage-3) and SA3 (CAPIF related security aspects) may impact these solutions; coordination will be required in such cases.
Next steps:
  Use case definition, requirement and solution for the authorization of external MnS consumers at the CCF

## Slide 42: 22. MonstraM: Management for MonStra
Progress since SA#107:
  Clean up of editor’s notes
  Improvements of parametrization of solutions
  Impacts and dependencies on other WGs:
  None.
Next steps:
  Potential editorial improvements
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1060012 | Management for MonStra | Monstra-OAM | 12/12/2024 | 80% | S5-245981 | 100% | 
OAM Prime feature

## Slide 43: Charging SWG

## Slide 44
SA5 SWG registration
  Increased number of companies registered to present mobile/satellite operators and mobile communication vendors interests
  Quite stable number of participating and active delegates complemented by remote participations
Charging Work progress on Rel-19
  Several Rel-19 WIDs has been completed, three revised and one (mini-)WIDs for approval
  completion preparation with two CH rapporteur calls
Charging Work for Rel-20 started
  One CH prime and one CH network support topic running via NWM for consolidation
6G Charging work initiated
  CH group discussed shared view on 6G charging evolution in respect of improvements on
    Charging Architecture for 6G
    new granularity of the collection for service usage Data Management
General information

## Slide 45: Charging (CH) WIs/SIs

## Slide 46: 1. CHSEG: WID on CHF Segmentation
CH Prime feature
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1040012 | CHF Segmentation | CHFSeg | 12/09/2025 | 60 % | SP-241001 | 90 % | 
Progress since SA#107
4 CRs agreed covering stage 2 and stage 3aspects:
  Clarify the CHF selection method for AMF (TS 32.256) and SMF (TS 32.255)
  Addition of charging characteristics (TS 32.274)
  Addition of domain features (TS 32.291)
RAN impacts and dependencies:
  None identified
Next steps:
  Final check of the stage 3 work

## Slide 47: 2. PROCH: WID on Charging Aspects for 5G ProSe Ph3
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1050030 | New WID on Charging Aspects for 5G ProSe Ph3 | 5G_ProSe_Ph3_CH | 12/09/2025 | 25 % | SP-241377 | 75 % | 
CH Support to Network features
Progress since SA#107
  4 CRs agreed covering stage 2 and stage 3 aspects:
    TS 32.277: Add information flows and information elements to support layer-3 ProSe UE-to-UE relay communication
    TS 32.291: Add layer 3 multi-hop ProSe UE-to-Network relay communication related attributes
    TS 32.298: Add layer 3 multi-hop ProSe UE-to-Network relay communication related CDR parameter
RAN impacts and dependencies:
  None identified
Next steps:
  Complete parameter description

## Slide 48: 3. SATCH: Charging aspects of satellite access Phase 3
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1040014 | Study on charging aspects of satellite access Phase 3 | FS_5GSAT_Ph3_CH | 03/03/2025 | 75 % | SP-240980 | 100 % | completed
1070014 | Charging aspects of satellite access Phase 3 | 5GSAT_Ph3-CH | 12/09/2025 | 0 % | SP-250365 | 90 % | 
Progress since SA#107
  18 CRs agreed covering stage 2 and stage 3 aspects:
    32.240: Introduce the support of store and forward satellite operation and UE-satellite-UE communication and Update Charging principles and architecture references for MVNOs charging, Add MVNO charging which provides satellite service
    32.251: Charging principle for store and forward satellite operation, Charging information for store and forward satellite operation of SMS service, Charging trigger and information for store and forward satellite operation with UP CIoT
    32.255: Addition of the Satellite Roaming Charging Principle, satellite backhaul category and MVNO charging
    32.256: Add MVNO charging which provides satellite access service
    32.260: Charging principle, trigger and charging information for UE-satellite-UE communication and Update charging principle for satellite change case
    32.291: Add Data Type and Open API for UE-satellite-UE charging
    32.298: Add Store&Forward charging information in the SMSChargingDataTypes, Add Satellite ID in the CHFChargingDataTypes and IMSChargingData Typels
RAN impacts and dependencies:
  None identified
Next steps:
  Final check of the stage 3 work
CH Support to Network features

## Slide 49: 4. CAPCH: Charging aspects of CAPIF
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1040015 | SID on Charging Aspects of CAPIF | FS_CAPIF_Ph2_CH | 03/03/2025 | 75 % | SP-240981 | 100 % | completed
1070015 | Charging aspects of CAPIF | CH_CAPIF_EXT | 12/09/2025 | 0 % | SP-250366 | 70 % | 
Progress since SA#107
14 CRs agreed covering stage 2 and stage 3 aspects:
  TS 32.240: CAPIF Logical Charging Architecture and CAPIF Service Charging
  TS 32.254: Addition of charging architecture for CAPIF charging principles, CAPIF support, CAPIF triggers, CAPIF Message Flows (PEC) and CAPIF specific charging information
  TS 32.254: CAPIF Exposure API Function (Tenant Identifier availability) and CAPIF API Invoker Charging Flow
  TS 32.291: CAPIF Service, CAPIF Attribute and CAPIF EnumerationValue
RAN impacts and dependencies:
  None identified
Next steps:
  Finalize the stage 3 work
CH Support to Network features

## Slide 50: 5. RTCCH: Charging aspects of next generation real time communication services phase 2
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1040016 | SID on Charging aspects of next generation real time communication services phase 2 | FS_NG_RTC_Ph2_CH | 03/03/2025 | 75 % | SP-240982 | 100 % | completed
1070016 | Charging aspects of next generation real time communication services phase 2 | NG_RTC_Ph2-CH | 12/09/2025 | 40 % | SP-250513 (SP-250367) | 70 % | Revised WID for SA approval
Progress since SA#107
12 CRs agreed covering stage 2 and stage 3 aspects:
  TS 32.255: Add volume-based charging for standalone IMS data channel, principle for DC application download & usage and to support IMS DC as a PS Data Off Exempt Service
  TS 32.260: Charging principle and information for Avatar communication charging and add duration-based charging for standalone IMS data channel and DC application usages
  TS 32.254: Add charging principle for IMS network capabilities exposure
  TS 32.291, TS 32.298: Add charging information for IMS DC application download
RAN impacts and dependencies:
  None identified
Next steps:
  Complete message flow and parameter definitions
CH Support to Network features

## Slide 51: 6. UASCH: Charging for Uncrewed Aerial Systems Phase 3
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1040017 | SID on Charging aspects of Uncrewed Aerial Vehicle | FS_UAS_PH2_CH | 03/03/2025 | 75 % | SP-240983 | 100 % | completed
1070017 | Charging for Uncrewed Aerial Systems Phase 3 | UAS_Ph3-CH | 12/09/2025 | 5 % | SP-250512 (SP-250396) | 45 % | Revised WID for SA approval
Progress since SA#107/SA5#160
  3 CRs agreed covering stage 2 aspects:
  TS 32.240: Add charging principles for UAS charging
  TS 32.255: Add UAS charging requirements for SMF
  TS 32.256: Add UAS charging requirements for AMF
RAN impacts and dependencies:
  None identified
Next steps:
  Definition of UE type identification for the stage 2 and stage 3 work completion based on LS exchange with CT WGs
CH Support to Network features

## Slide 52: 7. LCSCH: WID on Charging Aspects of 5GC LoCation Services
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1070019 | WID on Charging Aspects of 5GC LoCation Services | 5G_eLCS_CH | 12/09/2025 | 0 % | SP-250125 | 100% | completed
CH Support to Network features
Progress since SA#107
7 CRs agreed covering stage2 aspects in TS 32.271:
  Extend the scope and charging architecture to support 5G LCS converged charging and aaddition of LCS architecture
  Extend basic principles, CDR generation and handling for 5G LCS converged charging
  Add message flow of converged charging for 5GC-MT-LR and 5GC-MO-LR
  Extend data description, charging information and bindings for 5G LCS converged charging
  4 CRs agreed covering stage 3 aspects in TS 32.291 and TS 32.298:
  Extend Data Type/CHF-CDR for 5G LCS converged charging
  Introduce OpenAPI extension and add charging information to CDR for 5GS LCS
RAN impacts and dependencies:
  None identified
Next steps:
  Work item is completed

## Slide 53: 8.AIoTCH: WID on Charging for Ambient power-enabled Internet of Things
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1070018 | WID on Charging for Ambient power-enabled Internet of Things | AmbientIoT_CH | 12/09/2025 | 0 % | SP-250121 | 100% | completed
CH Support to Network features
Progress since SA#107
2 CRs agreed covering stage2 aspects:
  TS 32.240, TS 32.254: Add charging support for AIoT service
2 CRs agreed covering stage 3 aspects in TS 32.291 and TS 32.298:
  Add charging support for AIoT service
RAN impacts and dependencies:
  None identified
Next steps:
  Work item is completed

## Slide 54: 9. CHNS: WID on Charging enhancement for MOCN network sharing
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1070020 | WID on Charging enhancement for MOCN network sharing | CHNetShare | 12/09/2025 | 0 % | SP-250510 (SP-250126) | 75% | Revised WID for SA approval
CH Prime feature
Progress since SA#107
10 CRs agreed covering stage 2 aspects:
  TS 32.240: Introduction of MOCN network sharing
  TS 32.255: Addition of charging requirements, principles and architecture for MOCN
  TS 28.201 : Introduction of charging requirements and architecture for MOCN and addition of message flows and charging information for MOCN
RAN impacts and dependencies:
  Not known
Next steps:
  Complete the stage 3 work

## Slide 55: Thank you!

## Slide 56: General information (time plan/meeting plan/forge)

## Slide 57: 3GPP SA & SA5 meeting calendar (2025)
Meeting info | DateTime | Location | Release dates | Other WGs (potential colocation)
SA5#159 | 17 Feb 2025- 21 Feb 2025 | Sophia Antipolis, FR | 5GA SA5 workshop | 
SA#107 | 10 Mar 2025- 14 Mar 2025 | Incheon, South Korea | 6G workshop | 
SA5#160 | 07 Apr 2025- 11 Apr 2025 | Goteborg, SE |  | SA2/3/4/5/6
SA5#161 | 19 May 2025- 23 May 2025 | Fukuoka, Japan |  | SA WGs
SA#108 | 09 Jun 2025- 13 Jun 2025 | Prague, Czech Republic |  | 
SA5#162 | 25 Aug 2025- 29 Aug 2025 | Goteborg, SE |  | SA WGs/CT WGs
SA#109 | 15 Sep 2025- 19 Sep 2025 | China | Rel-19 freeze | 
SA5#163 | 13 Oct 2025- 17 Oct 2025 | China |  | SA2/3/4/5/6 and CT1/3/4 WGs
SA5#164 | 17 Nov 2025- 21 Nov 2025 | DALLAS, TEXAS |  | CT WGs, SA WGs, RAN WGs
SA#110 | 08 Dec 2025- 12 Dec 2025 | BALTIMORE, MARYLAND |  | 
6 f2f SA5 meeting planned in 2025
This slide is only for information, please book your hotel/flight after you received official meeting invitation

## Slide 58
6 f2f SA5 meeting planned in 2026, SA5 meetings to be collocated with other SA WG as much as possible.
This slide is only for information, please book your hotel/flight after you received official meeting invitation
Reference: confirmed tdoc from MHPG
Meeting info | DateTime | Location | Release dates | Other WGs (potential colocation)
SA5#165 | 9 Feb 2026 - 13 Feb 2026 | India |  | 
SA#111 | 9 Mar 2026 - 13 Mar 2026 | Japan |  | 
SA5#166 | 13 Apr 2026 - 17 Apr 2026 | Europe |  | 
SA5#167 | 18 May 2026 - 22 May 2026 | China |  | 
SA#112 | 08 Jun 2026 - 12 Jun 2026 | Singapore |  | 
SA5#168 | 24 Aug 2026 - 28 Aug 2026 | Europe |  | 
SA#113 | 14 Sep 2026 - 18 Sep 2026 | Madrid |  | 
SA5#169 | 12 Oct 2026 - 16 Oct 2026 | Prague |  | 
SA5#170 | 16 Nov 2026 - 20 Nov 2026 | North America |  | 
SA#114 | 07 Dec 2026 - 11 Dec 2026 | North America |  | 
3GPP SA & SA5 meeting calendar (2026)

## Slide 59: Joint meeting 2025
Meeting info | DateTime | Location | Planned topics
Joint meeting with ETSI ISG ZSM | Planned 3rd July 2025 13:00 UTC - 15:00 UTC | online | Management of Network Digital Twin (20 min) AI/ML management (20 min) Intent-driven Management Services (20 min) Autonomous Agents (20 min) ZSM PoCs (20 min) Open discussion (15 min)
Joint meeting with ETSI ISG NFV | Planned in September,2025 | online | TBD

## Slide 60: Rel-19 SA5 Summary Information in forge
SA5 Rel-19 ongoing topics
  Details of SA5 Rel-19 approved WIDs/SIDs : https://forge.3gpp.org/rep/sa5/MnS/-/wikis/SA5/Rel-19-Moderated-Topics
Stage 3 forge links: https://forge.3gpp.org/rep/sa5/MnS
  Management and Orchestration APIs:
    OpenAPI solution is captured in https://forge.3gpp.org/rep/all/5G_APIs (3GPP unified stage3 repository) and https://forge.3gpp.org/rep/sa5/MnS/-/tree/Rel-19/OpenAPI (SA5 stage3 repository)
    YANG solution is captured in https://forge.3gpp.org/rep/sa5/MnS/-/tree/Rel-19/yang-models (SA5 stage3 repository)
    Balazs Lengyel (Ericsson) as YANG Code moderator
    Sean Sun (Nokia) and Ruiyue Xu (Huawei) as YAML Code moderator
  Charging APIs:
    OpenAPI solution to be captured in https://forge.3gpp.org/rep/all/5G_APIs (3GPP unified stage3 repository) and https://forge.3gpp.org/rep/sa5/CH/-/tree/Rel-19/OpenAPI (SA5 stage3 repository)
      Chen Shan (Huawei) as Charging YAML Code moderator
    ASN.1 solution to be captured in https://forge.3gpp.org/rep/sa5/CH/-/tree/Rel-19/ (SA5 stage3 repository)
      Robert Törnkvist (Ericsson) as Charging ASN.1 Code moderator
  Stage 3 forge is supported by SA5 MCC and Miguel Angel Reina Ortega (ETSI) as code master.

## Slide 61: TU planning
Latest TU planning is captured in https://www.3gpp.org/ftp/Email_Discussions/SA5/SA5-level%20discussions/SA5%23157

## Slide 62: SA5 calendar with OAM TU (one track)
Time | Monday | Tuesday | Wednesday | Thursday | Friday (Closing plenary)
Q0 (If needed) |  | Breakout (opt.) | Breakout (opt.) | Breakout (opt.) | Closing plenary Start at 8:30am (may change depends on the host restriction)
Q1 (9:00 - 10:30) | Plenary Session#1 (1TU) [Single Stream] | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Closing plenary
10:30 - 11:00 | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break
Q2 (11:00 - 12:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Closing plenary
12:30 - 14:00 | Lunch | Lunch | Lunch | Lunch | Lunch
Q3 (14:00 - 15:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Closing plenary
15:30 - 16:00 | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break
Q4 (16:00 - 17:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Revision session | Closing plenary
17:30 - 17:40 | Break | Break | Break | Break | Break
Q5 (17:40 – 19:10) | Stream#1 (1TU) | Stream#1 (0.5 TU) Stop around 18:45 Social evening | Stream#1 (1TU) | Revision session | 
Assumption: Every day = 5 sessions (TUs), total TU in 1 ordinary meeting (exclude closing plenary TUs) = 18.5 TUs

## Slide 63: Rel-19 TU Budget for SA5 OAM
Assumptions for SA5 OAM :
  6 ordinary meeting per year.
  Rel-19 spans 21 months for SA5 (with early start of studies) = 10 meetings
  1 Session = 1.5 hour time window
  Max 5 sessions per meeting day
  1 Stream = 1 TU (Time Unit)
  1 TU is time (i.e., 1.5 hours) spent to discuss/handle technical contributions.
  Revisions/Drafting/offline conference call are not counted for the TU estimates.
  OAM revision sessions normally planned to be in Thursday Q4 and Q5 (initial assump.)
  1 parallel (OAM) stream per session => 18.5 TUs per meeting (incl. 2 TUs as buffer) = 185
  Assume Maintenance + Buffer = 33% => ~ 61 TU
  Resulting total TUs avail. f. SI/WI: 10 meetings x 18.5 sessions = 185 TU minus 61 => 124 TU
  With 20 SI/WI => Average 6 TU per SI/WI (0.6/meeting).
No update since SA#104

## Slide 64: SA5 Rel-19 OAM TU planning (Jan.2024~Sep.2025)
 | Maintenance+R18 | R19 | R20 preparation | Buffer (revision session)
Jan.2024~Mar.2024 SA5#153 (1 meeting) (Last meeting for Rel-18) | 1.5 TU (CR)+13 TU (Rel-18)=14.5 TU | 2 TU | NA | 2 TU
Apr. 2024~Dec.2024: SA5#154~#158 (5 meetings) | 2.5 TU*5 meetings = 12.5 TU (CRs) | 14 TU*5 meetings= 70 TU | NA | 2 TU*5=10 TU
Jan.2025~Sep.2025: SA5#159~#162 (4 meetings) | 1.5 TU*4 meetings= 6 TU (CRs) | 13 TU*4 meetings= 52 TU | 2 TU*4 meetings = 8 TU | 2 TU*4=8 TU
Total=185 TU | 33 TU | 124 TU | 8 TU | 20 TU
Assumptions:
Every meeting day = 5 quarters (= 5 TUs)
Total TUs per meeting = 18.5 TUs
  Buffer = 2 TUs
  OAM = 16.5 TUs
    Maintenance CRs + remaining Rel-18 work (TU allocation will decrease over time )
    Rel-20 preparation work (TU allocation will be zero at the beginning and will increase over time )
    All remaining time is available for Rel-19 SIDs / WIDs
Total TUs allocated to Rel-19 SIDs / WIDs = 120 TUs, implying:
  12 TUs allocated to Rel-19 SIDs / WIDs per meeting (= 120 TUs / 10 meetings)
  6 TUs allocated to each Rel-19 SID / WID in average (= 120 TUs / 20 Rel-19 SIDs/WIDs)
  0.6 TU allocated per Rel-19 SID / WID per meeting in average (= 12 TUs / 20 Rel-19 SIDs/WIDs)
No update since SA#104

## Slide 65: SA5 calendar with CH TU (one track)
Time | Monday | Tuesday | Wednesday | Thursday | Friday (Closing plenary)
Q0 (If needed) |  | Breakout (opt.) | Breakout (opt.) |  | Closing plenary Start at 8:30am (may change depends on the host restriction)
Q1 (9:00 - 10:30) | Plenary Session#1 (1TU) [Single Stream] | Stream#1 (1TU) | Stream#1 (1TU) | Revision session | Closing plenary
10:30 - 11:00 | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break
Q2 (11:00 - 12:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Revision session | Closing plenary
12:30 - 14:00 | Lunch | Lunch | Lunch | Lunch | Lunch
Q3 (14:00 - 15:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | CH Closing | Closing plenary
15:30 - 16:00 | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break
Q4 (16:00 - 17:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | CH Closing | Closing plenary
17:30 - 17:40 | Break | Break | Break | Break | Break
Q5 (17:40 – 19:10) | Stream#1 (1TU) | Stream#1 (0.5 TU) Stop around 18:45 Social evening | Stream#1 (1TU) | CH Closing(Opt.) | 
Assumption: Every day = 5 sessions (TUs), total TU in 1 ordinary meeting (exclude closing plenary TUs) = 15.5 TUs

## Slide 66: TU Budget for SA5 CH
Assumptions for SA5 CH :
  6 ordinary meeting per year.
  Rel-19 spans 18 months for SA5 (with early start of studies) = 8 meetings
  1 Session = 1.5 hour time window
  Max 5 sessions per meeting day
  1 Stream = 1 TU (Time Unit)
  1 TU is time (i.e., 1.5 hours) spent to discuss/handle technical contributions.
  Revisions/Drafting/offline conference call are not counted for the TU estimates.
  CH revision sessions normally planned to be in Thursday Q1 and Q2 (initial assump.),CH closing plenary planned to be in Thursday Q3 and Q4.
  1 (CH) stream per session => 15.5 TUs per meeting (incl. 2 TUs as buffer) = 124
  Assume Maintenance + Buffer = 33% as in SA2 => ~ 41 TU
  Resulting total TUs avail. f. SI/WI: 9 meetings x 15.5 sessions = 124 TU minus 41 => 83 TU
  => Recommended MAX no. of SI/WI = 14
  With 14 SI/WI => Average 6 TU per SI/WI (0.75/meeting).

## Slide 67: SA5 Rel-19 CH TU planning (May.2024~Sep.2025)
 | Maintenance+R18 | R19 | R20 preparation | Buffer (revision session)
May. 2024: SA5#155 (1 meeting) | 2.5 TU*1eetings = 2.5 TU (CRs) | 6 TU*1 meetings= 6 TU 5 TU: Rel-19 topic discussion | NA | 2 TU*4=8 TU
July. 2024~Dec.2024: SA5#156~#158 (3 meetings) | 2.5 TU*3 meetings = 7.5 TU (CRs) | 11 TU*3 meetings= 33 TU | NA | 2 TU*4=8 TU
Jan.2025~Sep.2025: SA5#159~#162 (4 meetings) | 1.5 TU*4 meetings= 6 TU (CRs) | 11 TU*4 meetings= 44 TU | 1 TU*4 meetings = 4 TU | 2 TU*4=8 TU
Total= 124 TU | 16 TU | 83 TU | 4 TU | 16 TU
Assumptions:
Every meeting day = 5 quarters (= 5 TUs)
Total TUs per meeting = 15.5 TUs
  Buffer = 2 TUs
  CH = 13.5 TUs
    Maintenance CRs + remaining Rel-18 work (TU allocation will decrease over time )
    Rel-20 preparation work (TU allocation will be zero at the beginning and will increase over time )
    All remaining time is available for Rel-19 SIDs / WIDs
Total TUs allocated to Rel-19 SIDs / WIDs = 83 TUs