## General
Last Update: October 02, 2025
Last Updated version: v04
3GPP TSG CT WG3 Meeting #143
3GPP TSG CT WG4 Meeting #131
Sophia-Antipolis, France, 13 - 17 October 2025
Source: | Samsung
Title: | Work plan
Agenda Item: | 19.60
Work Item / Release: | Rel-19
Latest WID | CP-250247
Completion Status:
CT3: 90%
CT4: 95%

## CT3
Meeting | Related LS or other WG tdoc(s) | Desciption | SA2 TDoc source Companies | Impacted Stage-2 TS | Impacted Stage-3 Spec | Volunteered company/delegate | Comments
SA2 #166 Ad Hoc-e
SA2 #166 Ad Hoc-e | S2-2501216 | Energy Saving indicator | Ericsson, AT&T, Deutsche Telekom, NEC, Samsung | Spec: 23.502 CR5144r2
SA2 #166 Ad Hoc-e | S2-2501215 | Energy saving subscription and AM policy. | Vivo, Qualcomm Incorporated, ZTE, Deutsche Telekom, CATT, Samsung | Spec: 23.502 CR5276r1
SA2 #166 Ad Hoc-e | S2-2501214 | Policy control with energy saving consideration. | Vivo, Qualcomm Incorporated, MediaTek Inc, ZTE, Deutsche Telekom, CATT, Samsung | Spec: 23.503 CR1486r1
SA2 #166 Ad Hoc-e | S2-2501213 | Updating EIF service operations | NTT DOCOMO, Deutsche Telekom, Vivo, China Mobile | Spec: 23.502 CR5239r1 | TS 29.508 | Samsung
SA2 #166 Ad Hoc-e | S2-2501212 | Data collection for energy information calculation and exposure | CATT, ETRI | Spec: 23.502 CR5160r2 | TS 29.508 | Samsung
SA2 #166 Ad Hoc-e | S2-2501211 | Clarification regarding energy collection and exposure | Huawei, HiSilicon, ETRI | Spec: 23.502 CR5289r1 | TS 29.508 | Samsung
SA2 #166 Ad Hoc-e | S2-2501210 | Compliance to regional legislation concerning user privacy. | Nokia, Deutsche Telekom, NTT Docomo | Spec: 23.501 CR5935r1
SA2 #166 Ad Hoc-e | S2-2501209 | Update on NF function descriptions and EIF selection factors | Vivo, Huawei, ZTE | Spec: 23.501 CR5997r1
SA2 #166 Ad Hoc-e | S2-2501208 | Parameters for EIF selection | China Mobile,vivo | Spec: 23.501 CR5897r1
SA2 #167
SA2 #167 | S2-2502371 | 23.501 CR5927R1 (Rel-19, 'F'): Resolution of editor's note on whether the Energy Saving indicator is one value or multiple values. | Nokia, Deutsche Telekom | TS 23.501
SA2 #167 | S2-2502372 | 23.502 CR5144R6 (Rel-19, 'F'): Energy Saving Indicator | Ericsson, AT&T, Deutsche Telekom, [NEC,] Samsung | TS 23.502 | TS 29.554 | China Telecom, ZTE, Samsung
SA2 #167 | S2-2502308 | 23.502 CR5370 (Rel-19, 'F'): Energy saving indicator to RAN in mobility | ZTE | TS 23.502
SA2 #167 | S2-2502373 | 23.501 CR5928R1 (Rel-19, 'F'): Resolution of editor's note on PCF taking EIF information into account | Nokia, ZTE, Deutsche Telekom, Qualcomm Inc, Ericsson, | TS 23.501 | TS 29.513 | China Telecom
SA2 #167 | S2-2502568 | 23.503 CR1486R5 (Rel-19, 'F'): Policy control with energy saving consideration | Vivo, [Qualcomm Incorporated], MediaTek Inc, [ZTE, Deutsche Telekom, CATT, Samsung] | TS 23.503 | TS 29.519, TS 29.122 | ZTE
SA2 #167 | S2-2502312 | 23.501 CR6031R1 (Rel-19, 'F'): Clarification on the BDT based on network energy related information | ZTE | TS 23.501 | TS 29.554 | Samsung
SA2 #167 | S2-2502376 | 23.501 CR6071 (Rel-19, 'F'): Update of the Energy consumption calculation formulae | Nokia | TS 23.501
SA2 #167 | S2-2502575 | 23.501 CR6010R1 (Rel-19, 'F'): Clarification on the EventExposure service operation of SMF | Huawei, HiSilicon | TS 23.501 | TS 29.508 | Samsung
SA2 #167 | S2-2502570 | 23.501 CR6100 (Rel-19, 'F'): Update on energy consumption information collection and exposure to solve the Editor's notes | vivo | TS 23.501 | TS 29.522, TS 29.122 | Nokia, ZTE, Ericsson
SA2 #167 | S2-2501511 | 23.502 CR5337 (Rel-19, 'F'): Update for Nudm service operation consumer | China Mobile | TS 23.502
SA2 #167 | S2-2502567 | 23.502 CR5289R2 (Rel-19, 'F'): Clarification regarding energy collection and exposure | [Huawei, HiSilicon, ETRI], China Mobile, | TS 23.502 | TS 29.508 | Samsung
SA2 #167 | S2-2502574 | 23.502 CR5351 (Rel-19, 'F'): Update on EIF services to solve the Editor's notes | vivo, MediaTek Inc. | TS 23.502
SA2 #167 | S2-2502782 | 23.501 CR6028R1 (Rel-19, 'F'): Adding per UE per Application level Energy consumption exposure | ZTE, China Mobile, NTT DOCOMO, Vivo | TS 23.501 | TS 29.122, TS 29.508 | Nokia, Ericsson,. Samsung
SA2 #167 | S2-2502783 | 23.502 CR5299R1 (Rel-19, 'F'): Adding per UE per Application level Energy consumption exposure filter | ZTE | TS 23.502 | TS 29.522, TS 29.508 | ZTE, Samsung
SA2 #167 | S2-2502382 | 23.501 CR5956R1 (Rel-19, 'C'): Support for S-NSSAI granularity energy consumption exposure | NEC | TS 23.501 | TS 29.522, TS 29.122 | Nokia
SA2 #167 | S2-2502361 | 23.502 CR5244R1 (Rel-19, 'C'): Support for S-NSSAI granularity energy consumption exposure | NEC | TS 23.502 | TS 29.522 | Nokia
SA2 #167 | S2-2502573 | 23.501 CR6142 (Rel-19, 'F'): Resolve the EN in the architecture clause | ZTE | TS 23.501
SA2 #167 | S2-2502363 | 23.501 CR5900R1 (Rel-19, 'F'): Clean up the architecture and interface for energysys | Qualcomm Incorporated, Nokia, Ericsson | TS 23.501
SA2 #168
SA2 #168 | S2-2503994 | 23.501 CR6243 (Rel-19, 'F'): Solve the editor s note about the renewable energy information | Vivo | TS 23.501 | TS 29.122 | Samsung
SA2 #168 | S2-2504297 | 23.502 CR5458 (Rel-19, 'F'): Energy Consumption information collection procedure clarification | Nokia | TS 23.502
SA2 #168 | S2-2504298 | 23.502 CR5480 (Rel-19, 'F'): On the report of SMF to EIF for user-plane energy consumption calculation | Huawei, HiSilicon | TS 23.502 | TS 29.508, TS 29.522, | Huawei, Samsung,
SA2 #168 | S2-2504300 | 23.501 CR6222 (Rel-19, 'F'): Correction on the granularity description and clause reference | ZTE | TS 23.501
SA2 #168 | S2-2504301 | 23.502 CR5456 (Rel-19, 'F'): Correction on energy consumption information collection and exposure | CATT | TS 23.502
SA2 #168 | S2-2504348 | 23.501 CR6223 (Rel-19, 'F'): Clarification on the OAM input | ZTE | TS 23.501
SA2 #168 | S2-2504303 | 23.501 CR6260 (Rel-19, 'F'): Energy consumption information collection for new PDU Session | Samsung | TS 23.501
SA2 #168 | S2-2504304 | 23.501 CR6262 (Rel-19, 'F'): Update on the energy consumption information collection | Vivo | TS 23.501
SA2 #168 | S2-2504305 | 23.502 CR5464 (Rel-19, 'F'): On the report of SMF to EIF for user-plane energy consumption calculation | Huawei, HiSilicon | TS 23.502
SA2 #168 | S2-2504340 | 23.501 CR6256 (Rel-19, 'F'): Energy consumption information for access type | Samsung | TS 23.501
SA2 #168 | S2-2504341 | 23.502 CR5470 (Rel-19, 'F'): Energy consumption information for access type | Samsung | TS 23.502
SA2 #168 | S2-2504307 | 23.502 CR5459 (Rel-19, 'F'): SMF exposure service clarification for Energy Consumption information collection | Nokia | TS 23.502
SA2 #168 | S2-2503124 | 23.501 CR6183 (Rel-19, 'F'): Clarification on the reporting period of energy-related information | NTT DOCOMO | TS 23.501
SA2 #168 | S2-2504007 | 23.501 CR6245 (Rel-19, 'F'): Update on the energy consumption information exposure | Vivo | TS 23.501 | TS 29.122 | Samsung
SA2 #168 | S2-2504338 | 23.501 CR6234 (Rel-19, 'F'): EIF exposure serice definition clarification | Nokia | TS 23.501 | TS 29.566 | Nokia, China Telecom, Huawei
SA2 #168 | S2-2504009 | 23.502 CR5461 (Rel-19, 'F'): EIF exposure service definition clarification | Nokia | TS 23.502 | TS 29.566 | China Telecom, Nokia, Huawei
SA2 #168 | S2-2504010 | 23.502 CR5449 (Rel-19, 'F'): Resolve the EN in the EIF service | ZTE | TS 23.502
SA2 #169
|  | KI#1: Collection of Energy Consumption information from SMF/UPF | -
SA2 #169 | S2-2505857 | 23.501 CR6242R4 (Rel-19, 'F'): Clarification on the EventExposure service operation of SMF | Huawei, HiSilicon | TS 23.501 | TS 29.508 | Huawei
SA2 #169 | S2-2505634 | 23.501 CR6305 (Rel-19, 'F'): Clarification on the UPF Energy Consumption information collection | ZTE | TS 23.501
SA2 #169 | S2-2505635 | 23.502 CR5499 (Rel-19, 'F'): Clarification on the UPF Energy Consumption information collection | ZTE | TS 23.502
SA2 #169 | S2-2505858 | 23.502 CR5480R4 (Rel-19, 'F'): On the report of SMF to EIF for user-plane energy consumption calculation | [Huawei, HiSilicon, NEC], Samsung | TS 23.502
SA2 #169 | S2-2505546 | 23.502 CR5498 (Rel-19, 'F'): Clarification on retrieving information from OAM | ZTE | TS 23.502
SA2 #169 | S2-2505637 | 23.501 CR6239R1 (Rel-19, 'F'): Report of SMF to EIF for user-plane energy consumption calculation | Huawei, HiSilicon | TS 23.501
SA2 #169 | S2-2506100 | 23.501 CR6256R6 (Rel-19, 'F'): Energy consumption information for access type | [Samsung, NTT DOCOMO], Huawei, HiSilicon | TS 23.501 | TS 29.508 | Huawei, Samsung
SA2 #169 | S2-2506101 | 23.502 CR5470R4 (Rel-19, 'F'): Energy consumption information for access type | [Samsung, NTT DOCOMO], vivo | TS 23.502
SA2 #169 | S2-2505860 | 23.501 CR6254R1 (Rel-19, 'F'): EIF discvoery and selection | Samsung | TS 23.501 | TS 29.566 | Samsung
|  | KI#2: BDT Policy | -
SA2 #169 | S2-2505551 | 23.502 CR5472R1 (Rel-19, 'F'): Alignment of Energy indicator in BDT policy | China Mobile | TS 23.502
SA2 #169 | S2-2505786 | 23.502 CR5110R2 (Rel-19, 'B'): BDT Energy Negotiation Procedures | Motorola Mobile Com Technology | TS 23.502 | TS 29.554 | Samsung
SA2 #169 | S2-2505861 | 23.502 CR5240R3 (Rel-19, 'F'): Negotiation for future background data transfer considering energy | NTT DOCOMO, Toyota, KDDI | TS 23.502 | TS 29.513 | ZTE
SA2 #169 | S2-2505788 | 23.503 CR1492R5 (Rel-19, 'F'): Corrections for energy saving related AF input on BDT policy negotiation | Huawei, HiSilicon, NTT DOCOMO, KDDI | TS 23.503 | TS 29.554 | ZTE,China Telecom
|  | KI#3: EIF Exposure Service, etc. | -
SA2 #169 | S2-2505789 | 23.501 CR6295 (Rel-19, 'F'): Clean up the consumer NF of energy consumption information exposure | Qualcomm Incorporated | TS 23.501
SA2 #169 | S2-2505790 | 23.501 CR6234R3 (Rel-19, 'F'): EIF exposure service definition clarification | Nokia | TS 23.501 | TS 29.522 | Samsung
SA2 #169 | S2-2505791 | 23.501 CR6311 (Rel-19, 'F'): Clarification on PLMN | LG Electronics | TS 23.501
SA2 #170
SA2 #170 | S2-2506217 | 23.502 CR5494R1 (Rel-19, 'F'): Removal of ESI to NG-RAN | Nokia, Huawei, LG Electronics, ZTE, Vivo | TS 23.502
SA2 #170 | S2-2507733 | 23.501 CR6329R3 (Rel-19, 'F'): Update on Energy Saving Indicator handling | vivo, Nokia, LG Electronics, ZTE, Huawei | TS 23.501 | TS 29.554
|  | Energy information collection | -
SA2 #170 | S2-2507798 | 23.502 CR5539 (Rel-19, 'F'): Clarification on SMF-UPF interactions for EC collection | Huawei, HiSilicon | TS 23.502
SA2 #170 | S2-2507736 | 23.502 CR5508R1 (Rel-19, 'F'): Support of SMF subscription termination | Samsung | TS 23.502
SA2 #170 | S2-2507737 | 23.501 CR6398 (Rel-19, 'F'): Node information collection from I-SMF | ZTE | TS 23.501 | TS 29.508
SA2 #170 | S2-2507738 | 23.501 CR6336 (Rel-19, 'F'): On clarification of sharing information at NF/done level from OAM among EIF exposure subscriptions | Nokia | TS 23.501
SA2 #170 | S2-2507739 | 23.501 CR6415 (Rel-19, 'F'): Update on energy consumption information collection from OAM | vivo | TS 23.501 | TS 29.522
SA2 #170 | S2-2507740 | 23.501 CR6334 (Rel-19, 'F'): Clarification on reporting of usage data to EIF when the UE is in EPS | Nokia | TS 23.501
SA2 #170 | S2-2507800 | 23.501 CR6416 (Rel-19, 'F'): Clarification on energy consumption information for Non-3GPP Access | vivo | TS 23.501

## CT4
Meeting | Related LS or other WG tdoc(s) | Desciption | SA2 TDoc source Companies | Impacted Stage-2 TS | Impacted Stage-3 Spec | Volunteered company/delegate | Comments
SA2 #166 Ad Hoc-e
SA2 #166 Ad Hoc-e | S2-2501216 | Energy Saving indicator | Ericsson, AT&T, Deutsche Telekom, NEC, Samsung | Spec: 23.502 CR5144r2 | TS 29.518, TS 29.503 | Samsung
SA2 #166 Ad Hoc-e | S2-2501215 | Energy saving subscription and AM policy. | Vivo, Qualcomm Incorporated, ZTE, Deutsche Telekom, CATT, Samsung | Spec: 23.502 CR5276r1
SA2 #166 Ad Hoc-e | S2-2501214 | Policy control with energy saving consideration. | Vivo, Qualcomm Incorporated, MediaTek Inc, ZTE, Deutsche Telekom, CATT, Samsung | Spec: 23.503 CR1486r1
SA2 #166 Ad Hoc-e | S2-2501213 | Updating EIF service operations | NTT DOCOMO, Deutsche Telekom, Vivo, China Mobile | Spec: 23.502 CR5239r1 | TS 29.508 | Samsung
SA2 #166 Ad Hoc-e | S2-2501212 | Data collection for energy information calculation and exposure | CATT, ETRI | Spec: 23.502 CR5160r2 | TS 29.508 | Samsung
SA2 #166 Ad Hoc-e | S2-2501211 | Clarification regarding energy collection and exposure | Huawei, HiSilicon, ETRI | Spec: 23.502 CR5289r1 | TS 29.508 | Samsung
SA2 #166 Ad Hoc-e | S2-2501210 | Compliance to regional legislation concerning user privacy. | Nokia, Deutsche Telekom, NTT Docomo | Spec: 23.501 CR5935r1
SA2 #166 Ad Hoc-e | S2-2501209 | Update on NF function descriptions and EIF selection factors | Vivo, Huawei, ZTE | Spec: 23.501 CR5997r1
SA2 #166 Ad Hoc-e | S2-2501208 | Parameters for EIF selection | China Mobile,vivo | Spec: 23.501 CR5897r1
SA2 #167
SA2 #167 | S2-2502371 | 23.501 CR5927R1 (Rel-19, 'F'): Resolution of editor's note on whether the Energy Saving indicator is one value or multiple values. | Nokia, Deutsche Telekom | TS 23.501
SA2 #167 | S2-2502372 | 23.502 CR5144R6 (Rel-19, 'F'): Energy Saving Indicator | Ericsson, AT&T, Deutsche Telekom, [NEC,] Samsung | TS 23.502 | TS 29.554 | China Telecom, ZTE, Samsung
SA2 #167 | S2-2502308 | 23.502 CR5370 (Rel-19, 'F'): Energy saving indicator to RAN in mobility | ZTE | TS 23.502
SA2 #167 | S2-2502373 | 23.501 CR5928R1 (Rel-19, 'F'): Resolution of editor's note on PCF taking EIF information into account | Nokia, ZTE, Deutsche Telekom, Qualcomm Inc, Ericsson, | TS 23.501 | TS 29.513 | China Telecom
SA2 #167 | S2-2502568 | 23.503 CR1486R5 (Rel-19, 'F'): Policy control with energy saving consideration | Vivo, [Qualcomm Incorporated], MediaTek Inc, [ZTE, Deutsche Telekom, CATT, Samsung] | TS 23.503 | TS 29.519, TS 29.122 | ZTE
SA2 #167 | S2-2502312 | 23.501 CR6031R1 (Rel-19, 'F'): Clarification on the BDT based on network energy related information | ZTE | TS 23.501 | TS 29.554 | Samsung
SA2 #167 | S2-2502376 | 23.501 CR6071 (Rel-19, 'F'): Update of the Energy consumption calculation formulae | Nokia | TS 23.501
SA2 #167 | S2-2502575 | 23.501 CR6010R1 (Rel-19, 'F'): Clarification on the EventExposure service operation of SMF | Huawei, HiSilicon | TS 23.501 | TS 29.508 | Samsung
SA2 #167 | S2-2502570 | 23.501 CR6100 (Rel-19, 'F'): Update on energy consumption information collection and exposure to solve the Editor's notes | vivo | TS 23.501 | TS 29.522, TS 29.122 | Nokia, ZTE, Ericsson
SA2 #167 | S2-2501511 | 23.502 CR5337 (Rel-19, 'F'): Update for Nudm service operation consumer | China Mobile | TS 23.502 | TS 29.503 | Samsung
SA2 #167 | S2-2502567 | 23.502 CR5289R2 (Rel-19, 'F'): Clarification regarding energy collection and exposure | [Huawei, HiSilicon, ETRI], China Mobile, | TS 23.502 | TS 29.508 | Samsung
SA2 #167 | S2-2502574 | 23.502 CR5351 (Rel-19, 'F'): Update on EIF services to solve the Editor's notes | vivo, MediaTek Inc. | TS 23.502
SA2 #167 | S2-2502782 | 23.501 CR6028R1 (Rel-19, 'F'): Adding per UE per Application level Energy consumption exposure | ZTE, China Mobile, NTT DOCOMO, Vivo | TS 23.501 | TS 29.122, TS 29.508 | Nokia, Ericsson,. Samsung
SA2 #167 | S2-2502783 | 23.502 CR5299R1 (Rel-19, 'F'): Adding per UE per Application level Energy consumption exposure filter | ZTE | TS 23.502 | TS 29.522, TS 29.508 | ZTE, Samsung
SA2 #167 | S2-2502382 | 23.501 CR5956R1 (Rel-19, 'C'): Support for S-NSSAI granularity energy consumption exposure | NEC | TS 23.501 | TS 29.522, TS 29.122 | Nokia
SA2 #167 | S2-2502361 | 23.502 CR5244R1 (Rel-19, 'C'): Support for S-NSSAI granularity energy consumption exposure | NEC | TS 23.502 | TS 29.522 | Nokia
SA2 #167 | S2-2502573 | 23.501 CR6142 (Rel-19, 'F'): Resolve the EN in the architecture clause | ZTE | TS 23.501
SA2 #167 | S2-2502363 | 23.501 CR5900R1 (Rel-19, 'F'): Clean up the architecture and interface for energysys | Qualcomm Incorporated, Nokia, Ericsson | TS 23.501
SA2 #168
SA2 #168 | S2-2503994 | 23.501 CR6243 (Rel-19, 'F'): Solve the editor s note about the renewable energy information | Vivo | TS 23.501 | TS 29.122 | Samsung
SA2 #168 | S2-2504297 | 23.502 CR5458 (Rel-19, 'F'): Energy Consumption information collection procedure clarification | Nokia | TS 23.502
SA2 #168 | S2-2504298 | 23.502 CR5480 (Rel-19, 'F'): On the report of SMF to EIF for user-plane energy consumption calculation | Huawei, HiSilicon | TS 23.502 | TS 29.508, TS 29.522, | Huawei, Samsung,
SA2 #168 | S2-2504300 | 23.501 CR6222 (Rel-19, 'F'): Correction on the granularity description and clause reference | ZTE | TS 23.501
SA2 #168 | S2-2504301 | 23.502 CR5456 (Rel-19, 'F'): Correction on energy consumption information collection and exposure | CATT | TS 23.502
SA2 #168 | S2-2504348 | 23.501 CR6223 (Rel-19, 'F'): Clarification on the OAM input | ZTE | TS 23.501
SA2 #168 | S2-2504303 | 23.501 CR6260 (Rel-19, 'F'): Energy consumption information collection for new PDU Session | Samsung | TS 23.501
SA2 #168 | S2-2504304 | 23.501 CR6262 (Rel-19, 'F'): Update on the energy consumption information collection | Vivo | TS 23.501
SA2 #168 | S2-2504305 | 23.502 CR5464 (Rel-19, 'F'): On the report of SMF to EIF for user-plane energy consumption calculation | Huawei, HiSilicon | TS 23.502
SA2 #168 | S2-2504340 | 23.501 CR6256 (Rel-19, 'F'): Energy consumption information for access type | Samsung | TS 23.501
SA2 #168 | S2-2504341 | 23.502 CR5470 (Rel-19, 'F'): Energy consumption information for access type | Samsung | TS 23.502
SA2 #168 | S2-2504307 | 23.502 CR5459 (Rel-19, 'F'): SMF exposure service clarification for Energy Consumption information collection | Nokia | TS 23.502
SA2 #168 | S2-2503124 | 23.501 CR6183 (Rel-19, 'F'): Clarification on the reporting period of energy-related information | NTT DOCOMO | TS 23.501
SA2 #168 | S2-2504007 | 23.501 CR6245 (Rel-19, 'F'): Update on the energy consumption information exposure | Vivo | TS 23.501 | TS 29.122 | Samsung
SA2 #168 | S2-2504338 | 23.501 CR6234 (Rel-19, 'F'): EIF exposure serice definition clarification | Nokia | TS 23.501 | TS 29.566 | Nokia, China Telecom, Huawei
SA2 #168 | S2-2504009 | 23.502 CR5461 (Rel-19, 'F'): EIF exposure service definition clarification | Nokia | TS 23.502 | TS 29.566 | China Telecom, Nokia, Huawei
SA2 #168 | S2-2504010 | 23.502 CR5449 (Rel-19, 'F'): Resolve the EN in the EIF service | ZTE | TS 23.502
SA2 #169
|  | KI#1: Collection of Energy Consumption information from SMF/UPF | -
SA2 #169 | S2-2505857 | 23.501 CR6242R4 (Rel-19, 'F'): Clarification on the EventExposure service operation of SMF | Huawei, HiSilicon | TS 23.501 | TS 29.508 | Huawei
SA2 #169 | S2-2505634 | 23.501 CR6305 (Rel-19, 'F'): Clarification on the UPF Energy Consumption information collection | ZTE | TS 23.501
SA2 #169 | S2-2505635 | 23.502 CR5499 (Rel-19, 'F'): Clarification on the UPF Energy Consumption information collection | ZTE | TS 23.502
SA2 #169 | S2-2505858 | 23.502 CR5480R4 (Rel-19, 'F'): On the report of SMF to EIF for user-plane energy consumption calculation | [Huawei, HiSilicon, NEC], Samsung | TS 23.502
SA2 #169 | S2-2505546 | 23.502 CR5498 (Rel-19, 'F'): Clarification on retrieving information from OAM | ZTE | TS 23.502
SA2 #169 | S2-2505637 | 23.501 CR6239R1 (Rel-19, 'F'): Report of SMF to EIF for user-plane energy consumption calculation | Huawei, HiSilicon | TS 23.501
SA2 #169 | S2-2506100 | 23.501 CR6256R6 (Rel-19, 'F'): Energy consumption information for access type | [Samsung, NTT DOCOMO], Huawei, HiSilicon | TS 23.501 | TS 29.508 | Huawei, Samsung
SA2 #169 | S2-2506101 | 23.502 CR5470R4 (Rel-19, 'F'): Energy consumption information for access type | [Samsung, NTT DOCOMO], vivo | TS 23.502
SA2 #169 | S2-2505860 | 23.501 CR6254R1 (Rel-19, 'F'): EIF discvoery and selection | Samsung | TS 23.501 | TS 29.566 | Samsung
|  | KI#2: BDT Policy | -
SA2 #169 | S2-2505551 | 23.502 CR5472R1 (Rel-19, 'F'): Alignment of Energy indicator in BDT policy | China Mobile | TS 23.502
SA2 #169 | S2-2505786 | 23.502 CR5110R2 (Rel-19, 'B'): BDT Energy Negotiation Procedures | Motorola Mobile Com Technology | TS 23.502 | TS 29.554 | Samsung
SA2 #169 | S2-2505861 | 23.502 CR5240R3 (Rel-19, 'F'): Negotiation for future background data transfer considering energy | NTT DOCOMO, Toyota, KDDI | TS 23.502 | TS 29.513 | ZTE
SA2 #169 | S2-2505788 | 23.503 CR1492R5 (Rel-19, 'F'): Corrections for energy saving related AF input on BDT policy negotiation | Huawei, HiSilicon, NTT DOCOMO, KDDI | TS 23.503 | TS 29.554 | ZTE,China Telecom
|  | KI#3: EIF Exposure Service, etc. | -
SA2 #169 | S2-2505789 | 23.501 CR6295 (Rel-19, 'F'): Clean up the consumer NF of energy consumption information exposure | Qualcomm Incorporated | TS 23.501
SA2 #169 | S2-2505790 | 23.501 CR6234R3 (Rel-19, 'F'): EIF exposure service definition clarification | Nokia | TS 23.501 | TS 29.522 | Samsung
SA2 #169 | S2-2505791 | 23.501 CR6311 (Rel-19, 'F'): Clarification on PLMN | LG Electronics | TS 23.501
SA2 #170
SA2 #170 | S2-2506217 | 23.502 CR5494R1 (Rel-19, 'F'): Removal of ESI to NG-RAN | Nokia, Huawei, LG Electronics, ZTE, Vivo | TS 23.502
SA2 #170 | S2-2507733 | 23.501 CR6329R3 (Rel-19, 'F'): Update on Energy Saving Indicator handling | vivo, Nokia, LG Electronics, ZTE, Huawei | TS 23.501 | TS 29.554
|  | Energy information collection | -
SA2 #170 | S2-2507798 | 23.502 CR5539 (Rel-19, 'F'): Clarification on SMF-UPF interactions for EC collection | Huawei, HiSilicon | TS 23.502
SA2 #170 | S2-2507736 | 23.502 CR5508R1 (Rel-19, 'F'): Support of SMF subscription termination | Samsung | TS 23.502
SA2 #170 | S2-2507737 | 23.501 CR6398 (Rel-19, 'F'): Node information collection from I-SMF | ZTE | TS 23.501 | TS 29.508
SA2 #170 | S2-2507738 | 23.501 CR6336 (Rel-19, 'F'): On clarification of sharing information at NF/done level from OAM among EIF exposure subscriptions | Nokia | TS 23.501
SA2 #170 | S2-2507739 | 23.501 CR6415 (Rel-19, 'F'): Update on energy consumption information collection from OAM | vivo | TS 23.501 | TS 29.522
SA2 #170 | S2-2507740 | 23.501 CR6334 (Rel-19, 'F'): Clarification on reporting of usage data to EIF when the UE is in EPS | Nokia | TS 23.501
SA2 #170 | S2-2507800 | 23.501 CR6416 (Rel-19, 'F'): Clarification on energy consumption information for Non-3GPP Access | vivo | TS 23.501

## LSs
Incoming liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments
Outgoing liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments