3GPP TSG RAN meeting #110										RP-253427

Baltimore, USA, December 8-11, 2025

## Status Report to TSG

Agenda item:			13.4.1

| WI / SI Name | Rel-18 NR CA and DC; and NR and LTE DC Configurations |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| included in this status report | Study Item: No | Core part: No | Performance part: No |  | Testing part: Yes |
| Acronym | NR_CADC_NR_LTE_DC_R18-UEConTest |  |  |  |  |
| Unique ID | 1000057 |  |  |  |  |
| TSG Tdoc of latest approved WI/SI description (if any) | RP-240285 |  |  |  |  |
| Target Completion Date (indicate if changed) | Study Item: N/A | Core part: N/A | Performance part: N/A | Testing part: June/2026 (+ 6 months) |  |
| Overall Completion level | Study Item: N/A | Core part: N/A | Performance Part: N/A | Testing part: 76% |  |

Note: Overall completion level percentage numbers should use one of the colors below:

- xx%: Normal progress, no RAN plenary action needed

- xx%: Progress behind schedule, may need RAN plenary intervention. If so, SR should clearly define requested action

- xx%: Progress critically behind, RAN plenary shall intervene. SR should define requested action

Source:

| Leading WG |  | TSG RAN WG5 |
| --- | --- | --- |
| Rapporteur | Name | Chunying GU |
|  | Company | Huawei Technologies. Co., Ltd. |
|  | Email | guchunying@huawei.com |

## 1	Work plan related evaluation

| Do you want to modify the time budget for this WI/SI compared to what was endorsed at the last RAN meeting? | No |
| --- | --- |

Additional explanations/motivations for the time budget changes in the attached Excel table:

## 2.	Detailed progress in RAN WGs since last TSG meeting (for all involved WGs)

## 2.1	RAN1

#### 2.1.1	Agreements

#### 2.1.2	Remaining Open issues

## 2.2	RAN2

#### 2.2.1	Agreements

#### 2.2.2	Remaining Open issues

## 2.3	RAN3

#### 2.3.1	Agreements

#### 2.3.2	Remaining Open issues

## 2.4	RAN4

#### 2.4.1	Agreements

#### 2.4.2	Remaining Open issues

## 2.5	RAN5

#### 2.5.1	Agreements

Status after RAN5#109:

- 4 CRs updating CA/DC configurations are agreed.

- The overall progress is 76%

#### 2.5.2	Remaining Open issues

#### 2.5.3	Remaining Open issues with cross-WG dependencies

## 2.6	RAN6

#### 2.6.1	Agreements

#### 2.6.2	Remaining Open issues

## 3.	Detailed progress in SA/CT WGs since last TSG meeting (for all involved WGs)

NOTE: This section only needs to be filled in for WI/SIs where there is a corresponding relevant WI/SI in SA/CT.

## 3.1	SAx/CTs

#### 3.1.1	Agreements with cross-TSG impacts

#### 3.1.2	Remaining Open issues with cross-TSG impacts

NOTE: This section should also flag any critical dependencies that need TSG attention.

## 4.	References

NOTE:	This can be e.g. a list of all related Tdocs in the affected WGs since last TSG, references to LSs, produced TRs/TSs, the work/study item description or status reports of previous TSGs.

General document

[1]	R5-256391	WP of Rel-18 NR CA and DC; and NR and LTE DC Configurations	Huawei, HiSilicon

TS 38.508-1 CR

[2]	R5-256005	Updates for additional Rel-18 band configurations and additional combination capabilities	Verizon Spain

TS 38.521-1 CR

[3]	R5-256204	Adding testing for CA_n8A-n78A for Power Class 2 UE in AMPR	Huawei, HiSilicon

[4]	R5-255910	General updates of TS 38.521-1 clause 5 for R18 CA configurations	China Unicom, NTT DOCOMO INC., Huawei, HiSilicon

TS 38.905 CR

[5]	R5-256205	Adding TP analysis for CA_n8A-n78A A-MPR test case for Power Class 2 UE in AMPR	Huawei, HiSilicon

12.08.2024		minor adaptations for RAN #105

30.04.2024		minor adaptations for RAN #104

16.02.2024		minor adaptations for RAN #103

10.11.2023		minor adaptations for RAN #102

02.08.2023		minor adaptations for RAN #101

26.04.2023		minor adaptations for RAN #100

01.02.2023		minor adaptations for RAN #99

27.10.2022		minor adaptations for RAN #98e

01.08.2022		minor adaptations for RAN #97e

21.05.2022		minor adaptations for RAN #96

10.01.2022		minor adaptations for RAN #95e

04.10.2021		minor adaptations for RAN #94e

08.08.2021		minor adaptations for RAN #93e

17.05.2021		minor adaptations for RAN #92e

28.01.2021		minor adaptations for RAN #91e

09.11.2020		minor adaptations for RAN #90e

31.08.2020		minor adaptations for RAN #89e

20.04.2020		minor adaptations for RAN #88e

18.02.2020		minor adaptations for RAN #87e

14.11.2019		minor adaptations for RAN #86

18.08.2019		minor adaptations for RAN #85

12.05.2019		minor adaptations for RAN #84

27.02.2019		minor adaptations for RAN #83

21.11.2018		completion levels with colours added (for RAN #82)

v04.81	31.07.2018		simplification of template and addition of cross-TSG aspects (for RAN #81)

v04.80	21.05.2018		minor adaptations for RAN #80

v04.79	26.02.2018		minor adaptations for RAN #79

v04.78	18.11.2017		minor adaptations for RAN #78

v04.77	06.08.2017		minor adaptations for RAN #77

v04.76	15.05.2017		minor adaptations for RAN #76

v04.75	31.01.2017		minor adaptations for RAN #75

v04.74	28.10.2016		minor adaptations for RAN #74

v04.73	01.09.2016		adaptations for RAN #73 (time units in extra Excel table, RAN6 reporting included)

v04.72	26.05.2016		adaptations for RAN #72 (introduction of NR & GERAN TUs)

v04.71	10.02.2016		minor adaptations for RAN #71

v04.70	30.10.2015		minor adaptations for RAN #70

v04.69	12.08.2015		minor adaptations for RAN #69

v04.68	21.05.2015		minor adaptations for RAN #68

v04.67	01.02.2015		minor adaptations for RAN #67

v04.66	16.11.2014		minor adaptations for RAN #66

v04.65	16.08.2014		minor adaptations for RAN #65

v04.64	22.05.2014		minor adaptations for RAN #64

v04.63	24.01.2014		restructuring for RAN #63 to cover Core & Perf. in one doc file

v03.62	11.11.2013		section 1.2.3 adapted for RAN #62

v03	11.08.2013		section 1.2.3 added on time budget

v02	07.05.2010		history added, some spelling corrections

v01	13.11.2009		First version of the template