## Cover sheet
<3GPP TSG RAN WG5#109> | [7 empty] | R5-255659
<Dallas, US, 17th Nov 2025 - 21st Nov 2025>
Agenda Item: | 7.5.2
Source: | China Unicom
Title: | UE Conformance - NR Support for UAV (Uncrewed Aerial Vehicles) plus CT1 aspects
Work item code: | 1070060
Release: | Rel-18
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
The objective of the UE Conformance - NR Support for UAV (Uncrewed Aerial Vehicles) plus CT1 aspects work item is to define the UE conformance requirements corresponding to WID on NR_UAV_plus_CT1-UEConTest, analyse the test case impact, applicability, test environment, and update the relevant conformance specifications for the UAV UE work item in Rel-18. At the RAN#107 meeting the Rel-18 RAN5 work item for UE Conformance - NR Support for UAV (Uncrewed Aerial Vehicles) plus CT1 aspects(NR_UAV_plus_CT1-UEConTest) was approved , the WID is in [1]. The purpose of present document is to provide a work plan for the RAN5 work item. The work plan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 50% (+8%) | 22 (+3) | 48
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR1) |  | 50.1% (+7.9%) | 22 (+3) | 48
FR1 |  | 50.1% (+7.9%) | 22 (+3) | 48
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 26.2% (+21.3%) |  |  | 26.2% (+21.3%)
Common ICS | 38.508-2 | 20% |  |  | 20%
NR RF/RRM
FR1 RF common parts | 38.521-1 | 100% | 1 | 1 | 100% | 1 | 1
FR1 RF Tx test cases | 38.521-1 Tx | 100% | 10 | 10 | 100% | 10 | 10
FR1 RF Rx test cases | 38.521-1 Rx
FR2 RF common parts | 38.521-2
FR2 RF Tx test cases | 38.521-2 Tx
FR2 RF Rx test cases | 38.521-2 Rx
FR1 and FR2 Interworking operation with other radios RF common parts | 38.521-3
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx
RF Demod/QSI test cases | 38.521-4
RRM test cases | 38.533
Applicability RF. Demod/QSI and RRM test cases | 38.522
Test Tolerances analysis RRM and RF Rx test cases | 38.903
Test Point analysis receiver and transmitter test cases | 38.905
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 29.7% (+8.1%) | 11 (+3) | 37 | 29.7% (+8.1%) | 11 (+3) | 37
Applicability Protocol test cases | 38.523-2 | 25% (+12.5%) |  |  | 25% (+12.5%)
Test suites (TTCN) | 38.523-3 | 80% (+80%) |  |  | 80% (+80%)
Test suites (TTCN) | 37.571-4 | 80% (+80%) |  |  | 80% (+80%)
5 References
[1] RP-250062 | New WID on UE Conformance - NR Support for UAV (Uncrewed Aerial Vehicles) plus CT1 aspects
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance - NR Support for UAV (Uncrewed Aerial Vehicles) plus CT1 aspects | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | 1070060
WP Scope: |  | The purpose of present document is to provide a workplan for the RAN5 work item UE Conformance - NR Support for UAV (Uncrewed Aerial Vehicles) plus CT1 aspects comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID
WP Resp: |  | Yu Shi(China Unicom), Yogesh Tugnawat(Qualcomm), Tuomo Saynajakangas(Nokia) |  |  | shiyu19@chinaunicom.cn; yogesht@qti.qualcomm.com; tuomo.saynajakangas@nokia.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | N/A |  |  | N/A
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1
50.1% (+7.9%)
52 (+1)
64 (+1)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  |  |  |  | 3.3 Abbreviations 4.5B（Vertical UE） 4.6.2（SIB2、3、5） 5.6 6.2.3 | TBD
1 |  | 38.508-1 | 4 | common test environment for UAV UE | Definition of common test environment for UAV UE |  | RAN5#110 (Feb-26) | R5-255896 |  | 1 | 85% (+85%) | 85% (+85%) |  | 85%
2 |  | 38.508-1 | 5 | Test environments for RF test | Necessary changes to RF test environments |  | RAN5#110 (Feb-26) |  |  | 1 | 0% | 0% |  | 0%
3 |  | 38.508-1 | 6 | Test environments for Signalling test | Necessary changes to Signalling test environments |  | RAN5#110 (Feb-26) | R5-255040 | [Ref: 38.331 clause 6.3.1,6.3.2,6.3.3,6.3.4] Add new frequencyBandListAerial-r18 in SIB2,SIB4,SIB5,FrequencyInfoDL-SIB,FrequencyInfoUL,FrequencyInfoUL-SIB,MultiFrequencyBandListNR-SIB,NR-NS-PmaxList; Add new Aerial-Config to provides configuration parameters for aerial UE; Add new ReportConfigNR to specifie criteria for triggering of an NR measurement reporting event; Add new aerialParameters in AerialParameters,UE-NR-Capability; Add new aerial-FlightPathAvailabilityConfig in OtherConfig; [Ref: 38.331 clause 5.2.2.4.2,5.2.2.4.3,5.2.2.4.5] Add new clause for Aerial UE（Actions upon reception of SIB2,SIB3,SIB5） | 1 | 20% | 20% |  | 20%
4 |  | 38.508-1 | Annex A | Connection Diagrams | Connection Diagrams |  | RAN5#110 (Feb-26) |  |  | 1 | 0% | 0% |  | 0%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
5 |  | 38.508-2 | A.4 | ICS proforma tables | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. |  | RAN5#110 (Feb-26) | R5-252043 |  | 1 | 20% | 20% |  | 20%
NR RF/RRM
TS 38.521-1: FR1 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
6 |  | 38.521-1 | 2 | References | Add ECC Decision(22)07 | Nokia | RAN5#107 (May-25) | R5-252153 |  | 1 | 100% | 100% |  | 100%
7 |  | 38.521-1 | 3.1 | Definition | Add Aerial UE definition | Nokia | RAN5#107 (May-25) | R5-252153 |  | 1 | 100% | 100% |  | 100%
8 |  | 38.521-1 | 3.3 | Abbreviations | Add Aerial UE abbreviations | Nokia | RAN5#107 (May-25) | R5-252153 |  | 1 | 100% | 100% |  | 100%
9 |  | 38.521-1 | 4.3 | Specification suffix information | Add suffix K for Aerial UE | Nokia | RAN5#107 (May-25) | R5-252153 |  | 1 | 100% | 100% |  | 100%
10 | Y | 38.521-1 | 5.2K | Operating bands for Aerial UE | Add new clause for Aerial UE | Nokia | RAN5#107 (May-25) | R5-252153 |  | 1 | 100% | 100% |  | 100%
TS 38.521-1: FR1 RF test cases - Tx
|  | 38.521-1 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
11 |  | 38.521-1 Tx | 6.2K | Transmitter power for Aerial UE | Add new sub-clause for Aerial UE | Nokia | RAN5#107 (May-25) | R5-253442 |  | 0
12 | Y | 38.521-1 Tx | 6.2K.1 | Maximum output power for Aerial UE | Add new clause for Aerial UE | Nokia | RAN5#107 (May-25) | R5-253442 | Refer to clause 6.2.1 | 1 | 100% | 100% |  | 100%
13 | Y | 38.521-1 Tx | 6.2K.2 | Maximum output power reduction for Aerial UE | Add new clause for Aerial UE | Nokia | RAN5#107 (May-25) | R5-253442 | Refer to clause 6.2.2 | 1 | 100% | 100% |  | 100%
14 | Y | 38.521-1 Tx | 6.2K.3 | Additional maximum output power reduction for Aerial UE | Add new clause for Aerial UE | Nokia | RAN5#108 (Aug-25) | R5-253442 R5-253869 | Specify A-MPR for NS_UAV_44 and NS_UAV_70 | 1 | 100% | 100% |  | 100%
15 | Y | 38.521-1 Tx | 6.2K.4 | Configured transmitted power for Aerial UE | Add new clause for Aerial UE | Nokia | RAN5#107 (May-25) | R5-253442 | Refer to clause 6.2.4 with modifications | 1 | 100% | 100% |  | 100%
16 |  | 38.521-1 Tx | 6.5K | Output RF spectrum emissions for Aerial UE | Add new sub-clause for Aerial UE | Nokia | RAN5#107 (May-25) | R5-253442 |  | 0
17 | Y | 38.521-1 Tx | 6.5K.1 | Occupied bandwidth for Aerial UE | Add new clause for Aerial UE | Nokia | RAN5#107 (May-25) | R5-253442 | Refer to clause 6.5.1 | 1 | 100% | 100% |  | 100%
18 | Y | 38.521-1 Tx | 6.5K.2 | Out of band emission for Aerial UE | Add new clause for Aerial UE | Nokia | RAN5#107 (May-25) | R5-253442 | Refer to clause 6.5.2 | 1 | 100% | 100% |  | 100%
19 |  | 38.521-1 Tx | 6.5K.3 | Spurious emissions for Aerial UE | Add new clause for Aerial UE | Nokia | RAN5#107 (May-25) | R5-253442 |  | 0
20 | Y | 38.521-1 Tx | 6.5K.3.0 | General | Add new clause for Aerial UE | Nokia | RAN5#107 (May-25) | R5-253442 | Refer to clause 6.5.3.0 | 1 | 100% | 100% |  | 100%
21 | Y | 38.521-1 Tx | 6.5K.3.1 | General spurious emissions | Add new clause for Aerial UE | Nokia | RAN5#107 (May-25) | R5-253442 | Refer to clause 6.5.3.1 | 1 | 100% | 100% |  | 100%
22 | Y | 38.521-1 Tx | 6.5K.3.2 | Spurious emissions for UE co-existence | Add new clause for Aerial UE | Nokia | RAN5#107 (May-25) | R5-253442 | Refer to clause 6.5.3.2 | 1 | 100% | 100% |  | 100%
23 | Y | 38.521-1 Tx | 6.5K.3.3 | Additional spurious emissions | Add new clause for Aerial UE | Nokia | RAN5#107 (May-25) | R5-253442 |  | 1 | 100% | 100% |  | 100%
TS 38.521-1: FR1 RF test cases - Rx (No need to change RF receiver requirements.)
|  | 38.521-1 Rx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TS 38.522: Applicability for RF, Demod/CSI reporting and RRM test cases
|  | 38.522 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
24 |  | 38.522 | 4 | Test case conditions and selection criteria | Add test case applicability statements for the new test cases introduced for 38.521-1. |  | RAN5#110 (Feb-26) |  |  | 1 | 0% | 0% |  | 0%
25 |  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Add test case applicability statements for the new test cases introduced for 38.521-1. |  | RAN5#110 (Feb-26) |  |  | 1 | 0% | 0% |  | 0%
TR 38.905: Test Point analysis receiver and transmitter test cases
|  | 38.905 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
26 |  | 38.905 | 4.1.2.1 | A-MPR, A-SEM and A-SE FR1 test cases for single carrier and UL MIMO | Add test point analysis for NS_UAV_44 and NS_UAV_70 | Nokia | RAN5#108 (Aug-25) | R5-255237 |  | 1 | 100% | 100% |  | 100%
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
Idle Mode
27 |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  | Need double check | 0
28 |  | 38.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  | Need double check | TBD
29 |  | 38.523-1 | <Clause> | Cell selection / NR UAV | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  | Need double check | 1
Layer 2
30 |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  | Need double check | 0
31 |  | 38.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  | Need double check | TBD
32 |  | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  | Need double check | 1
RRC
33 | Y | 38.523-1 | 8.1.3.5 | Measurement for Aerial UE | New sub-clause header |  | TBD
34 | Y | 38.523-1 | 8.1.3.5.1 | NR UAV / Measurement configuration control and reporting / Event H1 | [Ref: 38.331 clause 5.5.4.21] | Qualcomm | RAN5#111 (May-26) | R5-2545041 R5-256648 | Event H1: Aerial UE altitude becomes higher than a threshold; | 1 | 100% | 100% |  | 100%
35 | Y | 38.523-1 | 8.1.3.5.2 | NR UAV / Measurement configuration control and reporting / Event H2 | [Ref: 38.331 clause 5.5.4.22] | Qualcomm | RAN5#111 (May-26) | R5-255042 R5-256648 | Event H2: Aerial UE altitude becomes lower than a threshold; | 1 | 100% | 100% |  | 100%
36 | Y | 38.523-1 | 8.1.3.5.3 | NR UAV / Measurement configuration control and reporting / Event A3H1 / Measurement of Neighbour NR cell / Intra-frequency measurements | [Ref: 38.331 clause 5.5.4.23] | Qualcomm | RAN5#111 (May-26) | R5-255043 | Event A3H1: Neighbour becomes offset better than SpCell and the Aerial UE altitude becomes higher than a threshold; | 1 | 100% | 100% |  | 100%
37 | Y | 38.523-1 | 8.1.3.5.4 | NR UAV / Measurement configuration control and reporting / Event A3H1 / Measurement of Neighbour NR cell / Inter-frequency measurements | [Ref: 38.331 clause 5.5.4.23] | Qualcomm | RAN5#111 (May-26) | R5-255044 |  | 1 | 100% | 100% |  | 100%
38 | Y | 38.523-1 | 8.1.3.5.5 | NR UAV / Measurement configuration control and reporting / Event A3H1 / Measurement of Neighbour NR cell / Inter-band measurements | [Ref: 38.331 clause 5.5.4.23] | Qualcomm | RAN5#111 (May-26) | R5-255045 |  | 1 | 100% | 100% |  | 100%
39 | Y | 38.523-1 | 8.1.3.5.6 | NR UAV / Measurement configuration control and reporting / Event A3H2 / Measurement of Neighbour NR cell / Intra-frequency measurements | [Ref: 38.331 clause 5.5.4.24] | Qualcomm | RAN5#111 (May-26) | R5-256649 | Event A3H2: Neighbour becomes offset better than SpCell and the Aerial UE altitude becomes lower than a threshold; | 1 | 0% | 0% |  | 0%
40 | Y | 38.523-1 | 8.1.3.5.7 | NR UAV / Measurement configuration control and reporting / Event A3H2 / Measurement of Neighbour NR cell / Inter-frequency measurement | [Ref: 38.331 clause 5.5.4.24] | Qualcomm | RAN5#111 (May-26) | R5-255893 |  | 1 | 0% | 0% |  | 0%
41 | Y | 38.523-1 | 8.1.3.5.8 | NR UAV / Measurement configuration control and reporting / Event A3H2 / Measurement of Neighbour NR cell / Inter-band measurements | [Ref: 38.331 clause 5.5.4.24] | Qualcomm | RAN5#111 (May-26) | R5-256650 |  | 1 | 0% | 0% |  | 0%
42 | Y | 38.523-1 | 8.1.3.5.9 | NR UAV / Measurement configuration control and reporting / Event A4H1 / Measurement of Neighbour NR cell / Intra-frequency measurements | [Ref: 38.331 clause 5.5.4.25] | China Unicom | RAN5#111 (May-26) | R5-255046 R5-256647 | Event A4H1: Neighbour becomes better than threshold1 and the Aerial UE altitude becomes higher than a threshold2; | 1 | 100% | 100% |  | 100%
43 | Y | 38.523-1 | 8.1.3.5.10 | NR UAV / Measurement configuration control and reporting / Event A4H1 / Measurement of Neighbour NR cell / Inter-frequency measurements | [Ref: 38.331 clause 5.5.4.25] | China Unicom | RAN5#111 (May-26) | R5-255059 |  | 1 | 100% | 100% |  | 100%
44 | Y | 38.523-1 | 8.1.3.5.11 | NR UAV / Measurement configuration control and reporting / Event A4H1 / Measurement of Neighbour NR cell / Inter-band measurements | [Ref: 38.331 clause 5.5.4.25] | China Unicom | RAN5#111 (May-26) | R5-255060 |  | 1 | 100% | 100% |  | 100%
45 | Y | 38.523-1 | 8.1.3.5.12 | NR UAV / Measurement configuration control and reporting / Event A4H2 / Measurement of Neighbour NR cell / Intra-frequency measurements | [Ref: 38.331 clause 5.5.4.26] | China Unicom | RAN5#111 (May-26) | R5-256712 | Event A4H2: Neighbour becomes better than threshold1 and the Aerial UE altitude becomes lower than a threshold2; | 1 | 100% (+100%) | 100% (+100%) |  | 100%
46 | Y | 38.523-1 | 8.1.3.5.13 | NR UAV / Measurement configuration control and reporting / Event A4H2 / Measurement of Neighbour NR cell / Inter-frequency measurements | [Ref: 38.331 clause 5.5.4.26] | China Unicom | RAN5#111 (May-26) | R5-256714 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
47 | Y | 38.523-1 | 8.1.3.5.14 | NR UAV / Measurement configuration control and reporting / Event A4H2 / Measurement of Neighbour NR cell / Inter-band measurements | [Ref: 38.331 clause 5.5.4.26] | China Unicom | RAN5#111 (May-26) | R5-256715 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
48 | Y | 38.523-1 | 8.1.3.5.15 | NR UAV / Measurement configuration control and reporting / Event A5H1 / Measurement of Neighbour NR cell / Intra-frequency measurements | [Ref: 38.331 clause 5.5.4.27] | China Unicom | RAN5#111 (May-26) |  | Event A5H1: SpCell becomes worse than threshold1 and neighbour becomes better than threshold2 and the Aerial UE altitude becomes higher than a threshold3; | 1 | 0% | 0% |  | 0%
49 | Y | 38.523-1 | 8.1.3.5.16 | NR UAV / Measurement configuration control and reporting / Event A5H1 / Measurement of Neighbour NR cell / Inter-frequency measurements | [Ref: 38.331 clause 5.5.4.27] | China Unicom | RAN5#111 (May-26) |  |  | 1 | 0% | 0% |  | 0%
50 | Y | 38.523-1 | 8.1.3.5.17 | NR UAV / Measurement configuration control and reporting / Event A5H1 / Measurement of Neighbour NR cell / Inter-band measurements | [Ref: 38.331 clause 5.5.4.27] | China Unicom | RAN5#111 (May-26) |  |  | 1 | 0% | 0% |  | 0%
51 | Y | 38.523-1 | 8.1.3.5.18 | NR UAV / Measurement configuration control and reporting / Event A5H2 / Measurement of Neighbour NR cell / Intra-frequency measurements | [Ref: 38.331 clause 5.5.4.28] | China Unicom | RAN5#111 (May-26) |  | Event A5H2: SpCell becomes worse than threshold1 and neighbour becomes better than threshold2 and the Aerial UE altitude becomes lower than a threshold3. | 1 | 0% | 0% |  | 0%
52 | Y | 38.523-1 | 8.1.3.5.19 | NR UAV / Measurement configuration control and reporting / Event A5H2 / Measurement of Neighbour NR cell / Inter-frequency measurements | [Ref: 38.331 clause 5.5.4.28] | China Unicom | RAN5#111 (May-26) |  |  | 1 | 0% | 0% |  | 0%
53 | Y | 38.523-1 | 8.1.3.5.20 | NR UAV / Measurement configuration control and reporting / Event A5H2 / Measurement of Neighbour NR cell / Inter-band measurements | [Ref: 38.331 clause 5.5.4.28] | China Unicom | RAN5#111 (May-26) |  |  | 1 | 0% | 0% |  | 0%
54 | Y | 38.523-1 | TBD | TBD | [Ref: 38.331 clause 6.2.2] UE Information Response （FlightPathInfoReport field descriptions） |  | TBD |  |  | 3 | 0% | 0% |  | 0%
55 | Y | 38.523-1 | TBD | TBD | [Ref: 38.331 clause 6.2.2] RRC Reconfiguration |  | TBD |  |  | 3 | 0% | 0% |  | 0%
NAS
56 | Y | 38.523-1 | TBD | TBD | [Ref: 24.501 clause 4.22 Uncrewed aerial vehicle identification, authentication, and authorization] |  | TBD |  |  | 4 | 0% | 0% |  | 0%
57 | Y | 38.523-1 | TBD | TBD | [Ref: TS 24.577 Aircraft-to-Everything (A2X) services in 5G System (5GS); Protocol aspects; Stage 3] 1)Direct C2 communications over PC5 and authorization over NAS 2)Capability indication for A2X and associated services over NAS protocol |  | TBD |  |  | 4 | 0% | 0% |  | 0%
58 | Y | 38.523-1 | TBD | TBD | [Ref: TS 24.578 Aircraft-to-Everything (A2X) services in 5G System (5GS); User Equipment (UE) policies; Stage 3] |  | TBD |  |  | 3 | 0% | 0% |  | 0%
TS 38.523-2: Applicability for Protocol test cases
59 |  | 38.523-2 | 4.1 | Protocol conformance test cases applicability | Add applicability for NR UAV |  | RAN5#110 (Feb-26) | R5-255090 R5-255682 R5-255895 |  | 1 | 50% (+25%) | 50% (+25%) |  | 50%
60 |  | 38.523-2 | 4.2 | Protocol conformance test cases Applicability Condition | Add applicability for NR UAV |  | RAN5#110 (Feb-26) |  |  | 1 | 0% | 0% |  | 0%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
61 |  | 38.523-3 | <Clause> | Test Model |  |  | RAN5#110 (Feb-26) | R5-255776 |  | 1 | 80% (+80%) | 80% (+80%) |  | 80%
TS 37.571-4(TTCN)
|  | 37.571-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
62 |  | 37.571-4 | <Clause> | <Title of task> | GNSS test model aspects |  | RAN5#110 (Feb-26) | R5-255777 | Progress of TTCN development is tracked in MCC TF160 reports to RAN5/RAN | 1 | 80% (+80%) | 80% (+80%) |  | 80%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.