## Cover sheet
3GPP TSG-RAN WG5 Meeting #109 | [10 empty] | R5-256159
Dallas, USA, 17th-21st, Nov, 2025
Agenda Item: | NR_IoT_NTN_req_test_enh-UEConTest
Source: | Xiaomi, China Unicom, Samsung
Title: | UE Conformance - Enhanced requirements and conductive test methodology for NR NTN and IoT NTN
Work item code: | NR_IoT_NTN_req_test_enh-UEConTest
Release: | Rel-19
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
<Description of work item and its scope>
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 7% (+7%) | 0 | 11 (+11)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 5% (+5%) | 0 | 9 (+9)
FR1 |  | 5% (+5%) | 0 | 9 (+9)
FR2
FR1 + FR2
NSA Option 3 (EN-DC)
FR1
FR2
FR1 + FR2
LTE |  | 10.8% (+10.8%) | 0 | 2 (+2)
FDD |  | 10.8% (+10.8%) | 0 | 2 (+2)
TDD
FDD + TDD
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [8 empty] | NSA Option 3 (EN-DC) | [8 empty] | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 |  |  | FR1 + FR2 |  |  | FR1 |  |  | FR2 |  |  | FR1 + FR2 |  |  | FDD |  |  | TDD |  |  | FDD + TDD
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508 | 0% | [20 empty] | 0%
UE specific test functions | 36.509 | 0% | [20 empty] | 0%
LTE RF/RRM
RF common parts | 36.521-4
RF Rx test cases | 36.521-4 Rx | 0% | [20 empty] | 0%
RF Tx test cases | 36.521-4 Tx | 12.5% (+12.5%) | [20 empty] | 12.5% (+12.5%)
RF Demod test cases | 36.521-4 Demod | 0% | 0 | 2 (+2) | [18 empty] | 0% | 0 | 2 (+2)
Applicability RF. Demod/QSI and RRM test cases | 36.521-2 | 0% | [20 empty] | 0%
RRM test cases | 36.521-3
Test Tolerances analysis RRM test cases | 36.903 | 0% | [20 empty] | 0%
Test Tolerances analysis receiver test cases | 36.904 | 0% | [20 empty] | 0%
Test Point analysis receiver and transmitter test cases | 36.905 | 0% | [20 empty] | 0%
5GS
5GS Common
Common test environment | 38.508-1 | 0% |  |  | 0%
Common ICS | 38.508-2 | 0% |  |  | 0%
UE specific test functions | 38.509 | 0% |  |  | 0%
NR RF/RRM
FR1 RF common parts | 38.521-5 | 0% |  |  | 0%
FR1 RF Tx test cases | 38.521-5 Tx | 0% |  |  | 0%
FR1 RF Rx test cases | 38.521-5 Rx | 0% |  |  | 0%
RF Demod/QSI test cases | 38.521-5 Demod | 0% | 0 | 1 (+1) | 0% | 0 | 1 (+1)
RRM test cases | 38.533 | 0% | 0 | 5 (+5) | 0% | 0 | 5 (+5)
Applicability RF. Demod/QSI and RRM test cases | 38.522 | 0% |  |  | 0%
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 0% |  |  | 0%
Test Point analysis receiver and transmitter test cases | 38.905 | 0% |  |  | 0%
5 References
[1] RP-252575 | UE Conformance - Enhanced requirements and conductive test methodology for NR NTN and IoT NTN
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance - Enhanced requirements and conductive test methodology for NR NTN and IoT NTN | [12 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | [8 empty] | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_IoT_NTN_req_test_enh-UEConTest
WP Scope: |  | The objective of this work item is to enable UE conformance testing for the Rel-19 NTN enhancements WI which includes analysing the requirements, creation of corresponding test cases by defining the test environment, special conformance testing function, test procedure, message contents, MU/TT analysis, associated PICS, applicability and updating the relevant conformance specifications. The conformance testing aspects for this WI would consist of below areas:  UE RF test cases for：  HPUE requirements for NR NTN,  HPUE requirements for NB-IoT NTN,  NTN (NR and NB-IoT) testing NGSO channel model  NR NTN less than 5MHz  UE DEMOD test cases for:  NTN (NR and NB-IoT) testing NGSO channel model  NR NTN less than 5MHz  RRM test cases for:  NTN (NR and NB-IoT) testing NGSO channel model  NR NTN less than 5MHz Note: Applicability of Rel-19 satellite propagator model for Rel-19 SIG test case is pending RAN4 conclusions of the test requirements scope. | [14 empty] | vs Area
WP Resp: |  | Sunlin Zhu |  |  | zhusunlin@xiaomi.com | [5 empty] | WP item completion |  |  |  |  | SA Option 2 (SA NR) |  |  | NSA Option 3 (EN-DC) |  |  | LTE
TS Resp: |  | N/A |  |  | N/A
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) | LTE |  | FR1 | FR2 | FR1 + FR2 | FR1 | FR2 | FR1 + FR2 | FDD | TDD | FDD + TDD
[14 empty] | Overall |  | 5% (+5%) | [5 empty] | 10.8% (+10.8%)
[14 empty] | Number of WP items |  | 49 (+49) | 0 | 0 | 0 | 0 | 0 | 21 (+21) | 0 | 0
[14 empty] | Sum weight of WP items |  | 38.1 (+38.1) | 0 | 0 | 0 | 0 | 0 | 16.5 (+16.5) | 0 | 0
[14 empty] | Contribution by work plan analysis |  | 5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
|  | 36.508 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 36.508 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 36.508 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | 1 | 0% |  |  | 0% | [7 empty] | 0%
TS 36.509: UE specific testing functions
|  | 36.509 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 36.509 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 36.509 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | 1 | 0% |  |  | 0% | [7 empty] | 0%
LTE RF/RRM
TS 36.521-4: RF test cases - Common parts (general clauses, Annexes)
|  | 36.521-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 36.521-4 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 36.521-4 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | 1
TS 36.521-4: RF test cases - Tx
|  | 36.521-4 Rx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 36.521-4 Rx | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 36.521-4 Rx | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD |  | 36.521-4 Tx | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
|  | 36.521-4 Tx | 6.2A.1 | UE maximum output power for category M1 | new test case for Iot-NTN HPUE UE maximum output power for category M1 | Xiaomi | TSG RAN#114(Dec-26) |  |  | 1 | 0% |  |  | 0% | [7 empty] | 0%
|  | 36.521-4 Tx | 6.2A.2 | UE maximum output power reduction for category M1 | new test case for Iot-NTN HPUE UE maximum output power reduction for category M1 | Xiaomi | TSG RAN#114(Dec-26) |  |  | 1 | 0% |  |  | 0% | [7 empty] | 0%
|  | 36.521-4 Tx | 6.2A.3 | UE additional maximum output power reduction for category M1 UE | new test case for Iot-NTN HPUE UE additional maximum output power reduction for category M1 UE | Xiaomi | TSG RAN#114(Dec-26) |  |  | 1 | 0% |  |  | 0% | [7 empty] | 0%
|  | 36.521-4 Tx | 6.2A.4 | Configured transmitted Power for category M1 | new test case for Iot-NTN HPUE Configured transmitted Power for category M1 | SGS | TSG RAN#114(Dec-26) |  |  | 1 | 0% |  |  | 0% | [7 empty] | 0%
|  | 36.521-4 Tx | 6.2B.1 | UE maximum output power for category NB1 and NB2 | new test case for Iot-NTN HPUE UE maximum output power for category NB1 and NB2 | Ericsson | TSG RAN#114(Dec-26) | R5-256863 |  | 1 | 100% (+100%) |  |  | 100% (+100%) | [7 empty] | 100%
|  | 36.521-4 Tx | 6.2B.2 | UE maximum output power reduction for category NB1 and NB2 | new test case for Iot-NTN HPUE UE maximum output power reduction for category NB1 and NB2 | Ericsson | TSG RAN#114(Dec-26) |  |  | 1 | 0% |  |  | 0% | [7 empty] | 0%
|  | 36.521-4 Tx | 6.2B.3 | UE additional maximum output power reduction for category NB1 and NB2 UE | new test case for Iot-NTN HPUE UE additional maximum output power reduction for category NB1 and NB2 UE | Ericsson | TSG RAN#114(Dec-26) |  |  | 1 | 0% |  |  | 0% | [7 empty] | 0%
|  | 36.521-4 Tx | 6.2B.4 | Configured transmitted Power for category NB1 and NB2 | new test case for Iot-NTN HPUE Configured transmitted Power for category NB1 and NB2 | Ericsson | TSG RAN#114(Dec-26) |  |  | 1 | 0% |  |  | 0% | [7 empty] | 0%
TS 36.521-4: RF test cases - Rx
|  | 36.521-4 Rx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 36.521-4 Rx | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 36.521-4 Rx | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD |  | 36.521-4 Rx | 7.3A | Reference sensitivity power level for UE category M1 | new test case for Iot-NTN HPUE Reference sensitivity power level for UE category M1 |  | TSG RAN#114(Dec-26) |  |  | 1 | 0% |  |  | 0% | [7 empty] | 0%
TS 36.521-4: Demod/CSI reporting test cases
|  | 36.521-4 Demod |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 36.521-4 Demod | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 36.521-4 Demod | 8.1.2.3(new) | Applicability of requirements for different channel modelling | <Describe required change of the existing test case> | Xiaomi | TSG RAN#114(Dec-26) |  |  | 0.1 | 0% |  |  | 0% | [7 empty] | 0%
TBD | Y | 36.521-4 Demod | 8.2.1.1.1 | Single-antenna port performance | Test Purpose(s): <Describe test purpose(s)> | Xiaomi | TSG RAN#114(Dec-26) |  |  | 1 | 0% |  |  | 0% | [7 empty] | 0%
|  | 36.521-4 Demod | 8.3.1.1 | NPDSCH demodulation requirements |  | Sporton | TSG RAN#114(Dec-26) |  |  | 0.1 | 0% |  |  | 0% | [7 empty] | 0%
| Y | 36.521-4 Demod | 8.3.1.1.1 | Single-antenna port performance |  | Sporton | TSG RAN#114(Dec-26) |  |  | 1 | 0% |  |  | 0% | [7 empty] | 0%
|  | 36.521-4 Demod | Annex A.3 | Testing related to Satellite Access |  | SGS | TSG RAN#114(Dec-26) |  |  | 0.1 | 0% |  |  | 0% | [7 empty] | 0%
|  | 36.521-4 Demod | Annex E | Modelling of time varying Doppler shift and propagation delay for NGSO |  | SGS | TSG RAN#114(Dec-26) |  |  | 0.1 | 0% |  |  | 0% | [7 empty] | 0%
TS 36.521-2: Applicability for RF, Demod/CSI reporting and RRM test cases
TBD |  | 36.521-2 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1
TBD |  | 36.521-2 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced for 36.521-1 and 38.521-3. |  | TBD |  |  | 0.1 | 0% |  |  | 0% | [7 empty] | 0%
TS 36.521-3: RRM test cases
|  | 36.521-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 36.521-3 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 36.521-3 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 36.521-3 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TR 36.903: Test Tolerances analysis RRM test cases
|  | 36.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 36.903 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 36.903 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | 1 | 0% |  |  | 0% | [7 empty] | 0%
TR 36.904: Test Tolerances analysis receiver test cases
|  | 36.904 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 36.904 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 36.904 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | 1 | 0% |  |  | 0% | [7 empty] | 0%
TR 36.905: Test Point analysis receiver and transmitter test cases
|  | 36.905 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 36.905 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 36.905 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | 1 | 0% |  |  | 0% | [7 empty] | 0%
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.508-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.508-1 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | 1 | 0% | 0% |  |  |  | 0%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.508-2 | <Clause> | <Title> | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. |  | TBD |  |  | 1 | 0% | 0% |  |  |  | 0%
TS 38.509: UE specific testing functions
|  | 38.509 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.509 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.509 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | 1 | 0% | 0% |  |  |  | 0%
NR RF/RRM
TS 38.521-5: FR1 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.521-1 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
|  | 38.521-5 | 5.2.2 | Operating bands with conducted requirements | new TC for less than 5MHz NTN Operating bands with conducted requirements | Xiaomi | TSG RAN#114(Dec-26) |  |  | 0.1 | [5 empty] | 0%
|  | 38.521-5 | 5.3.2 | Maximum transmission bandwidth configuration | new TC for less than 5MHz NTN Maximum transmission bandwidth configuration | Xiaomi | TSG RAN#114(Dec-26) |  |  | 0.1 | [5 empty] | 0%
|  | 38.521-5 | 5.3.3 | Minimum guardband and transmission bandwidth configuration | new TC for less than 5MHz NTN Minimum guardband and transmission bandwidth configuration | Xiaomi | TSG RAN#114(Dec-26) |  |  | 0.1 | [5 empty] | 0%
|  | 38.521-5 | 5.3.5 | UE channel bandwidth per operating band | new TC for less than 5MHz NTN UE channel bandwidth per operating band | KTL | TSG RAN#114(Dec-26) |  |  | 0.1 | [5 empty] | 0%
|  | 38.521-5 | 5.3.6 | Asymmetric channel bandwidths | new TC for less than 5MHz NTN Asymmetric channel bandwidths | KTL | TSG RAN#114(Dec-26) |  |  | 0.1 | [5 empty] | 0%
|  | 38.521-5 | 5.4.3.1 | Synchronization raster and numbering | new TC for less than 5MHz NTN Synchronization raster and numbering | KTL | TSG RAN#114(Dec-26) |  |  | 0.1 | [5 empty] | 0%
|  | 38.521-5 | 5.4.3.3 | Synchronization raster entries for each operating band | new TC for less than 5MHz NTN Synchronization raster entries for each operating band | KTL | TSG RAN#114(Dec-26) |  |  | 0.1 | [5 empty] | 0%
TS 38.521-5: FR1 RF test cases - Tx
|  | 38.521-5 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-5 Tx | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.521-5 Tx | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD |  | 38.521-5 Tx | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TBD |  | 38.521-5 Tx | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1 | 0% | 0% |  |  |  | 0%
|  | 38.521-5 Tx | 6.2.1 | UE maximum output power | new test case for NR-NTN HPUE UE maximum output power | Xiaomi | TSG RAN#114(Dec-26) |  |  | 1 | 0% | 0% |  |  |  | 0%
|  | 38.521-5 Tx | 6.2.1 | UE maximum output power | new test casefor less than 5MHz NTN maximum output power | Xiaomi | TSG RAN#114(Dec-26) |  |  | 1 | 0% | 0% |  |  |  | 0%
|  | 38.521-5 Tx | 6.2.2 | UE maximum output power reduction | new test case for NR-NTN HPUE UE maximum output power reduction | Xiaomi | TSG RAN#114(Dec-26) |  |  | 1 | 0% | 0% |  |  |  | 0%
|  | 38.521-5 Tx | 6.2.3 | UE additional maximum output power reduction | new test case for NR-NTN HPUE UE additional maximum output power reduction | Xiaomi | TSG RAN#114(Dec-26) |  |  | 1 | 0% | 0% |  |  |  | 0%
|  | 38.521-5 Tx | 6.2.4 | Configured transmitted power | new test case for NR-NTN HPUE Configured transmitted power | Ericsson | TSG RAN#114(Dec-26) |  |  | 1 | 0% | 0% |  |  |  | 0%
|  | 38.521-5 Tx | 6.2.3 | UE additional maximum output power reduction | new test case for less than 5MHz NTN UE additional maximum output power reduction | Ericsson | TSG RAN#114(Dec-26) |  |  | 1 | 0% | 0% |  |  |  | 0%
|  | 38.521-5 Tx | 6.3.1 | Minimum output power | new test case for less than 5MHz NTN UE Minimum output power | Sporton | TSG RAN#114(Dec-26) |  |  | 1 | 0% | 0% |  |  |  | 0%
|  | 38.521-5 Tx | 6.3.2 | Transmit OFF power | new test case for less than 5MHz NTN UE Transmit OFF power | Sporton | TSG RAN#114(Dec-26) |  |  | 1 | 0% | 0% |  |  |  | 0%
|  | 38.521-5 Tx | 6.5.1 | Occupied bandwidth | new test case for less than 5MHz NTN UE Occupied bandwidth | Sporton | TSG RAN#114(Dec-26) |  |  | 1 | 0% | 0% |  |  |  | 0%
|  | 38.521-5 Tx | 6.5.2.2 | Spectrum emission mask | new test case for less than 5MHz NTN UE Spectrum emission mask | Sporton | TSG RAN#114(Dec-26) |  |  | 1 | 0% | 0% |  |  |  | 0%
|  | 38.521-5 Tx | 6.5.2.4.1 | NR ACLR | new test case for NR-NTN HPUE NR ACLR | Sporton | TSG RAN#114(Dec-26) |  |  | 1 | 0% | 0% |  |  |  | 0%
|  | 38.521-5 Tx | 6.5.2.4.1 | NR ACLR | new test case for less than 5MHz NTN UE NR ACLR | Sporton | TSG RAN#114(Dec-26) |  |  | 1 | 0% | 0% |  |  |  | 0%
|  | 38.521-5 Tx | 6.5.3.1 | General spurious emissions | new test case for less than 5MHz NTN General spurious emissions | KTL | TSG RAN#114(Dec-26) |  |  | 1 | 0% | 0% |  |  |  | 0%
|  | 38.521-5 Tx | 6.5.3.3 | Additional spurious emissions | new test case for less than 5MHz NTN Additional spurious emissions | KTL | TSG RAN#114(Dec-26) |  |  | 1 | 0% | 0% |  |  |  | 0%
TS 38.521-5: FR1 RF test cases - Rx
|  | 38.521-5 Rx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 38.521-5 Rx | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
|  | 38.521-5 Rx | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
|  | 38.521-5 Rx | 7.3.2 | Reference sensitivity power level | new test case for NR-NTN HPUE Reference sensitivity power level | Xiaomi | TSG RAN#114(Dec-26) |  |  | 1 | 0% | 0% |  |  |  | 0%
|  | 38.521-5 Rx | 7.3.2 | Reference sensitivity power level | new test case for less than 5MHz NTN UE Reference sensitivity power level | Xiaomi | TSG RAN#114(Dec-26) |  |  | 1 | 0% | 0% |  |  |  | 0%
|  | 38.521-5 Rx | 7.4 | Maximum input level | new test case for less than 5MHz NTN UE Maximum input level | Xiaomi | TSG RAN#114(Dec-26) |  |  | 1 | 0% | 0% |  |  |  | 0%
|  | 38.521-5 Rx | 7.5 | Adjacent channel selectivity | new test case for less than 5MHz NTN UE Adjacent channel selectivity | Sporton | TSG RAN#114(Dec-26) |  |  | 1 | 0% | 0% |  |  |  | 0%
|  | 38.521-5 Rx | 7.6.2 | In-band blocking | new test case for less than 5MHz NTN UE In-band blocking | Sporton | TSG RAN#114(Dec-26) |  |  | 1 | 0% | 0% |  |  |  | 0%
|  | 38.521-5 Rx | 7.6.3 | Out-of-band blocking | new test case for less than 5MHz NTN UE Out-of-band blocking | KTL | TSG RAN#114(Dec-26) |  |  | 1 | 0% | 0% |  |  |  | 0%
|  | 38.521-5 Rx | 7.6.4 | Narrow band blocking | new test case for less than 5MHz NTN UE Narrow band blocking | Sporton | TSG RAN#114(Dec-26) |  |  | 1 | 0% | 0% |  |  |  | 0%
|  | 38.521-5 Rx | 7.7 | Spurious response | new test case for less than 5MHz NTN UE Spurious response | KTL | TSG RAN#114(Dec-26) |  |  | 1 | 0% | 0% |  |  |  | 0%
TS 38.521-5: Demod/CSI reporting test cases
|  | 38.521-5 Demod |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-5 Demod | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD | Y | 38.521-5 Demod | 8.2.1.2.2.1.1 new | PDSCH demodulation performance requirements for NTN testing for NGSO | Verify the PDSCH mapping Type A normal performance under 2 receive antenna conditions and with different channel models and MCS for NGSO | SGS | TSG RAN#114(Dec-26) |  |  | 1 | 0% | 0% |  |  |  | 0%
|  | 38.521-5 Demod | Annex A.4 | Testing related to Satellite Access | This annex specifies the methodologies for time varying doppler shift and propagation delay modelling for NGSO. | SGS | TSG RAN#114(Dec-26) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
|  | 38.521-5 Demod | Annex F | TBD | TBD | SGS | TSG RAN#114(Dec-26) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
|  | 38.521-5 Demod | Annex new | Modelling of time varying Doppler shift and propagation delay for NGSO |  | SGS | TSG RAN#114(Dec-26) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
|  | 38.521-5 Demod | [8 empty] | 0% | 0% |  |  |  | 0%
TS 38.522: Applicability for RF, Demod/CSI reporting and RRM test cases
TBD |  | 38.522 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1
TBD |  | 38.522 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced for 38.521-x and 38.533. |  | TBD |  |  | 0.1 | 0% | 0% |  |  |  | 0%
TS 38.533: RRM test cases
|  | 38.533 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.533 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.533 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.533 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
| Y | 38.533 | 14.1.X | Cell reselection to FR1 intra-frequency NR case for UE operating on a cell with less than 5 MHz BW | This test is to verify the requirement for the intra frequency NR cell reselection requirements for satellite access specified in clause 4.2C.2.3 for UE capable of operating on a cell with less than 5 MHz BW. | SGS | TSG RAN#114(Dec-26) |  |  | 1 | 0% | 0% |  |  |  | 0%
| Y | 38.533 | 14.2.2.X | RACH-based hard Satellite switching with re-synchronization from FR1 to FR1 for less than 5MHz with NTN | The purpose of this test is to verify that the UE makes correct reporting of an event. This test will partly verify the SA inter-frequency NR cell search requirements in clause 9.3C.4. This test is applicable for UEs that support less than 5 MHz operation. | SGS | TSG RAN#114(Dec-26) |  |  | 1 | 0% | 0% |  |  |  | 0%
| Y | 38.533 | 14.4.1.X | Radio Link Monitoring Out-of-sync Test for FR1 SAN PCell configured with SSB-based RLM RS in non-DRX mode | The purpose of this test is to verify that the UE supporting support-3MHz-ChannelBW-r18 properly detects the out of sync for the purpose of monitoring downlink radio link quality of the PCell operating on a 3 MHz channel bandwidth. | China Unicom | TSG RAN#114(Dec-26) |  |  | 1 | 0% | 0% |  |  |  | 0%
| Y | 38.533 | 14.4.1.Y | Radio Link Monitoring In-sync Test for FR1 SAN PCell configured with SSB-based RLM RS in DRX mode for less than 5 MHz BW | The purpose of this test is to verify that the UE supporting support-3MHz-ChannelBW-r18 properly detects the out of sync and in sync for the purpose of monitoring downlink radio link quality of the PCell operating on a 3 MHz channel bandwidth. This test will partly verify the FR1 radio link monitoring requirements in clause 8.1C. | Xiaomi | TSG RAN#114(Dec-26) |  |  | 1 | 0% | 0% |  |  |  | 0%
| Y | 38.533 | 14.4.2.X | Beam Failure Detection and Link Recovery Test for FR1 PCell for satellite access configured with SSB-based BFD and LR in non-DRX mode for a UE operating on a cell with less than 5 MHz BW | The purpose of this test is to verify that the UE supporting support-3MHz-ChannelBW-r18 properly detects SSB-based beam failure in the set q0 configured for a serving cell which is served by satellite access node (SAN) and operatw on a less than 5 MHz bandwidth, and that the UE performs correct SSB-based link recovery based on beam candidate set q1. The purpose is to test the downlink monitoring for beam failure detection within the UEs active DL BWP, during the evaluation period, and link recovery, when no DRX is used. | CAICT | TSG RAN#114(Dec-26) |  |  | 1 | 0% | 0% |  |  |  | 0%
| Y | 38.533 | 14.5.1.x | SA event triggered reporting tests without gap under non-DRX with SSB index reading under less 5MHz BW | The purpose of this test is to verify that the UE makes correct reporting of an event. | CAICT | TSG RAN#114(Dec-26) |  |  | 1 | 0% | 0% |  |  |  | 0%
| Y | 38.533 | 14.5.2.x | SA event triggered reporting tests for FR1 with SSB time index detection when DRX is used with single gap for 3 MHz channel bandwidth in satellite access | This test is to verify the requirement for RACH-based hard satellite switching with re-synchronization from SAN FR1 to SAN FR1 for unknown target cell operating with 12 PRB SSB bandwidth specified in clause 6.1C.3. | R&S | TSG RAN#114(Dec-26) |  |  | 1 | 0% | 0% |  |  |  | 0%
| Y | 38.533 | 14.2.x | Intra-frequency SAN time-based conditional Handover from FR1 to FR1 for UE operating on a cell with less than 5 MHz BW | This test is to verify the requirement for NR FR1 NTN- NR FR1 NTN intra-frequency SAN handover requirements for unknown target cell operating with 12 PRB SSB bandwidth specified in clause 6.1C.1. | CAICT | TSG RAN#114(Dec-26) |  |  | 1 | 0% | 0% |  |  |  | 0%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.903 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.903 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | 1 | 0% | 0% |  |  |  | 0%
TR 38.905: Test Point analysis receiver and transmitter test cases
|  | 38.905 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.905 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.905 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | 1 | 0% | 0% |  |  |  | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.