## Slide 1
3GPP Work Plan
Review at Plenary #108
Source: MCC / Work Plan Manager (A. Sultan)
Agenda item: Review of the Work Plan
Document for: Information
Review based on the latest available version of the Work Plan, available at: https://ftp.3gpp.org/Information/WORK_PLAN
Includes: - the progress on all WIDs, as indicated in the WG Chairs’ reports (CT & SA) and in the Status Report (RAN), - the new WIDs proposed by SA/CT WGs to this TSG (will be removed if not TSG-approved)
- RAN Report to SA (SP-250800), CT Report to SA (SP-250776)
Does not include: - the company-proposed WIDs proposed/approved at this TSG, the revised WID/SID during this TSG
Warnings :
- This review is a high-level view of the 3GPP progress. It is based on the 3GPP Work Plan, a continuously updated document.
Some misalignments might temporarily appear on some individual items.
- Some WG cannot progress because of reasons beyond their control (e.g. dependencies with other groups).
These slides shall not be used to judge the “efficiency” of whatever WG.
© 3GPP 2025
SP-250713 (rev of rev of RP-250840 , CP-251011 ) 3GPP TSG#108, 9 -13 June 2025, Prague, Czech Republic

## Slide 2: Content of this Work Plan review
Snapshot of all ongoing/future Releases
Ongoing Releases
  Rel-19 Timeline and Progress
  Rel-20 Timeline and Progress
  Rel-21 Timeline and Progress
Background information

## Slide 3
Releases 19 to 21 timelines
#108
Release 19
Note: All starting dates are indicative
#110
#112
#114
#116
#118
#120
#122
#124
#126
2025
2026
2028
*: +3 months for RAN4
**: - 3 months for RAN1 & + 3 months for RAN4 perf
#111
#113
#115
#119
#121
#123
#125
2027
2029
5GA Stage 1
RAN Completion**
Stage 3 (CT & SA)
ASN.1
&
Open
APIs
Stage 2
#117
#109
2024
#104
#106
#107
#105
Mar.
#103
TSGs
Mar.
Mar.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Jun.
Jun.
Jun.
Sep.
Sep.
Sep.
Sep.
Sep.
Sep.
Dec.
Dec.
Dec.
Dec.
Dec.
Dec.
Now
SA1 St.1, Content Definition (RAN & SA St.2): completed Dec. 2023
Release 20 5GA
Release 20 FS_6G
5GA Stage 2
5GA RAN Completion**
5GA Stage 3
Chart showing Normative dates
(timeline for 5GA studies not shown)
Chart showing Studies dates
(no 6G normative work in Rel-20)
FS_6G Stage 1
FS_6G RAN P
FS_6G Stage 2
or
FS_6G RAN WG**
FS_6G Stage 3
TBD
Release 21 6G
Rel-21 timeline to be decided no later than June 2026
ITU deadlines for 6G: March 2029 for technology proposal, mid-2030 for specifications
ASN.1

## Slide 4: Content of this Work Plan review
Snapshot of all ongoing Releases
Rel-19 Timeline and Progress
Rel-20 Timeline and Progress
Rel-21 Timeline and Progress
Background information

## Slide 5
Release 19 timeline
#101
Note: All starting dates are indicative
#102
#103
#104
#105
#106
#107
#108
#109
#110
#111
#112
#99
RAN4
content def.
RAN Content def.
2024
2025
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Mar.
Dec.
Dec.
Dec.
2026
RAN4_Perf
Stage 3 (CT & SA)
RAN1
Stage 2 (SA2, SA6,…) Normative
RAN Completion (RAN2/3/4core)
ASN.1 & Open APIs
St.2 Content approval
#100
Jun.
2023
Now
100%
SA1 Stage 1 80%
TSGs
RAN Rel-19 workshop
SA Rel-19
Workshop

## Slide 6: Release 19 progress overview (1/2)
SA1 (Stage 1): completed and stable (14 Studies, 25 Normative items)
SA2, SA6 (Stage 2): completed (24 Studies, 72 Normative items), with 3 exceptions:
  Stage 2 for :
    AI/ML (UID 1040033, AIML_CN) (was 98%, now 99%)
    NG_RTC_Phase 2 (UID 1040026) (was 98%, now 99%)
    Ambient-IoT (introduced at SA#107, now 90%)

## Slide 7: Release 19 progress overview (2/3)
RAN
  Studies: 12 studies (against 11 at previous TSG), OCI = 96 % (against 76% at previous TSG)
  RAN Core: 55 items (against 54 at previous TSG), OCI = 84 % (against 64% at previous TSG)
    RAN2/RAN3/RAN4Core: Items on time for their target by Sept. 2025
    RAN1 : the main part of all the normative items completed at RAN#108, as per schedule .These items are:
  RAN4Perf: 37 items (against 36 at previous TSG), OCI = 45 % (against 23% at previous TSG)
    About half of the items are now scheduled to be completed by March 2026 (a quarter later than original Rel-19 timeline)
1021095 | Core part: Enhancements of Network energy savings for NR | Netw_Energy_NR_enh-Core | 90%
1021094 | Core part: Low-power wake-up signal and receiver for NR (LP-WUS/WUR) | NR_LPWUS-Core | 90%
1021093 | Core part: Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface | NR_AIML_air-Core | 85%
1061084 | Core part: Solutions for Ambient IoT (Internet of Things) in NR | Ambient_IoT_Solutions-Core | 84%
1051123 | Core part: Introduction of IoT-NTN TDD mode | IoT_NTN_TDD-Core | 76%
1051120 | Core part: Multi-carrier enhancements for NR Phase 2 | NR_MC_enh2-Core | 90%
1021089 | Core part: NR MIMO Phase 5 | NR_MIMO_Ph5-Core | 95%
1021090 | Core part: Evolution of NR duplex operation: Sub-band full duplex (SBFD) | NR_duplex_evo-Core | 93%
1061081 | Core part: LTE-based 5G Broadcast Phase 2 | LTE_terr_bcast_Ph2-Core | 95%

## Slide 8: Release 19 progress overview (3/3)
SA 3/4/5 & CT
  SA3/4/5:
    Studies: 53 studies (same at previous TSG), OCI = 95 % (against 90 % at previous TSG)
    Normative: 74 items (against 67 at previous TSG), OCI = 67 % (against 43 % at previous TSG)
    TARGET remains September 2025
  CT WG:
    Studies: 5 studies (against 4 at previous TSG), OCI = 80 % (against 85% at previous TSG)
    Normative: 123 items (against 112 at previous TSG), OCI = 78% (against 55% at previous TSG)
    CT #108: some blocking points in Stage 2 (see CT report to SA in SP-250776), such as 5G_ProSe_Ph3, MINT_Ph2, Ambient IoT, and Shared Data Handling on Nudm and Nudr (Shared_Data). SA has taken note and all these items will be closed in the next SA WGs meeting.
    TARGET remains September 2025

## Slide 9: Content of this Work Plan review
Snapshot of all ongoing Releases
Rel-19 Timeline and Progress
Rel-20 Timeline and Progress
Rel-21 Timeline and Progress
Background information

## Slide 10: Release 20: introduction
Rel-20 has 2 components: “Rel-20_5GA” and “Rel-20_6G” (or “Rel-20_FS_6G”)
  Rel-20_5GA covers 5GA studies and normative;
  Rel-20_6G covers 6G studies only (6G normative in Rel-21)
  Up to each TSG/WG how to split their time on each component (e.g. in SA1, it was initially at 50%-50%)

## Slide 11
2024
#103
Mar.
#111
Mar.
#107
Mar.
#104
Jun.
#108
Jun.
#112
Jun.
#105
Sep.
#109
Sep.
#102
Dec.
#106
Dec.
#110
Dec.
Now
TSGs
SA1 5GA SID definition
100%
SA1 5GA Studies + Norm 80%
100%
St. 2 (SA2, SA6, …) 5GA St.+Norm 80%
Stage 3 5GA St + Norm
#113
Sep.
#114
Dec.
#115
Mar.
Jun
RAN1
RAN Completion (RAN2/3/4core)
#116
RAN4 C.def.
RAN4 Perf
RP Content def.
2025
2026
2027
5GA ASN.1 & Open APIs
St.3 SID def. TBD
Release 20 5GA timeline
Note: All starting dates are indicative
Workshops
5GA RAN & SA
RAN WG SID def.
St.2 SID def.

## Slide 12: Release 20 5GA progress overview (1/5)
Stage 1:
  Target: Deadline for Stage 1 is now (both for Studies and Normative)
  Actual progress: All completed (studies and normative) except:
    FRMCS_Ph6-REQ: 10%, exception requested until September
1030042 | Study on satellite access - Phase 4 | FS_5GSAT_Ph4 | 100%
1060071 | Stage 1 for Satellite access - Phase 4 | 5GSAT_Ph4-REQ | 100%
1050105 | Indirect Network Sharing on Satellite Access Network | INS_SAT | 100%
1060072 | MPS support in 3GPP system with satellite | MPS_Sat | 100%
1030044 | Study on Energy Efficiency as Service Criteria Phase 2 | FS_EnergyServ_Ph2 | 100%
1070051 | Stage 1 for Energy Efficiency as Service Criteria Phase 2 | EnergyServ_Ph2-REQ | 100%
1050106 | Stage 1 for Indirect Network Sharing Phase 2 | NetShare_Ph2-REQ | 100%
1030043 | Study on FRMCS Phase 6 | FS_FRMCS_Ph6 | 100%
1070054 | Stage 1 for FRMCS Phase 6 | FRMCS_Ph6-REQ | 10%
1070052 | Stage 1 of Phase 2 of SMS to Emergency Centre | SMS2EC_Ph2-REQ | 100%
1060070 | Vehicle-Mounted Relays Phase3 | VMR_Ph3 | 100%
1050107 | Resident Phase 2 | Resident_Ph2 | 100%
1080047 | CPAS specific requirement | CPAS-REQ | 100%
1070053 | Stage 1 for Ambient listening enhancements including pause and resume in MCS | ALPR-REQ | 100%
1050108 | Combined QoS configuration and monitoring | CombQoS | 100%
1050109 | Legacy Residential Gateway Supporting 5G LAN-type Service | LegacyRG_5GLAN | 100%
1050111 | Exposure for Virtual Network information and capability | VNExposure | 100%

## Slide 13: Release 20 5GA progress overview (2/5)
Stage 2:
  Remaining SA2 5GA SIDs approved at SA#108, as per schedule
  SA2 studies (UIDs in the 108series were approved at SA#108):
  Current SA2 normative (UIDs in the 108series were approved at SA#108):
  Note that some acronyms/names might have slightly changed during the approval process
  See also SA/SA2 chair’s doc SP-250832 on “SA2 Rel-20 5GAanced Prioritization table”
Unique_ID | Name | Acronym | %Complete
1070011 | Study on Integration of satellite components in the 5G architecture Phase 4 | FS_5GSAT_Ph4_ARC | 0%
1070058 | Study on Energy Efficiency and Energy Saving Phase2 | FS_EnergySys_Ph2 | 0%
1080062 | Study on [phase 2 of] Short Message Service to Emergency Response Centre | FS_SMS2EC_Ph2_ARC | 0%
1080060 | Study on system architecture for Phase 3 of NG RTC | FS_NG_RTC_Ph3_ARC | 0%
1080061 | Study on MPS Enhancements for IoT | FS_MPS_IOT_ARC | 0%
1080063 | Study on Architecture support of Ambient power-enabled Internet of Things - Phase 2 | FS_AmbientIoT_Ph2_ARC | 0%
1070013 | Study on Core Network Enhanced Support for Artificial Intelligence (AI) / Machine Learning (ML) Phase 2 | FS_AIML_CN_Ph2 | 0%
1070012 | Study on Stage 2 for Integrated Sensing and Communication | FS_Sensing_ARC | 0%
1080059 | Stage 2 for Indirect Network Sharing Phase2 | NetShare_Ph2-ARC | 0%
1080058 | 5G ProSe Phase 4 | ProSe_Ph4-ARC | 0%

## Slide 14: Release 20 5GA progress overview (3/5)
Stage 2 (cont’d):
  Current SA6 items (UIDs in the 108series were approved at SA#108):
Unique_ID | Name | Acronym | Finish | %Complete | Hyperlink
1080027 | Study on Phase 4 to application enablement for satellite access enabled 5G services | FS_5GSAT_Ph4_APP | Tue 03/03/26 | 0% | SP-250874
1080024 | Study on Application Enablement to support Energy Saving [Phase 2?] | FS_EnergySys_APP | Tue 03/03/26 | 0% | SP-250871
1070031 | Stage 2 for FRMCS Phase 6 | FRMCS_Ph6-MC | Sat 06/06/26 | 35% | SP-250390
1070025 | Study on Logging and recording of mission critical services, Phase 2 | FS_MCLOG_Ph2 | Tue 03/03/26 | 10% | SP-250380
1070024 | Study on Discreet listening and monitoring of mission critical services, Phase 2 | FS_MCDISC_Ph2 | Tue 03/03/26 | 10% | SP-250379
1070029 | Study on Stage 2 for AI/ML service Phase 2 | FS_AIML_App_Ph2 | Fri 12/12/25 | 40% | SP-250384
1080029 | Guidelines for 3GPP Application Enablement usage | AppEnable_EXT | Tue 03/03/26 | 0% | SP-250588
1080026 | Study of CAPIF Phase 4 | FS_CAPIF_Ph4 | Tue 03/03/26 | 0% | SP-250873
1080025 | Study on Application user consent | FS_APCOT | Tue 03/03/26 | 0% | SP-250872
1080023 | Study on application enablement for Ambient IoT [Phase 2? ] services | FS_AmbientIoT_APP | Tue 03/03/26 | 0% | SP-250870
1050034 | Study on Service Enabler Architecture Layer (SEAL) Phase 4 | FS_SEAL_Ph4 | Fri 12/12/25 | 75% | SP-250374
1070026 | Study on Application enabler for XR Services Phase 3 | FS_XRM_Ph3_APP | Fri 12/12/25 | 35% | SP-250381
1070027 | Study on SEAL data delivery Phase 3 | FS_SEALDD_Ph3 | Fri 12/12/25 | 30% | SP-250382
1070028 | Study on Stage 2 for MMTel Phase 2 | FS_MMTel_Ph2_APP | Tue 03/03/26 | 30% | SP-250383
1070030 | Stage 2 for Mission Critical Services for UE-to-UE and UE-to-Network over multi-hop relay | MultiHop-MC | Tue 03/03/26 | 0% | SP-250389
1070032 | Stage 2 for Enhanced Mission Critical Services Architecture Phase 2 | enhMC_Ph2-MC | Sat 06/06/26 | 15% | SP-250391
1070033 | Stage 2 for mobile metaverse services Phase 2 | Metaverse_Ph2-APP | Fri 12/12/25 | 45% | SP-250392
1080028 | Study on use of Sensing results for Vertical Applications | FS_Sensing_APP | Tue 03/03/26 | 0% | SP-250875

## Slide 15: Release 20 5GA progress overview (4/5)
RAN: RAN WG SIDs/WIDs approved at RAN#108, as per schedule
  5GA RAN1-led WIDs:
    AI/ML for NR air interface enhancements
    NR MIMO Phase 6
    NR coverage enhancements Phase 3
    Study on GNSS resilient NR-NTN operation
    Study on Integrated Sensing And Communication (ISAC) for NR
  5GA RAN2-led WIDs:
    Artificial Intelligence (AI)/Machine Learning (ML) for mobility in NR
    Non-Terrestrial Networks (NTN) for Internet of Things (IoT) Phase 4
    NR mobility enhancements Phase 5
    XR (eXtended Reality) for NR Phase 4
    E-UTRA TN to NR NTN handover enhancements
  5GA RAN3-led WIDs:
    Study on Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN Phase 3
    Data collection for SON /MDT in NR Phase 5
  WID on Ambient IoT still under discussion as this is written
RAN4 WIDs approval to be finalized at RAN#109

## Slide 16: Release 20 5GA progress overview (5/5)
Rel-20 5GA SA3/4/5 activities:
  Approved: New SID on Modernization of Specification Format and Procedures for 6G (SP-250802)
  Number of WIDs/SIDs submitted by SA3/4/5 WGs approved at SA#108 (TBC at the end of the meeting)
    SA WG3 (Study on Preparing for Transition to Post Quantum Cryptography in 3GPP in SP-250858; Mission Critical security for Release 20 in SP-250653; Security related Events Handling in SP-250876; Security Assurance Specification for 5GAdvanced in SP-250877)
    SA WG4 (Study on Media Energy Consumption Exposure and Evaluation Framework phase 2 in SP-250636; AI/ML for IMS services in SP-250878)
    SA WG5 Studies (Energy efficiency and energy saving aspects of 5G Advanced in SP-250860; intent driven management services for mobile network phase 4 in SP-250861; Management Data Analytics (MDA) - Phase 4 in SP-250862; SBMA enhancement phase 4 in SP-250863; Enhanced exposure of management services in SP-250864; Study for Data management phase 3 in SP-250865; Management aspect of Network Digital Twins phase 2 in SP-250866; AI/ML management enhancements in SP-250867; Closed Control Loop Management -Ph2 in SP-250868; Charging Aspects of CAPIF Phase 3 in SP-250869)
    SA WG5 Normative (5G performance measurements&KPIs and Trace&MDT&QoE in SP-250505 ; OAM for Extended Reality and Media service (XRM) Phase 2 in SP-250880; Enhancement of Management Aspects related to NWDAF Phase 3 in SP-250507 ; 5G Advanced NRM features phase 4 in SP-250508)
Stage 3 and CT: not started

## Slide 17
2024
#103
Mar.
#111
Mar.
#107
Mar.
#104
Jun.
#108
Jun.
#112
Jun.
#105
Sep.
#109
Sep.
#102
Dec.
#106
Dec.
#110
Dec.
Now
TSGs
Workshop 6G TSGs
CT & St. 3 6G SID def.
#113
Sep.
#114
Dec.
#115
Mar.
Jun
Workshop SA1 on IMT-2030 use cases
#116
SA1 6G Study(ies)
SA1 6G SID def.
RP IMT-2030 disc.
RP ITU Study
RP 6G Study(ies)
RAN1 6G Study(ies)
SA2 6G Study(ies)
Stage 3 6G Study(ies)
2025
2026
2027
SA2 & RAN WGs 6G SID def.
SA3/4/5/6 6G SID def. TBD
RAN2/3/4 6G Study(ies)
Release 20 (FS) 6G timeline
or
TBD
Note: All starting dates are indicative
SA3/4/5/6 6G Study(ies)TBD

## Slide 18: Release 20 FS_6G progress overview
Reminder: no normative work on 6G in Rel-20 (only studies)
Stage 1:
  Study on 6G Use Cases and Service Requirements (FS_6G_REQ, 1050110): TR 22.870
  66% complete, Expected completion by 03/03/2026
Stage 2: SA2 6G SID approved at SA#108 (“Study on Architecture for 6G System”, SP-250806, 0%)
RAN:
  RAN Plenary 6G work started Dec. 2024, now 10% (“Study on 6G Scenarios and requirements”)
  RAN WG 6G SID approved at RAN#108 (“Study on 6G Radio”, RP-251881)
Unique_ID | Name | Acronym | WG | Start | Finish | % | WID
 | Rel-20 6G Studies |  |  |  |  |  | 
1050110 | Study on 6G Use Cases and Service Requirements | FS_6G_REQ | S1 | Sept 24 | March 26 | 66% | SP-241391
1060079 | Study on 6G Scenarios and Requirements | FS_6G_RAN_Scen_Req | RP | Dec 24 | June 26 | 10% | RP-250810
1080057 | Study on Architecture for 6G System | FS_6G_ARC | S2 | June 25 | June 26 | 0% | SP-250806
+ “Study on 6G Radio” , RAN WGs, in RP-251881 (0%)
Stage 3 and CT: not started

## Slide 19: Content of this Work Plan review
Snapshot of all ongoing Releases
Rel-19 Timeline and Progress
Rel-20 Timeline and Progress
Rel-21 Timeline and Progress
Background information

## Slide 20: Release 21
Release 21 is the release for submission to IMT-2030*, aka 6G
This implies that 3GPP (normative) work will be submitted to ITU-R before 2030
  ASN.1/OpenAPI freeze date is no earlier than March 2029
Release 21 Freezing dates and other milestones TBD
  Rel-21 timeline is to be decided no later than June 2026
SA1 needs some Rel-21 planning already, at least for 5GA
  Since Stage 1 freeze date for Rel-20 5GA is now
  See SA1 chair contribution in SP-250623
Note that, as usual in 3GPP, previous Generations will in parallel continue to be maintained & enhanced in Rel-21 and after
* source: TSG#103-endorsed CT-240307/SP-240458/RP-240823

## Slide 21: Content of this Work Plan review
Snapshot of all ongoing Releases
Rel-18 Timeline and Progress
Rel-19 Timeline and Progress
Rel-20 Timeline and Progress
Rel-21 Timeline and Progress
Background information

## Slide 22: Background information (1/2): overall background information
Dedicated e-mail list for Work Plan aspects
Open to everyone interested (rapporteus, chairs, delegates, etc.) by sending the message “Subscribe 3GPP_WORKPLAN” to the address LISTSERV@LIST.ETSI.ORG
For comments/update to the Work Plan, please use the 3GPP_WORKPLAN list
Editorial comments can be sent directly to: alain.sultan@etsi.org
3GPP Work Plan
http://www.3gpp.org/ftp/Information/WORK_PLAN
Contains Release 1999 to Release 20; Master version in MS Project; Working versions in Excel
Tutorials on content, maintenance and other info on the Work Plan in subfolder /info
3GPP Releases Descriptions – R99 to Rel-18
http://www.3gpp.org/ftp/Information/WORK_PLAN/Description_Releases/
“Releases Descriptions” for Releases 8 to 13: limited to copy-paste of the WIDs.
“Releases Descriptions” for Releases 14 to 18: TR 21.9xx: “Release xx Description; Summary of Rel-xx Work Items”, written in collaboration with all the Rel-xx Features Rapporteurs
3GPP Releases Descriptions – Rel-19
To be started September or December 2025 (time for work to stabilise)

## Slide 23: Background information (2/2): Relationship between WGs, Stages and deadlines
Most 3GPP Working Groups handle only one Stage:
  SA1  Stage 1
  SA2  Stage 2; SA6  Stage 2
  CT WGs  Stage 3 (also Stage 2 for some specific items)
SA3, SA4 and SA5 handle several Stages for some or all their WIDs:
  SA3: handles Stages 2 and 3 for all its WIDs. Stage 2 at SA3 is one quarter after SA2/SA6’s deadline, but this date is an SA3-internal date since there is no dependency (i.e. SA3 is not expecting work from any other WGs)
  SA4: handles Stage 2 for some WIDs (for which SA4 might rely on CT WGs for Stage 3), and Stage 3 for a majority of its WIDs. Stage 2 WIDs in SA4 are clearly identified as such and have the same deadline as SA2/SA6’s date.
  SA5: handles Stages 1, 2 and 3 for all its WIDs. Stage 1 for SA5 is 4 quarters after SA1’s date. Stage 2 for SA5 is 2 quarters after SA2/SA6’s date. Stage 3 for SA5 is same date as CT WGs’ date.
  For SA3, SA4 and SA5, the completion date for all WIDs dealing with Stage 3 (fully or partially) is the same as for CT WGs.
  In this Work Plan review slides, SA3, SA4 and SA5 are reported in the “Stage 3” slides since their overall completion date is aligned with (CT’s) Stage 3. Except for SA4’s Stage 2-only WIDs but this cannot be handled by the present tools.
RAN has a slightly different process. RAN defines two dates:
  The “RAN Content Definition”, which is the same date as SA Stage 1 and SA content definition
  The “RAN Completion”, which is the same date as SA/CT’s Stage 3
  Note that there is no specific RAN-equivalent date for SA/CT’s Stage 2