## Slide 1
FS_SMS2EC_ARC
Status Report
Krisztian Kiss (Primary Rapporteur)
Apple
Ellen Liao (Secondary Rapporteur)
Google
S2-2511286 - 3GPP SA2 #172, November 17-21, 2025, Dallas, TX, USA
© 3GPP 2025

## Slide 2: FS_SMS2EC_ARC
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1080062 | Study on Short Message Service to Emergency Response Centre | FS_SMS2EC_ARC | 12/2025 | 45% | SP-250959 | 75% | 
Progress at SA2#172:
  23 contributions were submitted, 9 contributions agreed:
    Additional Architectural Assumption was agreed
    New solutions agreed for KI#3 (SMS over IP Routing to Appropriate PSAP)
      6 new solutions
      2 new solutions covering both KI#1 and KI#3
    Interim conclusions agreed for KI#1 (Identification of SMS to Emergency Response Centre and Emergency Service Type)
Impacts and dependencies on other WGs:
  Intra SA: Security aspects to be analysed by SA3
Controversial Issues
  None
Next Steps:
  SA2#173: Final conclusions for all Key Issues, WID approval

## Slide 3: FS_SMS2EC_ARC
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1080062 | Study on Short Message Service to Emergency Response Centre | FS_SMS2EC_ARC | 12/2025 | 25% | SP-250959 | 75% | 
Progress since SA#109:
  45 contributions were submitted, 21 contributions agreed:
    Additional Architectural Assumptions were agreed
    New solutions agreed for all Key Issues:
      KI#1 (Identification of SMS to Emergency Response Centre and Emergency Service Type): 3 new solutions
      KI#2 (Support of SMS Delivery to Emergency Response Centre via NAS): 4 new solutions
      4 new solutions covering both KI#1 and KI#2
      KI#3 (SMS over IP Routing to Appropriate PSAP): 6 new solutions
      2 new solutions covering both KI#1 and KI#3
    Interim conclusions agreed for KI#1 (Identification of SMS to Emergency Response Centre and Emergency Service Type)
Impacts and dependencies on other WGs:
  Intra SA: Security aspects to be analysed by SA3
Controversial Issues
  None
Next Steps:
  SA2#173: Final conclusions for all Key Issues, WID approval

## Slide 4
Total 7.5 TUs
  4 TUs for Study Phase
  3.5 TUs for Normative Work
FS_SMS2EC_ARC Work plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#170 | Aug 2025 | 1 | 1 | TR 23.700-65 Skeleton/scope, Terms, Arch Assumptions and requirements, key issues for WT#1, WT#2, WT#3
SA2 #171 | Oct 2025 | 1 |  | Key issues updates, if needed New solutions Interim agreements, if any
SA2 #172 | Nov 2025 | 1 |  | Solution updates New solutions Interim agreements and conclusions
SA2#173 | Feb 2026 | 1 |  | Complete conclusions WID discussion/approval
SA2#174 | April 2026 | 1.5 |  | Normative work
SA2#175 | May 2026 | 1 |  | Normative work
SA2#176 | Aug 2026 | 1 |  | Normative work

## Slide 5: Annex

## Slide 6: FS_SMS2EC_ARC
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1080062 | Study on Short Message Service to Emergency Response Centre | FS_SMS2EC_ARC | 12/2025 | 25% | SP-250959 | 45% | 
Progress at SA2#171:
  22 contributions were submitted, 12 contributions agreed:
    Additional Architectural Assumption was agreed
    New solutions agreed for KI#1 and KI#2:
      KI#1 (Identification of SMS to Emergency Response Centre and Emergency Service Type): 3 new solutions
      KI#2 (Support of SMS Delivery to Emergency Response Centre via NAS): 4 new solutions
      4 new solutions covering both KI#1 and KI#2
  New solutions for KI#3 were not treated due to lack of time
Impacts and dependencies on other WGs:
  Intra SA: Security aspects to be analysed by SA3
Controversial Issues
  None
Next Steps:
  SA2#172: new solutions for KI#3 and interim conclusions for KI#1 & KI#2 will be treated with high priority

## Slide 7: FS_SMS2EC_ARC
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1080062 | Study on Short Message Service to Emergency Response Centre | FS_SMS2EC_ARC | 12/2025 | 0% | SP-250837 | 25% | 
Progress since SA#108:
  TR 23.700-65 TR skeleton and TR scope were agreed
  Architectural Assumptions and Requirements agreed
  3 Key Issues agreed:
    Key Issue #1: Identification of SMS to Emergency Response Centre and Emergency Service Type (corresponds to WT#1 and WT#2)
    Key Issue #2: Support of SMS Delivery to Emergency Response Centre via NAS (corresponds to WT#3)
    Key Issue #3: SMS over IP Routing to Appropriate PSAP (corresponds to WT#3)
Impacts and dependencies on other WGs:
  Intra SA: Security aspects to be analysed by SA3
Controversial Issues
  None
Next Steps:
  Work on Solutions