## Slide 1
Rajavelsamy R
SA3 Chair
Rel-20 SA3 Work Planning

## Slide 2
Rel-20 (5G-Advanced)
  For 5G-Advanced: 18-month. Assuming no delay of Rel-19
    Stage-1 freeze : Jun 2025
    Stage-2 freeze : Jun 2026 (>=80%); Sep 2026 (100%)
    Stage-3 freeze : Mar 2027
    ASN.1/OpenAPI freeze: June 2027
Release 20: 5G-Advanced Timeline [SP-250768]
2024
#103
Mar.
#111
Mar.
#107
Mar.
#104
Jun.
#108
Jun.
#112
Jun.
#105
Sep.
#109
Sep.
#102
Dec.
#106
Dec.
#110
Dec.
TSGs
SA1 5GA SID definition
100%
SA1 5GA Studies + Norm 80%
100%
St. 2 (SA2, SA6, …) 5GA St.+Norm 80%
Stage 3 5GA St + Norm
#113
Sep.
#114
Dec.
#115
Mar.
Jun
RAN1
RAN Completion (RAN2/3/4core)
#116
RAN4 C.def.
RAN4 Perf
RP Content def.
Rel-20 - 5GA part
2025
2026
2027
5GA ASN.1 & Open APIs
St.2 SID def. TBD
St.3 SID def. TBD
Workshop 5GA SA

## Slide 3
2024
#103
Mar.
#111
Mar.
#107
Mar.
#104
Jun.
#108
Jun.
#112
Jun.
#105
Sep.
#109
Sep.
#102
Dec.
#106
Dec.
#110
Dec.
Now
TSGs
Workshop 6G TSGs
CT & St. 3 6G SID def.
#113
Sep.
#114
Dec.
#115
Mar.
Jun
Workshop SA1 on IMT-2030 use cases
#116
SA1 6G Study(ies)
SA1 6G SID def.
RP IMT-2030 disc.
RP ITU Study
RP 6G Study(ies)
RAN1 6G Study(ies)
SA2 6G Study(ies)
Stage 3 6G Study(ies)
2025
2026
2027
SA2 & RAN WGs 6G SID def.
SA3/4/5/6 6G SID def. TBD
RAN2/3/4 6G Study(ies)
Release 20 (FS) 6G timeline[SP-250420]
or
TBD
Note: All starting dates are indicative
SA3/4/5/6 6G Study(ies)TBD

## Slide 4: SA3 TU capacity
SA3 TUs per meeting :
  Max TUs : 20 TUs per meeting in main room
  6 TUs for: TEI-20 + Maintenance of previous release + Incoming LSs from external forums (GSMA, ETSI,..) + CVDs + New SIDs/WIDs
  Expected TUs per meeting : 7 for 5GA & 7 for 6G (no additional TUs for revisions & incoming LSs)
  No parallel sessions planned initially, but going forward under unavoidable situations parallel sessions are possible
 | 60mins | 90mins | 30mins | 90mins | 90mins | 90mins | 30mins | 90mins | 15mins | 90mins
 | 8- 9am | 9 -10:30am | 10:30-11am | 11-12:30pm | 12:30 -2:00pm | 2:00 – 3:30 | 3:30- 4pm | 4 – 5:30 pm | 5:30-5:45pm | 5:45 - 7 .15 pm
Monday |  | 1 | Tea Break | 2 | Lunch Break | 3 | Tea Break | 4 | Break | 5
Tuesday |  | 6 |  | 7 |  | 8 |  | 9 |  | 10
 |  | 11 |  | 12 |  | 13 |  | 14 |  | 
Wednesday |  | 15 |  | 16 |  | 17 |  | 18 |  | 19#
 |  | 20 |  | 21 |  | 22 |  | 23 |  | 
Thrusday |  | 24 |  | 25 |  | 26 |  | 27 |  | 28
Friday |  | 29 |  | 30 |  | 31 |  |  |  | 
 | TUs from Plenary | TUs from Parallel sessions
TEI-20 & Maintainance | 6 | 
5GA SIDs/WIDs | 7 | 4
6G Study | 7 | 4
Start, Reports, Ending | 2 | 
Buffer | 1 | 
#Early closure for Social evening on Wednesday

## Slide 5: SA3 Rel-20 capacity
SA3 TUs for Rel-20: 12 Meetings
  5GA  Start: Aug 2025 (3GPPSA3#123), End: Feb 2027 (3GPPSA3#132) (For SID & WID)
  6G Study  Start: Oct 2025 (3GPPSA3#124), End: May 2027 (3GPPSA3#134) (Based on RAN approved 6G SID)
  More TUs for 5GA in SA3#129 & SA3#132 (Stage 2 & Stage 3 Freeze)
  5GA SIDs to be agreed no later than Nov 2025 (SA3#125) and target for approval in Dec.2025 (SA#110)
  6G SIDs to be agreed no later than Feb 2026 (SA3#126) and target for approval in Mar 2026 (SA#111)
  Prerequisite: Allocated TUs are well utilized in all meetings
    For example, it should not be the case where, TUs in SA3#124 for 5GA is under utilized and request for more than 10 TUs for 5GA in SA3#129
 |  | Maintenance | 5GA | 6G Study | Buffer | 
Aug'25 | SA3#123 | 12 | 4 |  | 5 | 
Oct'25 | SA3#124 | 6 | 7 | 7 | 1 | 
Nov.25 | SA3#125 | 6 | 7 | 7 | 1 | Last meeting for 5GA SIDs Agreement
Feb'26 | SA3#126 | 6 | 7 | 7 | 1 | Last meeting for 6G SIDs Agreement
April'26 | SA3#127 | 6 | 7 | 7 | 1 | 
May'26 | SA3#128 | 6 | 8 | 6 | 1 | 
Aug'26 | SA3#129 | 6 | 10 | 4 | 1 | Sep'26 Stage 2 Freeze
Oct'26 | SA3#130 | 6 | 7 | 7 | 1 | 
Nov'26 | SA3#131 | 6 | 8 | 6 | 1 | 
Feb'27 | SA3#132 | 6 | 10 | 4 | 1 | March'27 Stage 3 Freeze
April'27 | SA3#133 | 10 |  | 10 | 1 | 
May'27 | SA3#134 | 10 |  | 10 | 1 | June'27 Rel-20 Completion
 |  | 86 | 75 | 75 | 16 | 

## Slide 6: Rel-20 TU budget status and way forward
SID/WID should have consensus in SA3
Prioritization
  Based on the availability of the TUs. In case of less TUs availability
    Priority to the SA/RAN approved WIDs from other WGs that have SA3 dependency
    Priority to the most supported SIDs/WIDs/WTs
 More realistic TUs should be planned and proposed. As Rel-20 planning is based on TU budget, it is not possible to overshoot.
ID | Tech | Unique_ID | Name | Acronym | Start | Finish | #WTs | # 5GA TUs | # 6G TUs
Approved |  |  |  |  |  |  |  |  | 
1 | 5GA | 1080044 | Mission critical security for Rel-20 | MCX20-SEC | Jun-25 | Jun-26 | 1 | 0.4 | 
2 | 5GA+6G | 1080045 | Study on Transitioning to Post Quantum Cryptography in 3GPP | FS_CryptoPQC | Jun-25 | Jun-26 | 1 | 3 | 3
3 | 5GA | 1080042 | Security Assurance Specification for 5G-Advanced | SCAS_5GA | Jun-25 | Sep-26 | 1 | 4 | 
4 | 5GA | 1080041 | Security related Events Handling | SECHAND | Jun-25 | Dec-25 | 2 | 4 | 
Endorsed |  |  |  |  |  |  |  |  | 
5 | 6G |  | Study on supporting AEAD algorithms |  |  |  | 1 |  | 3
6 | 5GA |  | Study on AIMLE Service Security |  |  |  | 1 | 4.5 | 
7 | 5GA |  | New SID on Security Aspects for IMS resiliency |  |  |  | 2 | 4* | 
8 | 5GA |  | New SID on Security Aspect for NR Femto Phase 2 |  |  |  | 2 | 4 | 
9 | 5GA |  | New SID on Security aspects of WAB nodes for NR |  |  |  | 2 | 3 | 
10 | 5GA |  | New SID on security for PLMN hosting a NPN phase 2 |  |  |  | 3 | 3 | 
11 | 5GA |  | New SID on security aspects for QUIC or TLS |  |  |  | 1 | 1.5 | 
12 | 5GA |  | New SID on Security of AIML_Ph2 |  |  |  | 1 | 3* | 
13 | 5GA |  | New SID on security aspects of Integrated Sensing and Communication |  |  |  | 2 |  | 
14 | 5GA |  | New SID on 5G Security Assurance Specification (SCAS) for the Container-based Products |  |  |  | 2 | 3 | 
15 | 5GA |  | New SID on Security Aspects of 5G Satellite Access Phase 4 |  |  |  | 1 | 3 | 
Total TU Budget : |  |  |  |  |  |  |  | 75 | 71
TUs Allocated : |  |  |  |  |  |  |  | 40.4 | 6
TUs remaining : |  |  |  |  |  |  |  | 34.6 | 65
*TBD

## Slide 7: Thank You !
Rajavelsamy R
Chair of 3GPP SA3 WG
rajvel@samsung.com