## Sheet1
|  | Maintenance | 5GA | 6G Study | Buffer
Aug'25 | 3GPPSA3#123 | 12 | 4 |  | 5
Oct'25 | 3GPPSA3#124 | 6 | 11 | 3 | 1
Nov.25 | 3GPPSA3#125 | 6 | 11 | 3 | 1 | Last meeting for 5GA SIDs Agreement
Feb'26 | 3GPPSA3#126 | 6 | 7 | 7 | 1 | Last meeting for 6G SIDs Agreement
April'26 | 3GPPSA3#127 | 6 | 7 | 7 | 1
May'26 | 3GPPSA3#128 | 6 | 8 | 6 | 1
Aug'26 | 3GPPSA3#129 | 6 | 8 | 6 | 1 | Sep'26 Stage 2 Freeze
Oct'26 | 3GPPSA3#130 | 6 | 7 | 7 | 1
Nov'26 | 3GPPSA3#131 | 6 | 8 | 6 | 1
Feb'27 | 3GPPSA3#132 | 6 | 8 | 6 | 1 | March'27 Stage 3 Freeze
April'27 | 3GPPSA3#133 | 6 |  | 14 | 1
May'27 | 3GPPSA3#134 | 6 |  | 14 | 1 | June'27 Rel-20 Completion
|  | 78 | 79 | 79 | 16

## Sheet3
ID | Tech | Name | Acronym | Start | Finish | #WTs | # 5GA TUs | # 6G TUs | Other WGs dependency
Approved
1 | 5GA | Mission critical security for Rel-20 | MCX20-SEC | 2025-06-01 | 2026-06-01 | 1 | 1
2 | 5GA+6G | Study on Transitioning to Post Quantum Cryptography in 3GPP | FS_CryptoPQC | 2025-06-01 | 2026-06-01 | 1 | 3 | 3
3 | 5GA | Security Assurance Specification for 5G-Advanced | SCAS_5GA | 2025-06-01 | 2026-09-01 | 1 | 4
4 | 5GA | Security related Events Handling | SECHAND | 2025-06-01 | 2025-12-01 | 2 | 4
Endorsed
5 | 5GA | Study on AIMLE Service Security |  |  |  | 1 | 3 |  | SA6
6 | 5GA | New SID on Security Aspects for IMS resiliency |  |  |  | 2 | 3 |  | SA2
7 | 5GA | New SID on Security Aspect for NR Femto Phase 2 |  |  |  | 2 | 3 |  | RAN3
8 | 5GA | New SID on Security aspects of WAB nodes for NR |  |  |  | 2 | 3 |  | RAN3
9 | 5GA | New SID on security for PLMN hosting a NPN phase 2 |  |  |  | 3 | 3 |  | None
10 | 5GA | New SID on security aspects for QUIC or TLS |  |  |  | 1 | 1.5 |  | SA2, CT WGs
11 | 5GA | New SID on Security of AIML_Ph2 |  |  |  | 1 | 3.5 |  | SA2, RAN1/RAN2
12 | 5GA | New SID on security aspects of Integrated Sensing and Communication |  |  |  | 2 | 6 |  | SA2, RAN WGs
13 | 5GA | New SID on 5G Security Assurance Specification (SCAS) for the Container-based Products |  |  |  | 2 | 3 |  | None
14 | 5GA | New SID on Security Aspects of 5G Satellite Access Phase 4 |  |  |  | 1 | 3 |  | SA2, RAN WGs
15 | 6G | Study on supporting AEAD algorithms |  |  |  | 1 |  | 5 | None
Proposals
| 5GA | Study on Security aspects of CAPIF Phase 4 |  |  |  | 2 | 3 |  | SA6
| 5GA | New WID on PRINS Refinement |  |  |  | 3 | 1 |  | None
| 5GA | SID Study on best security practice for SBA |  |  |  | 1 | 2 |  | SA2
| 5GA | Study on Security Aspect of Ambient IoT Services in 5G phase 2 // R20 Amabient IoT SID |  |  |  | 3 | 7.5 |  | SA2, SA5, RAN WGs
| 5GA | New WID on SCAS for NR Femto |  |  |  | 2 | 1.5 |  | none
| 5GA | New WID on SCAS for NR Femto SeGW |  |  |  | 2 | 1 |  | none
| 6G | Study on Security for the 6G System | [5 empty] | 50 | RAN WGs, SA2, SA4, SA5, SA6
Total TU Budget: | [6 empty] | 79 | 75
TUs Allocated: | [6 empty] | 60 | 58
TUs remaining: | [6 empty] | 0 | 17
|  |  |  | Max TU acceptable |  |  | 70 | 60
|  |  |  | TU allocation this meeting |  |  | 60 | 50