## Slide 1: SA6 Rel-20 Planning (TU Status and Plan)
Basavaraj (Basu) Pattan
Vice-chair, basavarajjp@samsung.com

## Slide 2: Outline
Background
Rel-20 TU Status and Planning
Rel-20 TUs – until SA6#67
Rel-20 TUs – after SA6#67
Backup

## Slide 3: Background
SA6 Chair input to the Rel-20 Planning is available in SP-241875
The consolidated overview of the SA-WG groups planning provided in SP-241907 was Endorsed
This paper is to present current status of TUs consumed and planned

## Slide 4: Rel-20 5GA TU Status and Planning

## Slide 5: Rel-20 TUs – until SA6#67
Total number of TUs per SA6 meeting: 20 TUs
Total number of Rel-20 meetings until SA6#67 : 3 meetings
Total TUs that were available for Rel-20 5GA : 60 TUs
  (3 meetings * 20 TUs per meeting)
Total TUs used for Rel-20 5GA: 23.75 TUs*
  *(3 TBDs to be resolved)

## Slide 6: Rel-20 TUs – after SA6#67
Total number of TUs per SA6 meeting: 20 TUs
Total number of SA6 meetings remaining: 9 meetings*
Total TUs available for Rel-20 (both 5G-Adv and 6G Study): 180 TUs
  (9 meetings * 20 TUs per meeting)
TUs planned for Rel-20 5GA: 105 TUs**
  **(5 TBDs to be resolved)
* Assumptions:
5G-Adv Stage-2 SID/WID approval in Mar-2025 & freeze in June-2026
6G Stage-2 SID approval in Sep-2025 & freeze in Dec-2026

## Slide 7: Backup

## Slide 8: Rel-20 Timeline (Recap)
For 5G-Advanced: 18-month. Assuming no delay of Rel-19
  Stage-1 freeze : Jun 2025
  Stage-2 freeze : Jun 2026 (>=80%); Sep 2026 (100%)
  Stage-3 freeze : Mar 2027
  ASN.1/OpenAPI freeze: June 2027
Stage-2 Study
Q1
Q2
Q3
Q4
2025
Q1
Q2
Q3
Q4
2026
Study / WI Approvals*
Q1
Q2
2027
Stage-2 Study/Normative
Study Approvals*
Stage-3
Stage-2 freeze
(100%)
Stage-3 freeze
Rel-20 5G-Adv
Rel-20 6G
Study freeze**
6G SI Approval
  SA1 SI approval: TSG#105 (Sept 2024) - DONE
  SA2 SI approval: TSG#108 (Jun 2025)
  Other SA WG (SA3, SA4, SA5, SA6) SI approval: TBD at future TSG meeting
  SA1/SA2 6G SI may continue beyond Stage-1/Stage-2 freeze dates for 5G-Advanced
6G SI completion
  SA1 6G SI completion: Mar 2026
  SA2 6G SI completion: Dec 2026 or Mar 2027 (**To be confirmed at future TSG meeting)
*Additional notes:
5G-Adv stage-2 SID/WID for approval – not earlier than Mar 2025
6G SI for approval – not earlier than Sep 2025
Preparation
Preparation
Stage-2 freeze
(80%)

## Slide 9: 3GPP SA/SA6 Meeting Schedule
 | Dec-24 | Jan-25 | Feb-25 | Mar-25 | Apr-25 | May-25 | Jun-25 | Jul-25 | Aug-25 | Sep-25 | Oct-25 | Nov-25 | Dec-25 | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26
Meetings | SA#106 |  | SA6#65 | SA#107 | SA6#66 | SA6#67 | SA#108 |  | SA6#68 | SA#109 | SA6#69 | SA6#70 | SA#110 |  | SA6#71 | SA#111 | SA6#72 | SA6#73 | SA#112 |  | SA6#74 | SA#113 | SA6#75 | SA6#76 | SA#114
TITLE | TYPE | DATES | LOCATION | CTRY
3GPPSA6#65 | OR | 2025-02-17 09:00 - 2025-02-21 17:30 | Athens | GR
3GPPSA6#66 | OR | 2025-04-07 09:00 - 2025-04-11 17:30 | Goteborg | SE
3GPPSA6#67 | OR | 2025-05-19 09:00 - 2025-05-23 17:30 | Fukuoka | JP
3GPPSA6#68 | OR | 2025-08-25 09:00 - 2025-08-29 17:30 | Goteborg | SE
3GPPSA6#69 | OR | 2025-10-13 09:00 - 2025-10-17 17:30 | China (TBC) | CN
3GPPSA6#70 | OR | 2025-11-17 09:00 - 2025-11-21 17:30 | Dallas | US
3GPPSA6#71 | OR | 2026-02-09 09:00 - 2026-02-13 17:30 | IN | IN
3GPPSA6#72 | OR | 2026-04-13 09:00 - 2026-04-17 17:30 | EU | EU
3GPPSA6#73 | OR | 2026-05-18 09:00 - 2026-05-22 17:30 | China | CN
3GPPSA6#74 | OR | 2026-08-24 09:00 - 2026-08-28 17:30 | EU | EU
3GPPSA6#75 | OR | 2026-10-12 09:00 - 2026-10-16 17:30 | EU | EU
3GPPSA6#76 | OR | 2026-11-16 09:00 - 2026-11-20 17:30 | US | US
Rel-20 5G-Adv
  Assuming
    Stage-2 SID/WID approval in Mar-2025*
    Stage-2 SID/WID freeze in Sep-2026
  Total number of SA6 meetings: 9
6G Study
  Assuming
    Stage-2 SID approval in Sep-2025*
    Stage-2 SID freeze in Dec-2026**
  Total number of SA6 meetings: 8
Rel-20 Total number of SA6 meetings: 11
** To be confirmed at future TSG meeting
* Best case scenario

## Slide 10: Typical SA6 Session Planning
 | Monday |  | Tuesday |  | Wednesday |  | Thursday | Friday
Quarter 0 07:30 to 09:00 | Placeholder for additional official sessions or drafting sessions |  |  |  |  |  |  | 
Quarter 1 09:00 to 10:30 | Plenary session (Agenda, Reports, LSs, early discussion papers, Future work, etc.) |  | Parallel Track I | Parallel Track II | Parallel Track I | Parallel Track II | Plenary session (Revisions) | Plenary session (Revisions)
Morning break (10:30 – 11:00) SA6 Chair Election sessions on Tuesday and potentially Wednesday and Thursday |  |  |  |  |  |  |  | 
Quarter 2 11:00 to 12:30 | Plenary session (Agenda, Reports, LSs, early discussion papers, Future work, etc.) |  | Parallel Track I | Parallel Track II | Parallel Track I | Parallel Track II | Plenary session (Revisions) | Plenary session (Revisions)
Lunch break (12:30 – 14:00) |  |  |  |  |  |  |  | 
Quarter 3 14:00 to 15:30 | Parallel Track I | Parallel Track II | Parallel Track I | Parallel Track II | Parallel Track I | Parallel Track II | Plenary session (Revisions) | Plenary session (Work plan review, Future meetings, AOB)
Afternoon break (15:30 – 16:00) |  |  |  |  |  |  |  | 
Quarter 4 16:00 to 17:30 | Parallel Track I | Parallel Track II | Parallel Track I | Parallel Track II | Parallel Track I | Parallel Track II | Plenary session (Revisions) | Meeting will close at the latest by 16:00
Evening break (17:30 – 18:00) |  |  |  |  |  |  |  | 
Quarter 5 18:00 to 19:30 | Placeholder for additional official sessions or drafting sessions |  |  |  |  |  |  | 
A TU is a quarter dedicated to study or work items
  Those quarters not dedicated to Rel-20 study or work items (e.g. LSs, pre-Rel-20 maintenance) are not counted as TUs
  Quarters dedicated to revisions are not counted as TUs e.g. plenary sessions, handling revisions
Total number of TUs per SA6 meeting: 20 TUs
Indicates buffer TUs created if needed

## Slide 11: Potential SA6 Split ~50% for 5G-Adv
  Table shows meetings available for different phases of work and TUs split @ ~50% for 5G-Adv
    5G-Adv Study and Normative phase is 104 TUs
    6G Study phase is 116 TUs
 | Dec-24 | Jan-25 | Feb-25 | Mar-25 | Apr-25 | May-25 | Jun-25 | Jul-25 | Aug-25 | Sep-25 | Oct-25 | Nov-25 | Dec-25 | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26
Meetings | SA#106 |  | SA6#65 | SA#107 | SA6#66 | SA6#67 | SA#108 |  | SA6#68 | SA#109 | SA6#69 | SA6#70 | SA#110 |  | SA6#71 | SA#111 | SA6#72 | SA6#73 | SA#112 |  | SA6#74 | SA#113 | SA6#75 | SA6#76 | SA#114
Rel-19 Milestones | Stage 2 100% |  |  |  |  |  |  |  |  | Stage 3 100% |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Rel-20 milestones and events | 5GA WS |  |  | 6G WS |  |  | 5GA Stage 1 100% |  |  |  |  |  |  |  |  | 6G FS Stage 1 100% |  |  |  |  |  |  |  |  | 
Pre-Rel-20 Maintenance Phase Added for information |  |  | 16 TUs |  | 6 TUs | 6 TUs |  |  | 4 Tus |  | 4 TUs | 2 TUs |  |  | 2 TUs |  | 1 TU | 1 TU |  |  | 1 TU |  | 1 TU | 1 TU | 
5G-Adv timeline |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Preparation Phase |  |  | 4 TUs |  | 3 Tus * | 2 Tus * |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Study/Normative Phase |  |  |  |  | 6 TUs | 8 Tus |  |  | 8 Tus |  | 12 TUs | 10 TUs |  |  | 10 TUs |  | 10 TUs | 10 TUs |  |  | 8 TUs |  |  |  | 
Maintenance phase |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 6 TU | 6 TU | 
6G timeline |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Preparation Phase |  |  |  |  | 4 Tus * | 4 Tus * |  |  | 6 Tus * |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Study Phase |  |  |  |  |  |  |  |  |  |  | 8 TUs | 10 TUs |  |  | 10 TUs |  | 10 TUs | 10 TUs |  |  | 12 TUs |  | 14 TUs | 14 TUs | 
* Each Time Unit in a common session consume 2 TUs
5G-Adv Stage-2 Study/Normative (9 meetings)
Stage-3
Preparation
6G Stage-2 Study (8 meetings)
Preparation