## Slide 1: Summary of 2020 Income and Expenditure
Source
3GPP Funding and Finance Group
OP45(21)05

## Slide 2: Contents
Manpower (MCC staff)
Manpower (MCC Contractors/Seconded Experts)
Manpower (IT support staff)
Manpower (TTCN testing support staff)
Manpower (TTCN STF 160 contractors)
Manpower (TTCN STF 160P, 160G & 160V contractors)
Travel and subsistence
Promotion and marketing materials
Training
Overheads
Contingency
Income from Partners
Other income sources
Conclusions

## Slide 3
Manpower (MCC staff)
At the beginning of 2020, one contractor position (Kimmo Kymalainen) was converted into a staff position. This was not planned for in the budget.
In October 2020, Issam Toufik (contractor) replaced the MCC Director (John Meredith). John Meredith retired at the end of September 2020. The approved budget allowed for six months of overlap to enable a smooth handover of responsibilities. The selected successor was already working as a contractor in MCC and so this overlap provision has not been fully used.
Taking the above into account, expenditure at the end of 2020 under the MCC staff budget line was 2242,551 kEUR out of an annual budget of 2170 kEUR.
This represents an overspend of 72,551 kEUR.

## Slide 4
Manpower (MCC Contractors/Seconded Experts)
With the conversion of one contractor position (Kimmo Kymalainen) into a staff position, and the appointment of one contractor (Issam Toufik) to the position of MCC Director, there are no contractors remaining in MCC at the end of 2020.
The expenditure at the end of 2020 under the MCC contractor budget line was 59,970 kEUR out of an annual budget of 245,400 kEUR.
This represents an underspend of 185,430 kEUR.
(The value of the Seconded Experts provided in lieu of payment by by CCSA, TSDSI and TTA amount to a total value of 408,600 kEUR.)

## Slide 5: Manpower (IT support staff)
The pandemic situation had a widespread impact on 3GPP during year 2020. Only one meeting requiring onsite IT support was held during this period.
Taking the above into account, expenditure at the end of 2020 under the IT support staff budget line was 11,700 kEUR out of an annual budget of 132kEUR. This includes on-site support to the physical 3GPP meeting held in Incheon, South Korea and remote IT support provided to 3GPP meetings held online (documents upload via HTTP and TOHRU tool).
This represents an underspend of 120,3 kEUR.

## Slide 6
Manpower (TTCN testing support staff)
One full-time TTCN support expert is provided to manage the development of TTCN within 3GPP.
The cost of that expert at the end of 2020 was 137,839 kEUR out of an annual budget of 139 kEUR.
This represents an underspend of 1,161 kEUR.

## Slide 7
Manpower (TTCN STF 160 contractors)
By the end of 2020, 789 kEUR of contracts have been established for STF160 out of the annual budget of 884 kEUR.
This represents an underspend of 95 kEUR.

## Slide 8
Manpower (TTCN STF 160P, 160G and 160V contractors)
By the end of 2020:
156 kEUR has been spent on TTCN development requested by PTCRB/CTIA out of 156 kEUR budget
156 kEUR has been spent on TTCN development requested by GCF out of 156 kEUR budget.
In additional to funded work, 400 man days voluntary effort have been provided by members for TTCN development (STF160V)

## Slide 9: Travel and subsistence
The pandemic situation has led to the cancellation of most physical meetings during 2020. Where flight tickets had already been purchased in advance, negotiations led to reimbursement or the issuing of vouchers in the vast majority of cases.
Due to the extensive reimbursement of travel and flight reservations, expenditure at the end of 2020 under the travel and subsistence budget line was -19,928kEUR out of an annual budget of 525kEUR.
Hence this budget line is underspent by 544,928 kEUR by the year end.

## Slide 10: Promotion and marketing materials
The expenditure on promotion and marketing materials at the end of 2020 amounted to 25,824 kEUR from an annual budget of 60 kEUR. The cancellation of the Mobile World Congress and other events in 2020 has impacted expenditure under this budget line.
This represents an underspend of 34,176 kEUR .
Promotion and Marketing | Amount (kEUR)
Community Awards | 1,270
Printed deliverables | 5,412
Branded give-aways | 5,300
Videos & webinars | 8,842
Website design | 5,00
TOTAL | 25,824

## Slide 11: Training
Three antitrust and competition law compliance training courses took place in 2020.
The expenditure on training at the end of 2020 therefore amounted to 12,052 kEUR from an annual budget of 20 kEUR
This represents an underspend of 7,948 kEUR.

## Slide 12: Overheads
Changes in manpower expenditure during 2020 has led to lower overhead charges than expected. The expenditure at the end of 2020 amounted to 1 418,804 kEUR from an annual budget of 1500 kEUR
This represents an underspend of approximately 81,196 kEUR.
MCC staff costs in support of 3GPP | 2242,551
Testing staff | 137,839
3GPP contractors for MCC support (59,970 + 3*136,200) | 468,570
3GPP contractors for Specific Task 160 (excl 160V and 160P) | 789,000
TOTAL Workforce | 3637,960
Overhead: 39%*Workforce expenditure (figure based on ETSI overhead calculation) | 1418,804

## Slide 13: Contingency
A contingency of 150 kEUR had been set aside for 2020.
4,164 kEUR has been spent on the seconded experts’ immigration and work permit fees.
This represents an underspend of 145,836 kEUR.

## Slide 14
3GPP Income from Partners
Invoices issued to Partners in 2020 (credit notes and seconded experts taken into account)
Payments received by September 2020

## Slide 15: Other Income Sources
Seconded Experts from Partners:
    136,200 kEUR (value of the seconded expert provided by CCSA in lieu of payment).
    136,200 kEUR (value of the seconded expert provided by TSDSI in lieu of payment)
    136,200 kEUR (value of the seconded expert provided by TTA in lieu of payment)
Other payments:
  156 kEUR funding from CTIA/PTCRB for STF 160P
  156 kEUR funding from GCF for STF 160G

## Slide 16
Conclusions
On the expenditure side, the unforeseen pandemic has led to significant underspending as physical meetings have all but ceased and the associated travel cancelled.
On the income side, all Partner payments have been received.
At the year end, a total of approximately 5402 kEUR has been spent out of a budget of 6546 kEUR. There is therefore a budget surplus of approximately 1,144 kEUR. A detailed calculation is provided in document OP45(21)06