# Project plan – 3GPP 5G Naming

The following is to be distributed to Bisqit and to PCG colleagues to provide a timeline that incorporates the original Bisqit proposal and the subsequent ATIS requirements, submitted via the Heads of Delegation discussion (May 2016).

The attached excel sheet (consultation_group_v2) is the proposed list of people to be contacted for a direct interview or survey about naming (It is not NOT the Steering Group – See 2a below SG details). This list should be reviewed by each OP ASAP before the start of work. Names may be added or taken away under the guidance of the HoDs.

The naming project will start as soon as possible in June – A Purchase Order will go out to Bisqit as soon as we have signed their agreement and when they are set up as a Supplier.

The price is agreed and two payments (50% each) will be made - €32,500 immediately and €32,500 at the end of the work. We will not ask for work beyond that budget, which is firm.

## Timeline

- Start of work								Jun 20

- Clarification on decision making						Jun 20

  - Steering Group

  - Head of Delegations

  - OPs at PCG#37

- ‘Discovery’ phase – consulting the Steering Group on 5G			Jun 20 – Jul 19

- Bisqit Desk research and interviews (See excel sheet)			Jun 20 – Aug 9

- Steering Group Conference call #1					Jul 18

- Status report to PCG Head of Delegations (Marcom/Bisqit)			Jul 19

- Steering Group Conference call #2					Aug 9

- Status report to PCG Head of Delegations (Marcom/Bisqit)			Aug 10

- Bisqit ‘Creative’ phase to produce a list of names				Aug 15 – Aug 29

- Steering Group Conference call #3 – Shortlisting 1				Aug 29

- Status report to PCG Head of Delegations (Marcom/Bisqit)			Aug 29

- Bisqit to carry out Stakeholder testing					Aug 29 – Sep 14

- Steering Group Conference call #4 – Final Shortlisting			Sep 16

- Bisqit Proposal for PCG decision						Sep 20

- OP Decision (London, PCG#37)						Oct 20

…

- Graphic design (3GPP)							Nov - Dec

- OP decision on logo (virtual meeting or via correspondence)		Jan

## 1.	Start of work (Jun20)

The contract and PO will take a week to set up. The realistic start date is June 20th.

Work and payment will be completed in 2016.

## 2.	Clarification on decision making;

  - Steering Group

The Steering Group will be made up of the 3GPP OP Heads of Delegation, their appointed ‘Alternate’ and a representative from their Membership (3 persons maximum per OP). They will be joined by the TSG SA and TSG RAN Chairmen.

The Steering Group shall not exceed 23 persons (7 OPs +2 TSG).

Individuals appointed to the Steering Group should be willing to participate in the four scheduled Conference calls, and be active on the email list created for the Steering Group use.

The Steering Group will guide Bisqit it its work, providing the following decisions – by consensus and ‘ranking’ votes:

- Steering Group Conference call #3 – Shortlisting 1	(Aug 29) – ranking shortlisted names.

- Steering Group Conference call #4 – Final Shortlisting – Approval of the Bisqit proposal (very short list or one name, TBD).

  - Head of Delegations

A status report will be sent to the HoDs on July 19, August 10 and August 19 – Immediately after the Steering Group meetings.

This will serve as a report on the Bisqit work done and the outcome of the Steering Group call, to be copied to all Steering Group participants.

There is no formal decision making required in these reports – The HoDs are asked to provide guidance to Bisqit at these points in the process.

  - OPs at PCG#37

The Bisqit proposal (14. above) will be submitted to PCG#37 as a formal document for decision. The deadline for the document to be with the PCG Secretary – and on the server – is September 20, 2016.

The proposal will be presented by Bisqit at PCG#37 (London) and approval sought, via consensus. If consensus is not achieved an OP vote will be taken.

## 3.	‘Discovery’ phase – consulting the Steering Group on 5G (Jun 20 – Jul 19)

Steering Group members will be contacted directly by Bisqit, for a discussion about;

- What kind of name would work best,

- Whether it’s: - Descriptive, Abstract, Experience/image-based, Evocative, Origin-based…Or another initialism, like LTE.

- The benefits and weaknesses of each to hear your instincts on which feel right for 5G.

## 4.	Bisqit Desk research and interviews (Jun 20 – Aug 9)

The 3GPP Marketing Officer has produced an excel list of persons to be interviewed or surveyed. THIS MUST BE REVIEWED BY THE HoDs and STEERING GROUP ASAP.

The Steering Group participants are on this list – so will be interviewed a second time – if these topics are not covered in the initial conversation.

Bisqit to research;

- The audiences for the name,

- Contexts it will be seen in,

- Any other uses for it,

- How it needs to be future-proofed,

- The current industry feeling about 5G

- What are the main messages people want the name to get across?

- How will each group use the name when it exists?

- What are similar tech names they love and hate, and why?

These questions and conversations will be flexible enough to flow naturally. The three main ways of gathering inputs will be;

- Face to face meetings and interviews

- Video call or telephone interviews

- Surveys

## 5.	Steering Group Conference call #1 (Jul 18)

After Bisqit have talked to the individuals in the Steering group – we will have the first call, so that the agency can brief on the direction that these interviews have given and they will ask for guidance on their findings.

## 6.	Status report to PCG Head of Delegations (Jul 19)

Written details of what was discussed and actions taken from 5. above.

## 7.	Steering Group Conference call #2 (Aug 9)

At the completion of interviews and surveying – bisqit will again bring their current thinking to the Group – before they go in to their creative phase.

## 8.	Status report to PCG Head of Delegations (Aug 10)

Written details of what was discussed and actions taken from 7. above.

## 9.	Bisqit ‘Creative’ phase to produce a list of names (Aug 15 – Aug 29)

The agency creative team will work on a list of names that have come from the investigations done so far. This list will contain ideas that are fulfilling most of our community’s feedback.

Language testing will be introduced at this shortlisting stage, via the Steering Group members and an independent translation agency.

## 10.	Steering Group Conference call #3 (shortlisting 1, Aug 29)

Bisqit will bring a shortlist of names to this workshop meeting. We should schedule a longer meeting, so that we can have a full discussion on the proposed list. There will be a ranking of names out of 10 by the Steering Group – via email on August 29 or immediately afterwards.

## 11.	Status report to PCG Head of Delegations (Aug 29)

Written details of what was discussed and actions taken from 10. above.

## 12. 	Bisqit to carry out Stakeholder testing (Aug 29 – Sep 14)

The agency will take the shortlist from the Steering Group and gather evidence on which names people most understand, and which they most like, with the aim to bolster the arguments behind the best names.

Bisqit will do visual mock-ups to show the shortlisted names in the contexts the name needs to work in, to be shown to stakeholders, from within the project (sub-set of excel sheet list) and externally – via focus groups in the agency.

## 13.	Steering Group Conference call #4 (final shortlisting, Sep 16)

This meeting will see the final results of testing from Bisqit and their proposal – which will be submitted to the group for approval – prior to its submission to PCG#37.

## 14.	Bisqit Proposal for PCG decision	(Sep 20)

The written proposal - agreed in Steering Group Conference call #4 – must be with the PCG Secretary by September 20, 2016.

## 15.	OP Decision (London, PCG#37, Oct 20)

…

## 16.	Graphic design (3GPP) - Nov – Dec

Graphic design is not included in the Bisqit contract. The process of making a logo for the name will be considered as we start to get more clarity around the naming options available to us.

## 17.	OP decision on logo (virtual meeting or via correspondence, Jan 2017)

The graphic design will be considered later in the naming process.