## Slide 1: 3GPP TSG SA Management Report
Georg Mayer, 3GPP SA Chair
PCG47_06
Agenda item: 4.1

## Slide 2: TSG SA Dates
Meetings since PCG 46
    TSG SA 92-e – e-meeting, 15-21 June 2020
    TSG SA Rel-18 Workshop, e-meeting, 9 & 10 September 2020
    TSG SA 93-e – e-meeting, 14-20 September 2020
Meetings before PCG 48
    TSG SA Rel-18 Prioritization Workshop, e-meeting – 9 & 10 December 2020
    TSG SA 94-e – e-meeting, 14-20 December 2020
    TSG SA 95(-e) – exact dates depend on whether this is e-meeting
Meeting Setting
    Daily 2h or 3h GoToMeeting (GTM) sessions
    Tuesday – Friday: technical meeting, all technical documents need to have final status on Friday end of online session
    Monday: reporting from RAN, CT, MCC, WorkPlan discussions, administrative issues

## Slide 3: TSG SA Officials
Georg Mayer
TSG SA Chair
ETSI
georg.mayer@huawei.com
Mona Mustapha
TSG SA Vicechair
ETSI
mona_mustapha@apple.com
永田 聡 Satoshi Nagata
TSG SA Vicechair
ARIB nagatas@nttdocomo.com
Mark Younge
TSG SA Vicechair
ATIS
Mark.Younge@T-Mobile.com
Maurice Pope
Secretary
MCC
maurice.pope@etsi.org

## Slide 4: Release 17
Stage 2 functional freeze in SA2 and SA6 happened at TSG SA#92-e (June 2021) plenary, large number of exceptions were approved, which was expected.
Most exceptions were closed by SA#93-e (September 2021) plenary. Only few items left open due to need for coordination with RAN.
SA3, SA4 and SA5 are still working on Rel-17 issues as their role is different from SA1, SA2 and SA6 and they are also partially dependent on SA2 / SA6 outcome. This is also business as usual.

## Slide 5: Release 18 – WS & Timeline & Content
3GPP TSG SA held a 2 day workshop before SA#93-e (September 2021), during which companies presented over 40 contributions on their outlook and requirements for Rel-18.
SA/RAN/CT agreed on the Rel-18 timeline during TSGs#93-e meetings (September 2021)
  Stage 2 functional freeze: March 2022
  Stage 3 freeze: December 2022
  Coding (ASN.1/API) freeze: March 2023
  It was agreed that these dates hold, regardless of the amount of e-meetings which will take place during the indicated period.
The Rel-18 content will be approved by 3GPP SA, RAN and CT during TSGs#94 (December 2021)

## Slide 6: Timeline & Releases (SA View)
99
100
101
102
91
92
93
94
2022
95
96
97
98
2021
TSG#
103
2023
ASN.1 & Open APIs
Stage 1
104
2024
Stage 3 (CT & SA)
Stage 2
Exceptions
Stage 2
Stage 3 (CT & SA)
ASN.1 & Open APIs
Release 18
Release 17
Content approval
Timeline
approval
Stage 1 (no timeline defined yet)
Release 19

## Slide 7: Release 18 – Working Group Status
SA1 has indicated all Rel-18 requirements work 80% complete at SA#93-e (September 2021). SA1 will complete all Rel-18 work by SA#94-e (December 2021)
SA2 is discussing Rel-18 Study/Work Items mainly since June 2021
  So far only Work/Study Item descriptions are discussed. Technical work on CR/TR/TRs will start from Q1/22 on.
  Over 40 Study/Work Item proposals are currently discussed in SA2, they would in total require more than double the available time (time units / TU) which are projected to be available for Rel-18, based on the agreed timeline.
  Due to that a prioritization process has started on SA level, which will conclude at SA#94-e (December 2021) – see next slides.
SA6 also discussed Rel-18 Study/Work Items and has started initial technical work on them. So far the load is regarded as high, but no prioritization process seems to be needed for the moment.
SA3 work for Rel-18 will start later, as it is relying on initial outputs from RAN and SA stage 2 groups.
SA4 and SA5 both are started initial discussions on Rel-18 Study/Work Items. Also here currently it seems the workload can be managed by the groups, i.e. no prioritization needed.

## Slide 8: Release 18 – Prioritization
As indicated on the previous slide, so far it seems that only SA2 Rel-18 Items need to be prioritized. This means that not all Study/Work Items which are currently discussed in SA2 can be part of Rel-18, due to the limited time. It also means that the scope of some of the bigger items needs to be reduced.
SA has outlined a prioritization process which will take place during Q4/2021.
SA2 will further detail the Study/Work Item descriptions and rapporteurs will make realistic TU (time unit) estimations for all objectives / work tasks included in these items.
After the November SA2 meeting, companies will be asked to rank the available items based on their preferences. This will result in a “ranked list” of items which will be the input to the December SA Workshop and SA plenary.
At the 2 day Prioritization Workshop (December 9 & 10) and the subsequent SA#94-e Plenary SA will, in coordination with other SA WGs as well as RAN and CT, determine which of the candidate items will be part of the Rel-18 content.
A list of all SA2 S/WIs at the end of SA#93-e can be found here: https://www.3gpp.org/ftp/tsg_sa/TSG_SA/TSGS_93E_Electronic_2021_09/Docs/SP-211143.zip
The prioritization process is described in more detail here: https://www.3gpp.org/ftp/tsg_sa/TSG_SA/TSGS_93E_Electronic_2021_09/Docs/SP-211119.zip

## Slide 9: Release 19
Initial discussions started in SA1 on Rel-19 topics.
No timeline has been discussed so far. It might be that at SA#94-e (December 2021) SA discusses an initial timeline for SA1 only for Rel-19.
The overall Rel-19 timeline will not be discussed before the start of stage 2 work, i.e. earliest in the beginning of 2023.

## Slide 10: Cross TSG and SA Internal Coordination
TSG Chairs had at least one coordination call every month.
SA Officials (SA Chair, SA Vice Chairs, SA MCC, SA WG Chairs) had coordination calls roughly every 6 weeks.

## Slide 11: E-Meetings & Meeting Planning
Since more than 1.5 years all 3GPP SA and 3GPP SA WG meetings were held electronically.
Participation and input is high, discussions on the mailing list and GoToMeeting/Webinar sessions are lively.
The traffic on the mailing lists in several groups has gone to a level where it is hard to follow individual discussions. Some of the WGs face thousands of e-mails during a meeting week. The workload is the trigger for some of the individual contributions coming to this PCG meeting.
E-Meeting output from WG meetings is stable and has high quality, this is reflected by the few issues which were brought up during SA plenary for technical discussion.
All meetings (WGs and TSGs) until March 2022 are planned as e-meetings. As agreed with the other TSG chairs the planning of e-meetings should be done 6 months ahead.
Not all procedures are aligned across all TSGs/WGs, as different groups have different composition, settings and cultures. This is also the case in face-2-face meetings
Detailed SA & SA WG meeting planning for the case of March / June plenaries being either e-meetings or face-to-face meetings can be found here https://www.3gpp.org/ftp/tsg_sa/TSG_SA/TSGS_93E_Electronic_2021_09/Docs/SP-211139.zip

## Slide 12: For PCG Action
None, besides separately available contributions (e.g. LS out to ITU)

## Slide 13: Acknowledgements
The 3GPP SA Chair wants to thank
the SA Plenary and SA WGs officials for their excellent work, perfect cooperation, coordination and support;
the TSG CT and TSG RAN chairs for very good coordination and cooperation;
MCC for providing all e-meeting facilities in a highliy reliable way, as well as for support and guidance:
the meeting hosting organizations for their great flexibility and very good communication;
all delegates in 3GPP SA and the SA WGs for patience, support, hard work as well as great and stable output.

## Slide 14: Thank You!
Georg Mayer
3GPP SA Chair
mail: georg.mayer@huawei.com
phone: +43 699 1900 5758