## Slide 1: MCPTT-R Status Update Mission Critical Push To Talk over LTE Re-alignment
Andrew Thiessen
U.S. Dept. of Commerce
MCPTT-R Rapporteur
3GPP TSG-SA WG1 Meeting #72
Anaheim, CA, USA, 16-20 November 2015
Remember: present only slides 3, 6, 7
Notes: 1

## Slide 2: MCPTT-R Status
Is this a new WI? Yes
This WI has not been approved by SP
  The following slides assume approval at SP#70
Notes: 1

## Slide 3: MCPTT-R Progress
Progress made at this meeting
  Work Item proposal agreed
  Method for removal of requirements from TS 22.179 identified as common to MCVideo and MCData agreed
  Will keep TS 22.179 and use CR’s to update
Work/Study Item Completion: 0%
Controversial issues
  None
S1-154596
Notes: 1

## Slide 4: MCPTT-R Meeting Time
Number of slots assigned at this meeting
  sum of plenary and drafting slots: 2
Number of slots requested for next meeting
  sum of plenary and drafting slots: 12
Number of Drafting session participants: 15
S1-154596
Notes: 1

## Slide 5: MCPTT-R Completion Date
Target completion date in WID: 03/2016 SP#71
Is current completion date the same as above? Yes
Will target completion date be met? Yes
S1-154596
Notes: 1

## Slide 6: MCPTT-R Planning/Progress
Topics to focus on at next SA1 meeting:
  CR for addition of text into TS 22.179 describing process and rationale used for removal of requirements common to MCVideo and MCData
  CR for removal of identified requirements and (sub)clauses as needed
  CR for addition of informative Annex providing traceability for removed requirements and placement into MCCoRe
S1-154596
Notes: 1

## Slide 7: Work plan between meetings
Email planning
  Email sent on 20/11/2015 laying out plan for project
  Common requirements analysis spreadsheet to be sent to SA1 reflector on 23/11/2015
  First pass of common requirements analysis to be completed on 11/12/2015 and submitted to rapporteur
Email discussion & conference call
  Identification of common requirements
    Focus on disagreements
    Determine grouping for TS structure
    Develop common re-phrasing method
  Planning for Okinawa meeting
  Tentative start date: 14/12/2015
S1-154596
Notes: 1

## Slide 8: MCPTT-R Progress Estimate
Estimated percentage completion:
  now: 0%
  Next meeting: 100%
S1-154596
Notes: 1

## Slide 9: MCPTT-R Agreed documents
List of agreed documents at this meeting:
S1-154396 | U.S. Dept. of Commerce, TTA | Mission Critical Push To Talk over LTE Re-alignment
S1-154596
Notes: 1