## Sheet1
SA WG2 Meeting # | [16 empty] | S2-163688
date, location
Source: SA WG2 Chairman
Title: SA2 Work Planning Worksheet
Document for: Discussion
Agenda Item: 7.2
Work Item / Release: All / Rel-13 and later
Abstract of the contribution: A revision of this document will capture agreements during work planning as SA2 preparations for TSG SA and/or for future SA2 meetings.
SA2#116bis column next to "plan" shows the update compared to what was endorsed during SA2#115
1. Introduction
This paper provides the overview of the work item status at the time of the work planning session.
The budget figures show the estimates for the expected work or show the status reached so far.
Any shown budget figures may require further consolidation.
[11 empty] | Oct 15 |  | Nov 15 |  | Jan 16 |  | Feb 16 |  | Apr 16 |  | May 16 |  | Jul 16 |  | Aug 16 |  | Oct 16 |  | Nov 16
status estimation (%) | [5 empty] | Target |  | acc./plan. | planned | accumul. | SA2#111 |  | SA2#112 |  | SA2#113 |  | SA2#113AH |  | SA2#114 |  | SA2#115 |  | SA2#116 |  | SA2#116bis |  | SA2#117 |  | SA2#118 |  |  |  | percentage of planned resources by meeting #
4/15 | 1/16 | #114 | 2/16 | #116 | Work Item | date |  | TUs (%) | TUs | TUs | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Update during SA#116 | Plan | Actl. | Plan | Actl. |  | 113AH | 114 | 115 | 116 | 116bis | 117 | 118
95 | 100 |  |  |  | FS_AE_CIoT / R13 | 2016-12-15 |  | 100 | 5 | 5 | 4 | 4 | 1 | 1 | [16 empty] | FS_AE_CIoT / R13 | 113AH: 100; percentage of planned resources by meeting # 114: 100; percentage of planned resources by meeting # 115: 100
| 95 |  | 100 |  | CIOT_stage2 / R13 |  | O7 V6 | 136.3636 | 11 | 15 |  |  | 3 | 3 | 3 | 3 | 5 | 9 | [12 empty] | CIOT_stage2 / R13 | 113AH: 100; percentage of planned resources by meeting # 114: 100; percentage of planned resources by meeting # 115: 100
70 | 80 | 90 | 95 |  | FS_eDECOR | 2016-03-16 | O4 V5 | 83.3333 | 6 | 5 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | [7 empty] | FS_eDECOR | 113AH: 50; percentage of planned resources by meeting # 114: 66.6667; percentage of planned resources by meeting # 115: 83.3333
|  |  | 70 |  | eDECOR | 2016-09-16 | O4 V5 | 0 | 1.5 | 0 | [12 empty] | 0.5 |  | 1 | [5 empty] | FS_eDECOR | 113AH: 0; percentage of planned resources by meeting # 114: 0; percentage of planned resources by meeting # 115: 0
20 | 40 | 75 | 100 |  | FS_CUPS | 2016-06-16 | O7 V13 | 129.0323 | 9.3 | 12 | 1 | 2 | 2 | 2 | 2 | 2 |  |  | 2.3 | 2.3 | 2 | 3.7 | [8 empty] | FS_CUPS | 113AH: 53.7634; percentage of planned resources by meeting # 114: 78.4946; percentage of planned resources by meeting # 115: 100
[5 empty] | CUPS | 2016-09-16 | O7 V13 | 0 | 5 | 0 | [12 empty] | 3 |  | 2 | [5 empty] | FS_CUPS | 113AH: 0; percentage of planned resources by meeting # 114: 0; percentage of planned resources by meeting # 115: 0
5 | 15 | 20 | 35 |  | FS_NextGen | 2016-09-16 | many | 47.4627 | 67 | 31.8 |  |  | 1 | 2 | 4 | 4 | 9 | 9 | 6 | 6 | 7 | 10.8 | 10 |  | 10 |  | 10 |  | 10 |  | FS_NextGen | 113AH: 20.8955; percentage of planned resources by meeting # 114: 29.8507; percentage of planned resources by meeting # 115: 40.2985
10 | 22 | 50 | 80 |  | FS_V2XARC | 2016-06-16 | O9 V18 | 96.2617 | 10.7 | 10.3 |  |  | 1 | 1 | 2 | 2 |  |  | 2.7 | 3.3 | 2 | 4 | 3 | [7 empty] | FS_V2XARC | 113AH: 28.0374; percentage of planned resources by meeting # 114: 53.271; percentage of planned resources by meeting # 115: 71.9626
[5 empty] | V2XARC | 2016-09-16 | O9 V18 | 60 | 5 | 3 | [12 empty] | 1 |  | 4 | 3 |  |  |  |  | FS_V2XARC | 113AH: 0; percentage of planned resources by meeting # 114: 0; percentage of planned resources by meeting # 115: 0
| 10 | 85 | 100 |  | FS_GENCEF | 2016-06-16 | O3 V7 | 62.963 | 2.7 | 1.7 |  |  |  |  | 1 | 0.5 |  |  | 0.7 | 0.7 | 1 | 0.5 | [8 empty] | FS_GENCEF | 113AH: 37.037; percentage of planned resources by meeting # 114: 62.963; percentage of planned resources by meeting # 115: 100
[5 empty] | GENCEF | 2016-09-16 | O3 V7 | 0 | 2 | 0 | [12 empty] | 1 |  | 1 | [5 empty] | FS_GENCEF | 113AH: 0; percentage of planned resources by meeting # 114: 0; percentage of planned resources by meeting # 115: 0
|  | 6 | 6 |  | FS_IOPS_LB |  | O7 V5 | 10 | 3 | 0.3 | [8 empty] | 1 | 0.3 | 2 | 0 | [8 empty] | FS_IOPS_LB | 113AH: 0; percentage of planned resources by meeting # 114: 33.3333; percentage of planned resources by meeting # 115: 100
|  | 35 | 70 |  | FS_AE_enTV |  | O4 V5 | 34 | 5 | 1.7 | [8 empty] | 1 | 0.7 | 2 | 1 | 1 |  | 1 | [5 empty] | FS_AE_enTV | 113AH: 0; percentage of planned resources by meeting # 114: 20; percentage of planned resources by meeting # 115: 60
[5 empty] | AE_enTV |  | O4 V5 | 0 | 1 | 0 | [14 empty] | 1 | [5 empty] | FS_AE_enTV | 113AH: 0; percentage of planned resources by meeting # 114: 0; percentage of planned resources by meeting # 115: 0
|  | 50 | 50 |  | NonIP_GPRS |  | O1 V8 | 18.75 | 1.6 | 0.3 | [8 empty] | 0.3 | 0.3 | 0.3 | 0 | 0.5 |  | 0.5 | 0 |  |  |  |  | NonIP_GPRS | 113AH: 0; percentage of planned resources by meeting # 114: 18.75; percentage of planned resources by meeting # 115: 37.5
70 | 80 | 95 | 100 |  | FS_V8 | 2016-03-16 | O11 V8 | 106.8493 | 7.3 | 7.8 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 1.3 | 1.3 |  | 0.5 | [8 empty] | FS_V8 | 113AH: 82.1918; percentage of planned resources by meeting # 114: 100; percentage of planned resources by meeting # 115: 100
|  |  | 60 |  | V8 | 2016-09-16 |  | 20 | 2.5 | 0.5 | [10 empty] | 1 | 0.5 | 1 |  | 0.5 | 0 |  |  |  |  | V8 | percentage of planned resources by meeting # 115: 40
60 | 75 | 95 | 100 |  | FS_SEW2 | 2016-06-16 | O5 V9 | 85.7143 | 7 | 6 | 2 | 1.5 | 2 | 1 | 1 | 1.5 |  |  | 2 | 2 | [10 empty] | FS_SEW2 | 113AH: 71.4286; percentage of planned resources by meeting # 114: 100; percentage of planned resources by meeting # 115: 100
|  |  | 45 |  | SEW2 | 2016-09-16 |  | 66.6667 | 3 | 2 | [10 empty] | 1 | 2 | 1 |  | 1 | [5 empty] | SEW2 | percentage of planned resources by meeting # 115: 33.3333
40 | 70 | 90 | 100 |  | FS_AULC | 2016-06-16 | O6 V7 | 71.6981 | 5.3 | 3.8 | 1 | 1 | 1 | 1 | 1 | 0.5 |  |  | 1.3 | 1.3 | 1 | [9 empty] | FS_AULC | 113AH: 56.6038; percentage of planned resources by meeting # 114: 81.1321; percentage of planned resources by meeting # 115: 100
|  |  | 10 |  | AULC | 2016-09-16 | O6 V7 | 66.6667 | 1.5 | 1 | [11 empty] | 1 | 1 |  | 0.5 | [5 empty] | FS_AULC | 113AH: 0; percentage of planned resources by meeting # 114: 0; percentage of planned resources by meeting # 115: 0
| 30 | 50 | 70 |  | FS_SeDoC | 2016-06-16 | O5 V3 | 60 | 5 | 3 |  |  | 1 |  | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | [7 empty] | FS_SeDoC | 113AH: 40; percentage of planned resources by meeting # 114: 60; percentage of planned resources by meeting # 115: 80
[5 empty] | SeDoC | 2016-09-16 | O5 V3 | 0 | 1 | 0 | [14 empty] | 1 | [5 empty] | FS_SeDoC | 113AH: 0; percentage of planned resources by meeting # 114: 0; percentage of planned resources by meeting # 115: 0
10 | 40 | 85 | 100 |  | FS_SDCI | 2016-06-16 | O6 V7 | 158.1395 | 4.3 | 6.8 |  |  | 1 | 1 | 1 | 1.5 |  |  | 1.3 | 2 | 1 | 2.3 | [8 empty] | FS_SDCI | 113AH: 46.5116; percentage of planned resources by meeting # 114: 76.7442; percentage of planned resources by meeting # 115: 100
[5 empty] | SDCI | 2016-09-16 | O6 V7 | 0 | 2.5 | 0 | [12 empty] | 1.5 |  | 1 | [5 empty] | FS_SDCI | 113AH: 0; percentage of planned resources by meeting # 114: 0; percentage of planned resources by meeting # 115: 0
| 20 | 50 | 100 |  | EIEI | 2016-06-16 | O4 V5 | 100 | 3 | 3 |  |  |  |  | 1 | 1 |  |  | 1 | 1 | 1 | 1 | [8 empty] | EIEI | 113AH: 33.3333; percentage of planned resources by meeting # 114: 66.6667; percentage of planned resources by meeting # 115: 100
45 | 60 | 100 | 100 |  | EWE | 2016-06-16 | O4 V5 | 41.0714 | 2.8 | 1.15 |  |  | 1 | 0.5 | 1 | 0.25 |  |  | 0.3 | 0.3 | 0.5 | 0.1 | [8 empty] | EWE | 113AH: 71.4286; percentage of planned resources by meeting # 114: 82.1429; percentage of planned resources by meeting # 115: 100
| 20 | 45 | 100 |  | FS_RobVoLTE | 2016-06-16 | O6 V8 | 100 | 3 | 3 |  |  |  |  | 1 | 1 |  |  | 1 | 1 | 1 | 1 | [8 empty] | FS_RobVoLTE | 113AH: 33.3333; percentage of planned resources by meeting # 114: 66.6667; percentage of planned resources by meeting # 115: 100
[5 empty] | RobVoLTE | 2016-09-16 | O6 V8 | 0 | 0.5 | 0 | [12 empty] | 0.5 |  |  | 0 |  |  |  |  | FS_RobVoLTE | 113AH: 0; percentage of planned resources by meeting # 114: 0; percentage of planned resources by meeting # 115: 0
[5 empty] | PS data off | 2016-12-16 |  | 50 | 4 | 2 | [12 empty] | 1 |  | 1 | 2 | 1 |  | 1 |  | PS data off | percentage of planned resources by meeting # 115: 0
[5 empty] | FS_CIOT_ext | 2016-12-16 |  | 0 | 6 | 0 | [12 empty] | 2 |  | 2 |  | 1 |  | 1 |  | CIOT | percentage of planned resources by meeting # 115: 0
[5 empty] | VoWLAN | 2016-12-16 |  | 0 | 3 | 0 | [16 empty] | 2 |  | 1 |  | VoWLAN | percentage of planned resources by meeting # 115: 0
[5 empty] | eFMSS | 2016-09-16 |  | 0 | 1 | 0 | [12 empty] | 0.5 |  | 0.5 | 0 |  |  |  |  | eFMSS | percentage of planned resources by meeting # 115: 0
[5 empty] | eT-ADS | 2016-09-16 |  | 40 | 1.25 | 0.5 | [12 empty] | 1 |  | 0.25 | 0.5 |  |  |  |  | eMB2 | percentage of planned resources by meeting # 115: 0
[5 empty] | Maint 5.1 / 6.1 |  |  |  |  | 27 | 2 | 3 | 2 | 3 | 3 | 3 |  |  | 4.7 | 10 | 4 | 8 | 4 |  | 4
[5 empty] | Maint 5.2 / 6.2 |  |  |  |  | 3 |  |  |  |  | 1 | 1 |  |  | 1.3 | 1 | 1 | 1 | 1 |  | 1
[5 empty] | Maint 5.3 / 6.3 |  |  |  |  | 11.6 | 2 | 3.5 | 2 | 3.5 | 3 | 2.5 |  |  | 2.7 | 2 | 2 | 0.1 | 1 |  | 1
[5 empty] | Maint 5.4 / 6.4 |  |  |  |  | 4 | 1 | 0.5 | 1 | 1 | 1 | 0.5 |  |  | 1 | 1 | 0.5 | 1 | 1 |  | 1
[5 empty] | TEI14 3GPP acc |  |  |  |  | 1 | 1 | 1 | [13 empty] | 0.5 for AOB propsal from Saso
[5 empty] | TEI14 PCC/QoS |  |  |  |  | 0.5 | 0.5 | 0.5
[5 empty] | TEI14 n3GPP | [15 empty] | 0.5
[5 empty] | TEI14 IMS/rel. |  |  |  |  | 0 | 0.5 | [9 empty] | 1 |  |  |  |  | 0.5 for Curt's proposal
[5 empty] | sum | [5 empty] | 18 | 22 | 22 | 23 | 30 | 28.25 | 14 | 18 | 33.9 | 38.5 | 33.8 | 40.5 | 38.5 | 0 | 35.25 | 5.5 | 4 | 0 | 13 | 0
[11 empty] | Oct 15 |  | Nov 15 |  | Jan 16 |  | Feb 16 |  | Apr 16 |  | May 16 |  | Jul 16 |  | Aug 16 |  | Oct 16 |  | Nov 16
status (%) | [8 empty] | planned | accumul. | SA2#111 |  | SA2#112 |  | SA2#113 |  | SA2#113AH |  | SA2#114 |  | SA2#115 |  | SA2#116 |  | SA2#116bis |  | SA2#117 |  | SA2#118
4/15 | 1/16 | #114 | 2/16 | #116 |  |  |  |  | TUs | TUs | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl.
|  |  | 85 |  | common aspects |  |  |  | 20 | 17 |  |  | 1 | 2 | 4 | 4 | 9 | 9 | 1 | 1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 1
|  |  | 30 |  | KI1: Support of network slicing |  |  |  | 6 | 2 | [8 empty] | 1 | 1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 1
|  |  | 60 |  | KI2: QoS framework |  |  |  | 6 | 3 | [8 empty] | 1 | 1 | 1 | 2 | 1 |  | 1 |  | 1 |  | 1
|  |  | 50 |  | KI3: Mobility framework |  |  |  | 6 | 4 | [8 empty] | 1 | 1 | 1 | 3 | 1 |  | 1 |  | 1 |  | 1
|  |  | 50 |  | KI4: Session management |  |  |  | 5.5 | 1.5 | [8 empty] | 0.5 | 0.5 | 1 | 1 | 1 |  | 1 |  | 1 |  | 1
|  |  | 60 |  | KI5: Enabling (re)selection of efficient UP paths |  |  |  | 4.3 | 0.3 | [10 empty] | 0.3 | 0.3 | 1 |  | 1 |  | 1 |  | 1
|  |  | 60 |  | KI6: session/service continuity |  |  |  | 4.7 | 1 | [10 empty] | 0.7 | 1 | 1 |  | 1 |  | 1 |  | 1
|  |  | 30 |  | KI7: Network function granularity and interactions between them |  |  |  | 4.7 | 0.7 | [10 empty] | 0.7 | 0.7 | 1 |  | 1 |  | 1 |  | 1
|  |  | 30 |  | KI8: core - access - functional division and interface |  |  |  | 5.3 | 1.5 | [8 empty] | 1 | 1 | 0.3 | 0.5 | 1 |  | 1 |  | 1 |  | 1
KI9: network capability exposure
|  |  | 0 |  | KI10: Policy Framework
KI11: Charging
|  |  | 50 |  | KI12: Authentication framework |  |  |  | 1.2 | 0.8 | [8 empty] | 0.5 | 0.5 | 0.7 | 0.3 | 0 |  | 0 |  | 0 |  | 0
KI13: Broadcast/Multicast Capabilities
KI14: Support for Off-Network Communication
KI15: NextGen core support for IMS
KI16: connectivity via a relay UE
|  |  | 0 |  | KI17: network discovery and selection
|  |  | 0 |  | KI18: Interworking and Migration | [19 empty] | 1
|  |  | 0 |  | KI19: using virtual environments
|  |  | 0 |  | KI20: Traffic steering
KI21: Extrem rural
|  |  | 10 |  | TR clause 7 / overall architecture
|  |  | 32.1875 |  | <- Average ¦ SUM -> | [5 empty] | 0 | 0 | 1 | 2 | 4 | 4 | 9 | 9 | 6 | 6 | 7.7 | 10.8 | 9 | 0 | 10 | 0 | 9 | 0 | 9 | 0