## Slide 1: FS_eNPN Status Report
Peter Hedman
Ericsson

## Slide 2: FS_eNPN Status at SA#87
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNPN | Enhanced support of Non-Public Networks | 15% > 35% | June, 20 | SP-190453
Progress since SA#86:
  Key Issues #5 (Support for equivalent SNPNs) and #6 (Support of non-3GPP access for SNPN services) marked as not addressed within Rel-17 timeframe as a result of TSG#86 Rel-17 prioritization
  Key Issue 2 clarified
  One solution updated, and 6 new solutions were agreed for inclusion in the TR 23.700-07
  Sent LS to SA1 (cc: SA, CT1, SA3, CT6) asking clarifications from SA1 regarding KI #4
  Revised WID submitted for Approval (SP-19xxxx) aligning scope to agreed Rel-17 prioritization at TSG#86.
  RAN impacts and dependencies:
  RAN impact depends on the conclusions of the KIs (e.g. KI#1, KI#4).
Next steps:
  Complete description of existing solutions, and add new solutions e.g. for key issues without solutions.
  Start initial evaluation, and agree on conclusions

## Slide 3: FS_eNPN status after SA2#136AH (1/2)
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNPN | Enhanced support of Non-Public Networks | 15% > 35% | June, 20 | SP-190453
General
  FS_eNPN TR 23.700-07 v0.3.0 is available here.
  Total TUs requested for Study Phase in 2020 is 5. 2 TUs are used and 3 TUs are remaining.
  Key Issues #5 (Support for equivalent SNPNs) and #6 (Support of non-3GPP access for SNPN services) marked as not addressed within Rel-17 timeframe as a result of down-scoping exercise.
Key Issue 1 (Enhancements to Support SNPN along with credentials owned by an entity separate from the SNPN):
  One solution updated, and 3 new solutions were agreed for inclusion in the TR. Total number of solutions for KI#1 is 4.
  Next Steps: Next meeting (SA2#138) should be the last meeting to propose new solutions for KI. Proceed with evaluations and (interim) conclusions.
Key Issue 2 (NPN support for Video, Imaging and Audio for Professional Applications (VIAPA))
  KI clarified
  No solutions focused on this KI could be handled due to lack of time.
Key Issue 3 (Support of IMS voice and emergency services for SNPN)
  No contributions focused on this KI could be handled due to lack of time.
Key Issue 4 (UE Onboarding and remote provisioning)
  Sent LS to SA1 (cc: SA, CT1, SA3, CT6) asking clarifications from SA1
  Agreed 3 solutions for inclusion in the TR.

## Slide 4: FS_eNPN status after SA2#136AH (2/2)
  RAN impacts and dependencies:
  Key issues 1 and 4 may potentially lead to solutions with RAN impact and may require RAN coordination.
  RAN impacts due to key issues 2 and 3 are still unknown
  RAN intended to discuss NPN enhancements related work at TSG RAN#87
Contentious Issue:
  Scope for UE provisioning in relation to IMSI and AKA (see Q1 in S2-2001729)
  Scope for KI#4 in relation to PNI-NPN (see Q2 and Q3 in S2-2001729)
Focus for the Next Meeting (SA2#138):
  New solutions for key issues 2 and 3
  Solutions and possibly way forward for key issues 1 and 4
  Find a way to resolve RAN as well as SA3 dependencies as given the delayed start of eNPN related work in RAN and SA3.
    Collect open issues / questions and seek RAN WGs’ and SA3 feedback with LS OUT from SA2#138.
  Any new Key Issue will be low priority unless supported by large number of companies.
Overall Plan:
  SA2#137E (Feb): Agree revised SID
  SA2#138 (Apr): Complete description of existing solutions, and add new solutions (i.e. all submitted solutions should be complete). Start initial evaluation, and possibly interim conclusions.
  SA2#139 (May): Final evaluation and conclusions. Submit TR 23.700-07 to SA#87 plenary for approval. Agree a WID.
  SA2#140 (Aug):