## Slide 1: FS_AMP Status Report
Zhuoyi Chen
China Telecom (Rapporteur)

## Slide 2: FS_AMP status after SA2#152E (1/2)
General
  TR 23.700-89 v0.3.0 is available and ready for TSG SA#97E approval
  Evaluation and Conclusion are documented
  Study phase is completed.
  Normative WID is submitted and approved at SA2
Key Issue #1: RFSP Index consistency when UE moves from 5GC to EPC
  4 papers for solution update are approved.
  Evaluation and Conclusion on KI#1 per N26 based and without N26 interface interworking scenario are discussed and reach agreement.
Next Steps: SA2 normative work based on the conclusion (0.5TU)
  RAN impacts and dependencies:
  No RAN impacts or dependencies are identified
WI Code | Work Item Title | WP | Target Date | WID#
FS_AMP | Study on 5G AM Policy | 80% > 100% | Sept, 22 | SP-211642

## Slide 3: FS_AMP status after SA2#152E (2/2)
Contentious Issue:
  None
Focus for the Next Meeting (SA2#153E):
  Normative work begins at SA2.
Overall Plan:
  SA2#149-E, 0.5 TU assigned, TR Skeleton, TR Scope, Architectural Assumption, Key Issues, allow solutions.
  SA2#150-E, 0.5 TU assigned, no new Key Issue could be allowed and the last e-meeting for new solution(s).
  SA2#151-E, no TU assigned.
  SA2#152-E, 0.5 TU assigned, for solution clean-up, evaluation and conclusion. Normative WID creation. Submit TR23.700-89 to SA#97E.
  SA2#153-E: 0.25 TU assigned, for normative
  SA2#154AH: 0.25 TU assigned, for normative
Risks:
  None.

## Slide 4: FS_AMP status at SA#96E
General
  TR23.700-89 is ready for approval
  Evaluation and conclusion are documented
  Study phase is completed and normative WID proposal is for SA Plenary approval
  RAN impacts and dependencies
  No RAN impacts or dependencies are identified
Next steps
  SA2#153E (0.25 TU): Normative work begins at SA2.
WI Code | Work Item Title | WP | Target Date | WID#
FS_AMP | Study on 5G AM Policy | 80% > 100% | Sept, 22 | SP-211642