## Slide 1: TEI20_NEPS WI Status Report
Alessio Casati(Rapporteur)
Nokia
3GPP TSG-WG SA2 Meeting #171
Wuhan, China, October 13 – October 17, 2025

## Slide 2
Progress since SA#109:
  Two CRs (one for 23.501 and one for 23.502) were agreed,
    Added the support for NSSAA over EPC.
Impacts and dependencies on other WGs:
  CT1 to define the Pending indicator in PCO and the support of the NSSAA over EPC indicator in PCO.
Next steps:
  Resolve editor’s notes on the need of indication or UE MM capability in 5GS and on the storage in UDM of the outcome of NSSAA at SMF+PGW-C and AMF. Once resolved more impacts to CT1/CT4 may be identified.
TEI20_NEPS status at SA#110
UID | Name | Acronym | Old% | New% | Target Date | WID | Change or comment
1090005 | Support of NSSAA in EPS | TEI20_NEPS | 0% | 90% | Dec 2025 | SP-251210 | 0.5 TU still available at SA2#172

## Slide 3
TEI20_NEPS status report after SA2#171
UID | Name | Acronym | Old% | New% | Target Date | WID | Change or comment
1090005 | Support of NSSAA in EPS | TEI20_NEPS | 0% | 90% | Dec 2025 | SP-251210 | 0.5 TU still available at SA2#172
Progress in SA2#171
  Two CRs agreed (TS 23.501 and TS 23.502).
  This TEI20 WI is 90% complete
  RAN impacts and dependencies
  None
Contentious issues
  None
Next steps
  Resolve editor’s notes on the need of indication or UE MM capability in 5GS and on the storage in UDM of the outcome of NSSAA at SMF+PGW-C and AMF.