## Slide 1: CT WG4 Status Report to TSG CT#86
Peter Schmitt
3GPP TSG CT WG4 Chairman, Huawei

## Slide 2: TSG CT4 Officials
Peter Schmitt
TSG CT WG4 Chairman
CCSA
peter.schmitt@huawei.com
Song Yue
TSG CT WG4 Vicechair
CCSA songyue@chinamobile.com
Yvette Koza
TSG CT WG4 Vicechair
ETSI
yvette.koza@magenta.at
Kimmo Kymalainen
Secretary
MCC
kimmo.kymalainen@3gpp.org

## Slide 3: Meeting Calendar
Since the last CT plenary
  Ordinary:
    CT4#94 (Portoroz, SL)
    CT4#95 (Reno, US)
  Ad-hoc:
    None
Upcoming Meetings
  Ordinary:
    CT4#96 (Sophia-Antipolis, FR)
  Ad-hoc:
    None

## Slide 4: TSG WG CT4 Statistics
Number of handled documents
  563 in CT4#94
  564 in CT4#95
Agreed CRs
  Cat B(193)/C(2)/F(130)
Agreed pCRs
  58
Attendances
    CT4#94 (Portoroz, SL): 83 present: ~35
    CT4#95 (Reno, US): 98 present: ~32
Other information
    5GS_Ph1-CT
  In CT4#94&95 agreed CAT F: 40 (11CRs for version update) (in Q3: 46)
    Release 16 work:
  In CT4#94&95 agreed CAT B: 193 (in Q3: 145)

## Slide 5: New/revised agreed Study/Work Items led by CT4
TDoc # | Title | Source | Objectives
CP-193013 | [NUDSF] – New WID Nudsf Service Based Interface | Hewlett-Packard Enterprise | to provide the stage 3 definition of the service based Nudsf service defined in 3GPP TS 23.502. The Nudsf will provide the following capabilities: - REST-style service operations to support Create, Read, Update and Delete. - Support a search capability with a filter criteria on meta tags. - Support Subscribe to Notifications and Notification of data change as an optional capability. - Support multiple logical storage spaces. - Support common data types as well as the storage of binary data
CP-193017 | [NSORAF] – New WID on Nsoraf Service Based Interface | Orange | Finalize the work on this 5G SoR mechanism: -Define the protocol and interface aspects of the interactions between a NF Consumer (e.g. the UDM) and the new SOR-AF over the Nsoraf Service-based interface. -Define the mechanisms to support the updated list of preferred networks. -Clarify potential impacts on UDM services. -Clarify the specific use of the UDR used by the UDM during the SoR procedure, -Any further alignment with stage 2 defined in the 3GPP TS 23.122

## Slide 6: New/revised agreed Study/Work Items led by CT4
TDoc # | Title | Source | Objectives
CP-193016 | [UDICOM] – Revised WID on User data interworking, Coexistence and Migration | Nokia | Target date for the new TS 23.632 is modified
CP-193014 | [5G_SRVCC] – Revised WID on CT aspect of single radio voice continuity from 5GS to 3G, | China Unicom/ZTE | CT4 impacted are enhanced by the Impacts to Nsmf_PDUSession service to support 5G SRVCC
CP-193015 | [IABARC-CT] – New WID on 5G CT aspects of support for integrated access and backhaul, is Rapporteuer | Qualcomm | CT1 Impacts are removed to align with stage 2 agreements, IAB node capabilities are not signaled via NAS

## Slide 7: Work Plan (1/3)
Name | Acronym | Start | End | % | WID
CT4 Aspects of 5G_URLLC | 5G_URLLC | 06/06/2019 | 12/03/2020 | 20% now 60% | CP-191063
CT4 aspects of Vertical_LAN | Vertical_LAN | 14/03/2019 | 12/03/2020 | 50% now 85% | CP-191157
CT4 aspects of 5G_CIoT | 5G_CIoT | 14/03/2019 | 12/03/2020 | 25% now 60% | CP-111237
CT4 aspects of V2XAPP | V2XAPP | 06/06/2019 | 12/03/2020 | 0% | CP-191153
CT4 aspects of eV2XARC | eV2XARC | 06/06/2019 | 12/03/2020 | 0% | CP-191154
CT4 aspects of 5G_eLCS | 5G_eLCS | 07/03/2019 | 05/12/2019 | 20% now 90% | CP-191064
CT4 aspects of RACS | RACS | 06/06/2019 | 12/03/2020 | 20% now 75% | CP-191061
CT4 aspects of eNA | eNA | 07/03/2019 | 05/12/2019 | 25% now 90% | CP-191111
CT4 aspects of 5WWC | 5WWC | 13/06/2019 | 12/03/2020 | 5% now 60% | CP-191156
CT4 aspects of eNAPIs | eNAPIs | 06/09/2018 | 13/12/2019 | 0% now 80% | CP-192184
Legend Green row – Newly completed
Yellow row – on time for completion on time Red row – at risk for completion on time
98 – no progress since the last plenary
98 - Updated

## Slide 8: Work Plan (2/3)
Name | Acronym | Start | End | % | WID
CT4 aspects of eNS | eNS | 07/03/2019 | 05/12/2019 | 50% now 95% | CP-190196
CT4 aspects of PARLOS | PARLOS | 14/03/2019 | 12/12/2019 | 0% now 100% | CP-190197
CT4 aspects of ETSUN | ETSUN | 08/03/2019 | 06/12/2019 | 95% now 100% | CP-190192
CT4 aspects of ATSSS | ATSSS | 11/03/2019 | 09/12/2019 | 45% now 75% | CP-190201
CT4 aspect of 5G_SRVCC | 5G_SRVCC | 06/06/2019 | 12/03/2020 | 60% now 80% | CP-191062
CT4 aspects of 5G_eSBA | 5G_eSBA | 14/03/2019 | 12/12/2019 | 40% now 70% | CP-190191
CT4 aspects of eIMS5G_SBA | eIMS5G_SBA | 06/06/2019 | 12/03/2020 | 25% now 50% | CP-191065
CT4 Aspects of E2E_DELAY | E2E_DELAY | 14/03/2019 | 12/12/2019 | 100% | CP-190193
CT aspects of UDICOM | UDICOM | 06/06/2019 | 12/03/2020 | 25% now 75% | CP-191066
Shared Data Handling on Nudm and Nudr | Shared_Data | 06/06/2018 | 14/12/2018 | 100% | CP-181136
Legend Green row – Newly completed
Yellow row – on time for completion on time Red row – at risk for completion on time
98 – no progress since the last plenary
98 - Updated

## Slide 9: Work Plan (3/3)
Name | Acronym | Start | End | % | WID
CT4 aspects of SBIProtoc16 | SBIProtoc16 | 06/06/2019 | 12/03/2020 | 45% now 90% | CP-191060
Study on Load and Overload Control of 5GC Service Based Interfaces | FS_LOLC | 06/06/2018 | 14/06/2019 | 90% now 100% | CP-181195
Study on IETF QUIC Transport for Service Based Interfaces | FS_QUIC | 06/06/2018 | 12/06/2019 | 80% | CP-183245
Study on User Plane Protocol in 5GC | FS_UPPS | 15/12/2017 | 14/06/2019 | 100% | CP-182052
Study on Nudsf Service Based Interface | FS_NUDSF | 06/06/2019 | 12/12/2019 | 30% now 100% | CP-191236
Load and Overload Control of 5GC Service Based Interfaces | LOLC | 18/09/2019 | 12/03/2020 | 0% | CP-192019
5GS Enhanced support of OTA mechanism for configuration parameter update | 5GS_OTAF | 18/09/2019 | 12/03/2020 | 0% now 65% | CP-192021
CT aspects of support for integrated access and backhaul | IABARC | 18/09/2019 | 12/03/2020 | 0% | CP-193
Nudsf Service Based Interface | NUDSF | 09/12/2019 | 12/03/2020 | 5% | CP-193
Nsoraf Service Based Interface | NSORAF | 09/12/2019 | 12/03/2020 | 5% | CP-193
Legend Green row – Newly completed
Yellow row – on time for completion on time Red row – Behind the schedule
98 – no progress since the last plenary
98 - Updated

## Slide 10: Work Plan and Release 16
Evaluation of the workplan and background
  Overall CT4 is on time for Release 16 work
  -for some WI we are ahead of schedule and for some little behind
  In November we started the work on 3 new TSs, the TS Rapporteuers acknowledged that it is a challenge but possible to compete the TSs in Next CT4 meeting.
  The WIDs which are marked as on risk there was the clear statement from the supporting companies to complete the work on time
  e.g. For LOLC the Rapporteuer promised to distribute a workplan, organise and schedule conference calls to clairify topics in advance of the next meeting.
The status of the work is also reflected in the TSs send for Information or information and approval a subset of the archivements are also mentioned in the following slides.

## Slide 11: TS/TR sent to CT plenary
TDoc # | Title | Version | Rapporteurs | Sent for
CP-193066 | 3GPP TS 23.632 v1.0.0 on User data interworking, coexistence and migration; Stage 2 | 1.0.0 | Nokia | Information and approval
CP-193068 | 3GPP TR 29.808 v1.0.0 on Study on the Nudsf Service Based Interface | 1.0.0 | HPe | Information and approval
CP-193067 | 3GPP TS 29.563 v1.0.0 on 5G System (5GS); Home Subscriber Server (HSS) services for interworking with Unified Data Management (UDM); Stage 3 | 1.0.0 | Ericsson | Information
CP-193065 | 3GPP TS 29.515 v1.0.0 on 5G System; GMLC Services; Stage 3 | 1.0.0 | CATT | Information
CP-193069 | 3GPP TS 29.673 v1.0.0 on 5G System; UE Radio Capability Management Services; Stage 3 | 1.0.0 | Ericsson | Information
CP-193070 | 3GPP TS 29.674 v1.0.0 on Interface between the UCMF and the MME; Stage 3 | 1.0.0 | Ericsson | Information
CP-193071 | 3GPP TS 29.544 v1.0.0 on 5G System (5GS); Over The Air (OTA) services; Stage 3 | 1.0.0 | Nokia | Information
CP-193072 | 3GPP TS 29.541 v1.0.0 on 5G System (5GS); Session management services for Nxx Ixx Dxx Dxx (NIDD); Stage 3 | 1.0.0 | Ericsson | Information

## Slide 12: Release 15 Status
Title:
  CT aspects on 5G System –Phase 1 (CT1)
Objectives:
  After completion of the Study, specify the service-based interfaces (API)
  CT4 responsible for the specification of core-network SBIs (except PCC) and impacts on existing protocols (e.g. GTP, PFCP)
WID: 100% completed
Normative Phase:
  Consolidation of API specifications e.g. External groupID definition
  24 essential corrections are agreed (in Q3 46 CRs were agreed/approved)
<10% of the meeting time we spend to 5GS, work is going down

## Slide 13: Release 16 Status
Title:
  Study on Nudsf Service Based Interface [FS_NUDSF](CT4)
Objectives:
  Study the Nudsf service as a service based interface and as defined in 3GPP TS 23.502.
  Study required operations
  Study subscribe to notifcations of data change and the notifications of data change
TR: 29.808 v 1.0.0
Status:
  SBI based solution with Key-Value Pair is the only solution and now agreed to be standardised.
  TR is send for information and approval
Next steps:
  Work is seen as completed.
  WID to start normative work is agreed and the skeleton of the new TS
SID completion: 100%

## Slide 14: Release 16 Status
Title:
  CT aspects on Enhancements to the Service-Based 5G System Architecture [5G_eSBA] (CT4)
Objectives (e.g.):
  Specify procedures for the SBIs under remit of CT4 to support binding between the NF service producer and NF service consumer, where necessary
  Specify the general concept and procedures for NF set
Status:
  It is agreed to convey delegated Discovery Parameters in HTTP/2 Headers (one header for each NF service discovery), discovery factors signalled within the protocol are removed
  new headers are agreed e.g. the 3gpp-Sbi-Discovery-notification-type header set to the type of notification being set, the 3gpp-Sbi-Discovery-target-nf-type header indicating the type of the consumer NF
  A new header 3gpp-Sbi-Target-apiRoot header is introduced which can be used as an alternative to use wildcard certificates and telescopic FQDNs (introduced in Rel-15), which solution is used in a network is an operator choice. SA3 provided feedback that the proposed solution is inline with 5G security.
  WID completion: 70%

## Slide 15: Release 16 Status
Title:
  Service based Interface protocol improvements [SBIProtoc16]
Objectives:
  Introduction of optimisations and improvements on SBI services, e.g. improve the criteria for NF selection
Status:
  In the NRF: NF servingScope reflecting the served area(s) of the NF instance, this may reflect geographical areas is addded as selection creteria
  In the NRF: Preferred API Version is added as selection criteria
  It is clarified that subscribed DNNs for the UE may contain wildcard DNN
WID completion: 90%

## Slide 16: Release 16 Status
Title:
  Technical Enhancements and improvements [TEI16]
Objectives:
  N4 enhancements/Improvements.
Status:
  To use the N4 Interface to configure predefined rules in UPF was discussed and postponed as we could not reach consensus half of the companies thought that N4 Interface should not be used to configure UPF, O&M interface should be the preferred interfaces for this task.
Next steps:
  Offline discussion is requested to be performed to reach consensus on the requirement and possible solution

## Slide 17: Backward Incompatible Changes
In “Frozen” specification, with impact on other TSG WGs
TDoc # | Title | Source | Impacted TS | Impacted TSG WG
No CR was marked as backward incompatible this time.

## Slide 18: For Information to CT
  Per decision from last CT plenary the use of ETSI Forge Phase is now mandated.
  All data is now under 3GPP/ 5G-APIs
  The move from Play ground to the new repository went very smoothly without any problems
  Check of the OpenAPI specification files by the rapporteur/delegates
  ETSI Forge is used by all Rapporteurs now, the cross check of OpenAPI files is performed by all rapporteurs when uploading files
  Meeting participation
  CT4 is a small group with limited number of delegates.
  Companies have up to 3 delegates active
  In last meeting some delegates had trouble to get visa US
  In worst case scenario a company is not present at all if one delegate did not get a visa

## Slide 19: For Action to CT
LS
Rel-16 Reply LS on support of Remote Interference Management send in copy to CT:
CT4 Informs RAN3 that the attached 29.518 CR0240 (CP-193036) to support transferring RIM information between AMFs. The approval of the CR at CT#86 is conditioned to the approval by RAN#86 of the related RAN3 agreed CR (TS 38.413 CR 0137).

## Slide 20: Acknowledgement
The Chairman wants to:
  Thank CT4 delegates for their dedication and their excellent team spirit on the 5GS related specifications
  Thank CT3 Chair Susana and CT3 delegates for the coordination and the joint sessions on 5GS work between CT3 and CT4
  Thank WI and spec rapporteurs for their priceless coordination work and the pre-editing work of the 5GC specifications and check of the Open API files
  Thank CT4 vice chairs Yvette Koza and Song Yue for their help in CT4 management, especially in chairing the parallel sessions.
  Thank Kimmo for his hard work as MCC (and his guidelines)
  Thanks to ETSI support and providing IT facilities.
  Thank the hosts EF3 of the meeting in Portoroz and NAF3 of the meeting in Reno.

## Slide 21: Annex

## Slide 22: CRs for Conditional Approval
CRs with dependencies to other groups agreed CRs
CP-TD# | TS | CR | Title | C4 TD# | Other Affected Specs | Affected WG
CP-193050 | 23.003 | 0553 | Global uniqueness of NID | C4-195256 | TS 23.501 CR 1797 | SA2
CP-193036 | 23.008 | 0574 | Adding support for subscription-based access restriction in 5GS | C4-195559 | TS 23.501 CR 1847 | SA2
CP-193040 | 29.229 | 0294 | S-CSCF restoration after registration timer expiry | C4-194097 | TS 23.380 CR 0110 | C4
CP-193038 | 29.230 | 0666 | New Error Code for TS 29.336 | C4-194464 | TS 29.336 CR 0159 | C4
CP-193040 | 29.230 | 0667 | S-CSCF restoration after registration timer expiry | C4-194545 | TS 29.229 CR 0294 | C4
CP-193051 | 29.244 | 0300 | Handling of GBR traffic of a MA PDU session | C4-195546 | TS 29.244 CR 0322 | C4
CP-193041 | 29.274 | 1975 | Unlicensed spectrum NR-U restrictions | C4-195519 | TS 23.401 CR 3547 TS 23.501 CR 1847 | SA2
CP-193049 | 29.502 | 0223 | Adding Rate Control attributes to the Release operations | C4-195582 | TS 23.502 CR 1808r3 | SA2
CP-193049 | 29.502 | 0224 | Adding Rate Control attributes to the Update operations | C4-195472 | TS 23.502 CR 1808r3 | SA2
CP-193051 | 29.502 | 0231 | MA PDU request indication | C4-195424 | TS 23.502 CR 1770 | SA2
CP-193224 | 29.502 | 0240 | Event subscriptions in SM Context | C4-195248 | TS 23.502 CR 1736 | SA2
CP-193056 | 29.502 | 0241 | Missing DNAI list across N16a | C4-195535 | TS 23.502 CR 1737r1 | SA2

## Slide 23: CRs for Conditional Approval
CRs with dependencies to other groups agreed CRs
CP-TD# | TS | CR | Title | C4 TD# | Other Affected Specs | Affected WG
CP-193061 | 29.502 | 0243 | PDU Session Release due to SRVCC | C4-195575 | TS 23.216 CR 0359 | SA2
CP-193050 | 29.503 | 0250 | Serving Network Name in SNPN | C4-194532 | TS 23.003 CR 0553 TS 24.501 CR 1511 | C4 C1
CP-193046 | 29.503 | 0252 | QoS for wireline access network | C4-195502 | TS 23.316 CR 0052 | SA2
CP-193049 | 29.503 | 0261 | UE expected behaviour in SDM | C4-195505 | TS 29.503 CR0258 | C4
CP-193036 | 29.503 | 0282 | Updating support for subscription-based access restriction | C4-195557 | TS 23.501 CR 1847 | SA2
CP-193055 | 29.504 | 0060 | LCS privacy | C4-194469 | TS 29.505 CR0109 | C4
CP-193055 | 29.504 | 0061 | Mobile Originated Data | C4-194472 | TS 29.505 CR0110 | C4
CP-193055 | 29.505 | 0109 | LCS privacy | C4-194553 | TS 29.504 CR0060 | C4
CP-193055 | 29.505 | 0110 | Mobile Originated Data | C4-195135 | TS 29.504 CR0110 | C4
CP-193036 | 29.518 | 0240 | RIM Information Transfer procedure | C4-194112 | TS 38.413 CR 0137 | RAN3
CP-193164 | 29.518 | 0261 | Updating support for subscription-based access restriction | C4-195558 | TS 23.501 CR 1847 | SA2

## Slide 24: CRs for Conditional Approval
CRs with dependencies to other groups agreed CRs
CP-TD# | TS | CR | Title | C4 TD# | Other Affected Specs | Affected WG
CP-193046 | 29.571 | 0136 | QoS for wireline access network | C4-195594 | TS 23.316 CR 0052 | SA2
CP-193049 | 29.571 | 0149 | LTE-M RAT Type | C4-195102 | TS 23.501 CR 1363 | SA2
CP-193036 | 29.571 | 0150 | Adding support for NR and E-UTRA accessing through unlicensed bands | C4-195560 | TS 23.501 CR 1847 | SA2

## Slide 25: Thank You!
Peter Schmitt
3GPP TSG CT WG4 Chairman
Peter.schmitt@huawei.com