## Cover sheet
3GPP TSG-RAN WG5 meeting #99 | [8 empty] | R5-232120
Incheon, South Korea, 22 – 26 May 2023
Agenda Item: | 7.4.2
Source: | Nokia, Apple
Title: | WP UE Conformance Test Aspects for NR RF Requirement Enhancements for FR2
Work item code: | NR_RF_FR2_req_enh-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The objective of this work item is to define the UE conformance requirements corresponding to WID (830089) on NR RF requirement enhancements for FR2. This work item will cover RF conformance test specifications for NR RF requirement enhancements for FR2. At the RAN#91-e meeting in March 2021 the Rel-16 RAN5 work item for UE Conformance Test Aspects for NR RF Requirement Enhancements for FR2 was approved [1]. The purpose of present document is to provide a workplan for the RAN5 work item on the conformance test cases for the core requirement introduced by the core and performance work items. The workplan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 97% (+3%) | 20.4 (+0.4) | 20.7
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR2) |  | 97.1% (+3%) | 20.4 (+0.4) | 20.7
FR2 |  | 97.1% (+3%) | 20.4 (+0.4) | 20.7
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 100% |  |  | 100%
Common ICS | 38.508-2 | 100% |  |  | 100%
NR RF/RRM
FR2 RF common parts | 38.521-2 | 100% |  |  | 100%
FR2 RF Tx test cases | 38.521-2 Tx | 100% | 11.2 | 11.2 | 100% | 11.2 | 11.2
FR2 RF Rx test cases | 38.521-2 Rx | 84.5% (+19.7%) | 1.1 (+0.4) | 1.4 | 84.5% (+19.7%) | 1.1 (+0.4) | 1.4
EN-DC FR2 RF test cases | 38.521-3 | 100% | 8.1 | 8.1 | 100% | 8.1 | 8.1
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 100% |  |  | 100%
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 50% |  |  | 50%
Test Point analysis receiver and transmitter test cases | 38.905 | 50% |  |  | 50%
5 References
[1] RP-210363 | New WID on UE Conformance Test Aspects for NR RF Requirement Enhancements for FR2
[2] RP-212304 | Revised WID - UE Conformance Test Aspects for NR RF Requirement Enhancements for FR2
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance Test Aspects for NR RF Requirement Enhancements for FR2 | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_RF_FR2_req_enh-UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item UE Conformance Test Aspects for FR2 RF Enhancements for NR comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID).
WP Resp: |  | Tuomo Säynäjäkangas, Nokia Ashwin Mohan, Apple |  |  | tuomo.saynajakangas@nokia.com ashwin_mohan@apple.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR2
97.1% (+3%)
163
34.7
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 38.508-1 | 4.3 | Reference test conditions | Add necessary test conditions for Rel-16 NR RF FR2 aspects | Nokia | RAN5#93 (Nov-21) | R5-218267, R5-220308, R5-220309 | Inter-band CA_n260A-n261A. Intra contig CA config CA_n261M | 0.1 | 100% | 100% |  | 100%
2 |  | 38.508-1 | 4.6 | Default NG-RAN RRC message and information elements contents | New message and IE definition for new Rel-16 NR RF FR2 features | Nokia | RAN5#92 (Aug-21) | R5-214026 |  | 0.1 | 100% | 100% |  | 100%
3 |  | 38.508-1 | 5 | Test environments for RF test | Necessary changes to RF test environments | Nokia | RAN5#93 (Nov-21) |  | No changes required | 0.1 | 100% | 100% |  | 100%
TS 38.508-2: Common ICS
4 |  | 38.508-2 | A,4 | ICS proforma tables | Add ICS as needed for the test case applicability statements for Rel-16 NR RF FR2 aspects | Nokia, Keysight | RAN5#92 (Aug-21) | R5-214027 R5-227893, R5-233031 | Adding PICS for SSB based BC and CSI-RS based BC | 0.1 | 100% | 100% |  | 100%
NR RF/RRM
TS 38.521-2: FR2 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-2 | 2 | References | Define References made in TS | Nokia | RAN5#94 (Feb-22) |  | No changes required | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 | 3 | Definitions, symbols and abbreviations | 3 subsections which define definitions, symbols and abbreviations respectively | Apple | RAN5#94 (Feb-22) | R5-215980 |  | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 | 4 | General | Define categories of test requirements | Nokia | RAN5#92 (Aug-21) |  | No changes required | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 | 5 | Operating bands and Channel arrangement | Frequency Separation Classes, Intra-band and Inter-band CA configuration updates | Apple | RAN5#92 (Aug-21) | R5-218475, R5-221355 | Add inter-band CA clauses + CA band and config for CA_n260A-n261A | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 | Annex A | Measurement channels | Annex A.3 updates for Rel-16 Beam Correspondence | Apple | RAN5#93 (Nov-21) | R5-221889 |  | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 | Annex B | Propagation conditions | Possible propagation conditions updates in Rel-16 NR RF FR2 tests (IBM) | Nokia | RAN5#94 (Feb-22) |  | No changes required | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 | Annex C | Downlink physical channels | Define new downlink physical channels in Rel-16 | Nokia | RAN5#94 (Feb-22) |  | No changes required | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 | Annex D | Interfering signals | Define any updates to characteristics of the interfering signal updates in Rel-16 NR RF FR2 tests | Nokia | RAN5#94 (Feb-22) |  | No changes required | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 | Annex E | Global In-Channel TX-Test | Specifiy the measurement of all relevant parameters that describe the in-channel quality of the output signal of the TX under test in a single measurement process (Rel-16 Updates, if any) | Nokia | RAN5#94 (Feb-22) |  | No changes required | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 | Annex F | Measurement uncertainties and Test Tolerances | Define measurement uncertainties and TT for updated Rel-16 test cases/bands | Nokia, Keysight, Apple | RAN5#97 (Nov-22) | R5-218368, R5-218369, R5-221354 R5-225660, R5-225659, R5-225607, R5-227819. R5-233560 | Check new TCs Add Power Boost values Add values for new test 6.2.2_1 | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 | Annex G | Uplink Physical Channels | Define uplink physical channels (Rel-16 updates) | Nokia | RAN5#93 (Nov-21) |  | No changes required | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 | Annex H | Statistical Testing | TBD | Nokia | RAN5#95 (May-22) |  | No changes required | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 | Annex K | EIRP, TRP, and EIS measurement procedures | Update K.1.1 TX beam peak direction search and K.1.9 Beam Correspondence tolerance procedure | Apple, Nokia | RAN5#94 (Feb-22) | R5-223750 R5-227764 | Editorial correction to EIS spherical coverage | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 | Annex P | Modified MPR Behavior | Rel-16 MPR enhancements | Nokia | RAN5#94 (Feb-22) |  | No changes required | 0.1 | 100% | 100% |  | 100%
TS 38.521-2: FR2 RF test cases - Tx
|  | 38.521-2 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD | Y | 38.521-2 Tx | 6.2.1.1_1 | UE maximum output power - EIRP and TRP | Rel-16 MBR enhancements (check accessStratumrelease for Rel-16 support) | Apple, Keysight | RAN5#93 (Nov-21) | R5-223750 R5-224109, R5-225659, R5-227762, R5-233717 | Separate TC/clause for Rel-16 MBR Update to test applicability and side condition of beam correspondence | 1 | 100% | 100% |  | 100%
TBD | Y | 38.521-2 Tx | 6.2.1.2_1 | UE maximum output power - Spherical coverage | Rel-16 MBR enhancements | Apple, Keysight | RAN5#93 (Nov-21) | R5-223750 R5-225659, R5-233717 | Separate TC/clause for Rel-16 MBR | 1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.2.2 | UE maximum output power reduction | Update minimum requirement and power boost IE updates for Rel-16, Beam Management Config updates | Apple, Keysight, Huawei | RAN5#95-e (May-22) | R5-223749, R5-223636, R5-225607, R5-231890 | Rel16 updates to be tracked as part of separate test case as per Prop3 endorsed in R5-223636. | 1 | 100% | 100% |  | 100%
TBD | Y | 38.521-2 Tx | 6.2.2_1 | UE maximum output power reduction | Update minimum requirement and power boost IE updates for Rel-16, Beam Management Config updates | Apple, Keysight, CAICT, Huawei | RAN5#96 (Aug-22) | R5-223749, R5-223636, R5-225607, R5-227763, R5-227775, R5-226921, R5-231890 | Rel16 specific test case as per R5-223636 Proposal 3 endorsed at RAN5#95e | 1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.2.4 | Configured transmitted power | P-MPR updates, support for powerboost IE in minimum conformance requirements | Nokia | RAN5#92 (Aug-21) | R5-212225 | No core spec changes in CA section 6.2A.4 | 0.1 | 100% | 100% |  | 100%
TBD | Y | 38.521-2 Tx | 6.2.4_1 | Configured transmitted power with Power boost | Add Power Boost associated testing from Rel-16 onwards for devices supporting mpr-PowerBoost-FR2-r16 UE capability. | Keysight, Apple | RAN5#97 (Nov-22) | R5-224046 R5-225647 R5-225658 | New TC for Power boost | 1 | 100% | 100% |  | 100%
|  | 38.521-2 Tx | 6.2A | Transmit power for CA | Existing sub-clause header
|  | 38.521-2 Tx | 6.2A.1 | UE maximum output power for CA | Existing sub-clause header
TBD |  | 38.521-2 Tx | 6.2A.1.0 | Minimum conformance requirements | New requirements for n260 for up to three uplink sub-blocks | Apple | RAN5#92 (Aug-21) |  | R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
|  | 38.521-2 Tx | 6.2A.1.1 | UE maximum output power - EIRP and TRP for CA | Existing sub-clause header
TBD |  | 38.521-2 Tx | 6.2A.1.1.1 | UE maximum output power - EIRP and TRP for CA (2UL CA) | New requirements for n260 for up to three uplink sub-blocks | Apple | RAN5#93 (Nov-21) |  | R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.2A.1.1.2 | UE maximum output power - EIRP and TRP for CA (3UL CA) | New requirements for n260 for up to three uplink sub-blocks | Apple | RAN5#93 (Nov-21) |  | R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.2A.1.1.3 | UE maximum output power - EIRP and TRP for CA (4UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements | Apple | RAN5#93 (Nov-21) |  | R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.2A.1.1.4 | UE maximum output power - EIRP and TRP for CA (5UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements | Apple | RAN5#93 (Nov-21) |  | R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.2A.1.1.5 | UE maximum output power - EIRP and TRP for CA (6UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements | Nokia | RAN5#93 (Nov-21) |  | R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.2A.1.1.6 | UE maximum output power - EIRP and TRP for CA (7UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements | Nokia | RAN5#93 (Nov-21) |  | R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.2A.1.1.7 | UE maximum output power - EIRP and TRP for CA (8UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements | Nokia | RAN5#93 (Nov-21) |  | R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
|  | 38.521-2 Tx | 6.2A.1.2 | UE maximum output power - Spherical coverage for CA | Existing sub-clause header
TBD |  | 38.521-2 Tx | 6.2A.1.2.1 | UE maximum output power - Spherical coverage for CA (2UL CA) | New requirements for n260 for up to three uplink sub-blocks | Apple | RAN5#93 (Nov-21) |  | R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.2A.1.2.2 | UE maximum output power - Spherical coverage for CA (3UL CA) | New requirements for n260 for up to three uplink sub-blocks | Apple | RAN5#93 (Nov-21) |  | R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.2A.1.2.3 | UE maximum output power - Spherical coverage for CA (4UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements | Apple | RAN5#93 (Nov-21) |  | R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.2A.1.2.4 | UE maximum output power - Spherical coverage for CA (5UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements | Apple | RAN5#93 (Nov-21) |  | R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.2A.1.2.5 | UE maximum output power - Spherical coverage for CA (6UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements | Nokia | RAN5#93 (Nov-21) |  | R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.2A.1.2.6 | UE maximum output power - Spherical coverage for CA (7UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements | Nokia | RAN5#93 (Nov-21) |  | R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.2A.1.2.7 | UE maximum output power - Spherical coverage for CA (8UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements | Nokia | RAN5#93 (Nov-21) |  | R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
|  | 38.521-2 Tx | 6.2A.2 | UE maximum output power reduction for CA | Existing sub-clause header | ZTE |  | R5-231837
|  | 38.521-2 Tx | 6.2A.2.0 | Minimum conformance requirements | New requirements for n260 for up to three uplink sub-blocks | Huawei | RAN5#94 (Feb-22) |  | R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.2A.2.1 | UE maximum output power reduction for CA (2UL CA) | New requirements for n260 for up to three uplink sub-blocks | Huawei | RAN5#94 (Feb-22) |  | R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.2A.2.2 | UE maximum output power reduction for CA (3UL CA) | New requirements for n260 for up to three uplink sub-blocks | Huawei | RAN5#94 (Feb-22) |  | R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.2A.2.3 | UE maximum output power reduction for CA (4UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements | Huawei | RAN5#94 (Feb-22) |  | Align sub-clause structure with Rel-15. R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.2A.2.4 | UE maximum output power reduction for CA (5UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements | Huawei | RAN5#94 (Feb-22) |  | Align sub-clause structure with Rel-15. R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.2A.2.5 | UE maximum output power reduction for CA (6UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements | Huawei | RAN5#94 (Feb-22) |  | Align sub-clause structure with Rel-15. R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.2A.2.6 | UE maximum output power reduction for CA (7UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements | Huawei | RAN5#94 (Feb-22) |  | Align sub-clause structure with Rel-15. R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.2A.2.7 | UE maximum output power reduction for CA (8UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements | Huawei | RAN5#94 (Feb-22) |  | Align sub-clause structure with Rel-15. R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
|  | 38.521-2 Tx | 6.2A.4 | Configured transmitted power for CA | Existing sub-clause header
TBD |  | 38.521-2 Tx | 6.2A.4.0 | Minimum conformance requirements | New requirements for n260 for up to three uplink sub-blocks | Huawei | RAN5#94 (Feb-22) |  | R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.2A.4.1 | Configured transmitted power for CA (2UL CA) | New requirements for n260 for up to three uplink sub-blocks | Huawei | RAN5#94 (Feb-22) |  | R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.2A.4.2 | Configured transmitted power for CA (3UL CA) | New requirements for n260 for up to three uplink sub-blocks | Huawei | RAN5#94 (Feb-22) |  | R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.2A.4.3 | Configured transmitted power for CA (4UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements | Huawei | RAN5#94 (Feb-22) |  | Align sub-clause structure with Rel-15. R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.2A.4.4 | Configured transmitted power for CA (5UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements | Huawei | RAN5#94 (Feb-22) |  | Align sub-clause structure with Rel-15. R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.2A.4.5 | Configured transmitted power for CA (6UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements | Huawei | RAN5#94 (Feb-22) |  | Align sub-clause structure with Rel-15. R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.2A.4.6 | Configured transmitted power for CA (7UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements | Huawei | RAN5#94 (Feb-22) |  | Align sub-clause structure with Rel-15. R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.2A.4.7 | Configured transmitted power for CA (8UL CA) | Intra-band non-contiguous UL CA udpates ; Check impact of Rel-16 MBR enhancements | Huawei | RAN5#94 (Feb-22) |  | Align sub-clause structure with Rel-15. R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.3A.1 | Minimum output power for CA | Existing sub-clause header
TBD |  | 38.521-2 Tx | 6.3A.1.0 | Minimum conformance requirements | Include intra-band non-contiguous CA | Nokia | RAN5#92 (Aug-21) | R5-212227, R5-218430 | R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.3A.2 | Transmit OFF power for CA | Existing sub-clause header
TBD |  | 38.521-2 Tx | 6.3A.2.0 | Minimum conformance requirements | Include intra-band non-contiguous CA | Nokia | RAN5#92 (Aug-21) | R5-212227, R5-218430 | R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.3A.3 | Transmit ON/OFF time mask for CA | Existing sub-clause header |  |  |  | Sub-clause structure aligned with Rel-15 WP
TBD |  | 38.521-2 Tx | 6.3A.3.0 | Minimum conformance requirements | Include intra-band non-contiguous CA | Nokia | RAN5#93 (Nov-21) | R5-212227, R5-214914, R5-218430 | 2UL-8UL clauses in rel-15 WP R5-218430 removes introduction of NC UL CA as no interested operator | 0.5 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.3A.3.1 | General ON/OFF time mask for CA | Measure the general ON/OFF time mask of 5G-NR FR2 UE. | Nokia |  |  | FFSs in 6.3A.3.1.1 To be solved by Rel-15 WI NC included => Rel-16 complete |  | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.3A.4.2 | Absolute power tolerance for CA | Existing sub-clause header
TBD |  | 38.521-2 Tx | 6.3A.4.2.0 | Minimum conformance requirements | Include intra-band contiguous and non-contiguous CA | Nokia | RAN5#92 (Aug-21) | R5-212227, R5-218430 | R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.3A.4.3 | Relative power tolerance for CA | New sub-clause header |  |  | R5-215858 | Clause introduced by Rel-15 WP | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.3A.4.3.0 | Minimum conformance requirements | Include intra-band contiguous and non-contiguous CA | Nokia | RAN5#94 (Feb-22) | R5-215858, R5-218430 | Clause introduced by Rel-15 WP R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.3A.4.4 | Aggregate power tolerance for CA | New sub-clause header |  |  |  | Clause introduced by Rel-15 WP | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.3A.4.4.0 | Minimum conformance requirements | Include intra-band contiguous and non-contiguous CA | Nokia | RAN5#94 (Feb-22) | R5-216549, R5-218430 | Clause introduced by Rel-15 WP R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
TBD | Y | 38.521-2 Tx | 6.4.2.1_1 | Error vector magnitude with Power Boost | Define a new test case | Keysight | RAN5#97 (Nov-22) | R5-227911 |  | 1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.4.2.2.3 | Carrier Leakage, minimum requirements for FR2 | Rel-16 powerBoost (IBE suspended) | Apple | RAN5#92 (Aug-21) |  | No changes required | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.4.2.3.3 | In-band emissions, minimum requirements for FR2 | Rel-16 powerBoost (IBE suspended) | Nokia, Keysight, Apple | RAN5#92 (Aug-21) | R5-212226 R5-225743 | Alignment with core spec | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.4A.1.0 | Frequency error for CA | Include intra-band non-contiguous CA for minimum conformace | Nokia | RAN5#92 (Aug-21) | R5-214104, R5-214915 R5-218430 | R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.4A.2 | Transmit modulation quality for CA | Include intra-band non-contiguous CA for minimum conformace | Nokia | RAN5#92 (Aug-21) | R5-214104, R5-215975, R5-218430 | Tests are incomplete due to lack of RRC framework for LO position retrieval. Mus and TTs are FFS R5-218430 removes introduction of NC UL CA as no interested operator | 0.5 | 100% | 100% |  | 100%
TBD | Y | 38.521-2 Tx | 6.5.2.1_1 | Spectrum Emission Mask with Power Boost | Define a new test case | Keysight | RAN5#97 (Nov-22) | R5-227910 |  | 1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.5.2.3 | ACLR, minimum requirements for FR2 | Rel-16 powerBoost (IBE suspended) |  | RAN5#97 (Nov-22) |  | No changes required | 0.1 | 100% | 100% |  | 100%
TBD | Y | 38.521-2 Tx | 6.5.3.1_1 | Transmitter Spurious emissions with Power Boost | Define a new test case | Keysight | RAN5#97 (Nov-22) | R5-228037 |  | 1 | 100% | 100% |  | 100%
TBD | Y | 38.521-2 Tx | 6.5.3.2_1 | Spurious emission band UE co-existence with Power Boost | Define a new test case | Keysight | RAN5#97 (Nov-22) | R5-228038 |  | 1 | 100% | 100% |  | 100%
TBD | Y | 38.521-2 Tx | 6.5.3.3_1 | Additional spurious emissions with Power Boost | Define a new test case | Keysight | RAN5#97 (Nov-22) | R5-228039 |  | 1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.5A.1 | Occupied bandwidth for CA | Existing sub-clause header | Nokia |  | R5-212229 | 2UL-8UL clauses in rel-15 WP
TBD |  | 38.521-2 Tx | 6.5A.1.0 | Minimum conformance requirements | Align text with Rel-15 and RAN4 spec | Nokia | RAN5#94 (Feb-22) | R5-212229 | FFSs in 6.5A.1.1 To be solved by Rel-15 WI NC included => Rel-16 complete | 0.1 | 100% | 100% |  | 100%
TBD | Y | 38.521-2 Tx | 6.5A.1.0.0 | General | New clause for General | Nokia | RAN5#94 (Feb-22) | R5-212229 | RAN4 WI introduced new clause. Align spec structure with other Wis | 0.1 | 100% | 100% |  | 100%
TBD | Y | 38.521-2 Tx | 6.5A.1.0.1 | Occupied bandwidth for intra-band contiguous UL CA | New clause for intra-band contiguous UL CA | Nokia | RAN5#94 (Feb-22) | R5-212229 | RAN4 WI introduced new clause. Align spec structure with other Wis | 0.1 | 100% | 100% |  | 100%
TBD | Y | 38.521-2 Tx | 6.5A.1.0.2 | Occupied bandwidth for intra-band non-contiguous UL CA | New clause for intra-band non-contiguous UL CA | Nokia | RAN5#94 (Feb-22) | R5-212229, R5-218430 | RAN4 WI introduced new clause. Align spec structure with other Wis R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.5A.2.1 | Spectrum emission mask for CA | Existing sub-clause header | Nokia |  | R5-212230
TBD |  | 38.521-2 Tx | 6.5A.2.1.0 | Minimum conformance requirements | Align text with Rel-15 and RAN4 spec | Nokia | RAN5#94 (Feb-22) | R5-212230 |  | 0.1 | 100% | 100% |  | 100%
TBD | Y | 38.521-2 Tx | 6.5A.2.1.0.0 | General | New clause for General | Nokia | RAN5#94 (Feb-22) | R5-212230 | RAN4 WI introduced new clause. Align spec structure with other Wis | 0.1 | 100% | 100% |  | 100%
TBD | Y | 38.521-2 Tx | 6.5A.2.1.0.1 | Spectrum emission mask for intra-band contiguous UL CA | New clause for intra-band contiguous UL CA | Nokia | RAN5#94 (Feb-22) | R5-212230 | RAN4 WI introduced new clause. Align spec structure with other Wis | 0.1 | 100% | 100% |  | 100%
TBD | Y | 38.521-2 Tx | 6.5A.2.1.0.2 | Spectrum emission mask for intra-band non-contiguous UL CA | New clause for intra-band non-contiguous UL CA | Nokia | RAN5#94 (Feb-22) | R5-212230, R5-218430 | RAN4 WI introduced new clause. Align spec structure with other Wis R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.5A.2.2 | Adjacent channel leakage ratio for CA | Existing sub-clause header | Nokia |  | R5-212231
TBD |  | 38.521-2 Tx | 6.5A.2.2.0 | Minimum conformance requirements | Align text with Rel-15 and RAN4 spec | Nokia | RAN5#94 (Feb-22) | R5-212231 |  | 0.1 | 100% | 100% |  | 100%
TBD | Y | 38.521-2 Tx | 6.5A.2.2.0.1 | Adjacent channel leakage ratio for CA intra-band contiguous UL CA | New clause for intra-band contiguous UL CA | Nokia | RAN5#94 (Feb-22) | R5-212231 | RAN4 WI introduced new clause. Align spec structure with other Wis | 0.1 | 100% | 100% |  | 100%
TBD | Y | 38.521-2 Tx | 6.5A.2.2.0.2 | Adjacent channel leakage ratio for CA intra-band non-contiguous UL CA | New clause for intra-band non-contiguous UL CA | Nokia | RAN5#94 (Feb-22) | R5-212231, R5-218430 | RAN4 WI introduced new clause. Align spec structure with other Wis R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.5A.3 | Spurious emissions for CA | Existing sub-clause header | Nokia |  | R5-214028
TBD |  | 38.521-2 Tx | 6.5A.3.1 | General spurious emissions for CA | Clause title change from transmitter to general | Nokia | RAN5#94 (Feb-22) | R5-214028 |  | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.5A.3.1.0 | Minimum conformance requirements | Align text with Rel-15 and RAN4 spec | Nokia | RAN5#94 (Feb-22) | R5-214028 |  | 0.1 | 100% | 100% |  | 100%
TBD | Y | 38.521-2 Tx | 6.5A.3.1.0.0 | General | New clause for General | Nokia | RAN5#94 (Feb-22) | R5-214028 | RAN4 WI introduced new clause. Align spec structure with other Wis | 0.1 | 100% | 100% |  | 100%
TBD | Y | 38.521-2 Tx | 6.5A.3.1.0.1 | Spurious emissions for intra-band contiguous UL CA | New clause for intra-band contiguous UL CA | Nokia | RAN5#94 (Feb-22) | R5-214028 | RAN4 WI introduced new clause. Align spec structure with other Wis | 0.1 | 100% | 100% |  | 100%
TBD | Y | 38.521-2 Tx | 6.5A.3.1.0.2 | Spurious emissions for intra-band non-contiguous UL CA | New clause for intra-band non-contiguous UL CA | Nokia | RAN5#94 (Feb-22) | R5-214028, R5-218430 | RAN4 WI introduced new clause. Align spec structure with other Wis R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.5A.3.2 | Spurious emission band UE co-existence for CA | Include UL, intra-band non-contiguous CA | Nokia | RAN5#92 (Aug-21) | R5-212233, R5-218430 | R5-218430 removes introduction of NC UL CA as no interested operator | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.6.0 | Beam Correspondence - General | Update text to cover Enhanced (Rel-16) Beam Correspondence | Apple, Nokia | RAN5#93 (Nov-21) | R5-214029 |  | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.6.1 | Beam Correspondence - EIRP | Align sub-clause structure with 38.101-2. This clause continue to cover Rel-15 aspects | Apple, Nokia, Anritsu | RAN5#93 (Nov-21) | R5-214029, R5-215636, R5-215637, R5-218366, R5-218367, R5-230976, R5-233717 |  | 0.1 | 100% | 100% |  | 100%
TBD | Y | 38.521-2 Tx | 6.6.2 | Enhanced Beam Correspondence - EIRP | New sub-clause to cover Rel-16 content | Apple, Nokia | RAN5#93 (Nov-21) | R5-214029 R5-218474, R5-221889, R5-223632, R5-223750, R5-225659, R5-233717 | TT impact on enhanced beam correspondence side conditions is FFS | 1 | 100% | 100% |  | 100%
TBD | Y | 38.521-2 Tx | 6.6.2.3.1.2 | Enhanced Beam Correspondence - EIRP | New sub-clause; Applicability rules based on support for type of enhanced beam correspondence | Apple | RAN5#93 (Nov-21) | R5-216081, R5-221890 |  | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Tx | 6.6A | Beam Correspondence for CA | Rel-16 Requirements Updates | Apple | RAN5#93 (Nov-21) | R5-221356 |  | 0.5 | 100% | 100% |  | 100%
TS 38.521-2: FR2 RF test cases - Rx
|  | 38.521-2 Rx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-2 Rx | 7.3.2 | Reference sensitivity power level | Possible requirements updates | Apple | RAN5#93 (Nov-21) |  | No changes required | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Rx | 7.3.4 | EIS spherical coverage | Possible requirements updates | Apple | RAN5#93 (Nov-21) |  | No changes required | 0.1 | 100% | 100% |  | 100%
|  | 38.521-2 Rx | 7.3A.2 | Reference sensitivity power level for CA | Existing sub-clause header |  |  |  | Check if need to include DL into clause 7.3A heading.
TBD |  | 38.521-2 Rx | 7.3A.2.0 | Minimum requirements | Requirements updates | Apple | RAN5#93 (Nov-21) | R5-213329, R5-215979 |  | 0.1 | 100% | 100% |  | 100%
TBD | Y | 38.521-2 Rx | 7.3A.2.0.3 | Inter-band CA | Add Inter-band CA requirements | Apple | RAN5#94 (Feb-22) | R5-213329, R5-214910 | New clause included in 38.521-2. Remove brackets and correct clause references. | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Rx | 7.3A.2.1 | Reference sensitivity power level for CA (2DL CA) | Delta RIB updates for intra-band CA. DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple, Keysight | RAN5#94 (Feb-22) | R5-213329 R5-227941 | MU and TT are FFS. Beam peak search is FFS Extreme conditions for FR2 are FFS Some references in square brackets for inter-band DL CA R5-227941: Test procedure for Inter-band CA added | 0.1 | 50% (+30%) | 50% (+30%) |  | 50%
TBD |  | 38.521-2 Rx | 7.3A.2.2 | Reference sensitivity power level for CA (3DL CA) | Delta RIB updates for intra-band CA. DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  | Clause structure complete. FFSs in editors notes | 0.1 | 50% (+50%) | 50% (+50%) |  | 50%
TBD |  | 38.521-2 Rx | 7.3A.2.3 | Reference sensitivity power level for CA (4DL CA) | Delta RIB updates for intra-band CA. DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  | Clause structure complete. FFSs in editors notes | 0.1 | 50% (+50%) | 50% (+50%) |  | 50%
TBD |  | 38.521-2 Rx | 7.3A.2.4 | Reference sensitivity power level for CA (5DL CA) | Delta RIB updates for intra-band CA. DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) | R5-233560 | Clause structure complete. FFSs in editors notes | 0.1 | 50% (+50%) | 50% (+50%) |  | 50%
TBD |  | 38.521-2 Rx | 7.3A.2.5 | Reference sensitivity power level for CA (6DL CA) | Delta RIB updates for intra-band CA. DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) | R5-233560 | Clause structure complete. FFSs in editors notes | 0.1 | 50% (+50%) | 50% (+50%) |  | 50%
TBD |  | 38.521-2 Rx | 7.3A.2.6 | Reference sensitivity power level for CA (7DL CA) | Delta RIB updates for intra-band CA. DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) | R5-233560 | Clause structure complete. FFSs in editors notes | 0.1 | 50% (+50%) | 50% (+50%) |  | 50%
TBD |  | 38.521-2 Rx | 7.3A.2.7 | Reference sensitivity power level for CA (8DL CA) | Delta RIB updates for intra-band CA. DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) | R5-233560 | Clause structure complete. FFSs in editors notes | 0.1 | 50% (+50%) | 50% (+50%) |  | 50%
TBD | Y | 38.521-2 Rx | 7.3A.3 | EIS spherical coverage for CA | New clause for EIS spherical coverage for CA | Apple, CAICT | RAN5#95 (May-22) | R5-215618 R5-224248 | RAN4 WI introduced new clause. Align spec structure with other WIs | 0.1 | 100% | 100% |  | 100%
TBD | Y | 38.521-2 Rx | 7.3A.3.0 | Minimum conformance requirements | New clause | Apple | RAN5#95 (May-22) | R5-215618 | RAN4 WI introduced new clause. Align spec structure with other WIs | 0.1 | 100% | 100% |  | 100%
TBD | Y | 38.521-2 Rx | 7.3A.3.0.1 | Void | New clause to align with 38.101-2 | Apple | RAN5#95 (May-22) | R5-215618 | RAN4 WI introduced new clause. Align spec structure with other WIs | 0.1 | 100% | 100% |  | 100%
TBD | Y | 38.521-2 Rx | 7.3A.3.0.2 | Void | New clause to align with 38.101-2 | Apple | RAN5#95 (May-22) | R5-215618 | RAN4 WI introduced new clause. Align spec structure with other WIs | 0.1 | 100% | 100% |  | 100%
TBD | Y | 38.521-2 Rx | 7.3A.3.0.3 | EIS spherical coverage for Inter-band CA | New clause for Inter-band CA | Apple, CAICT | RAN5#95 (May-22) | R5-215618 R5-224248 | RAN4 WI introduced new clause. Align spec structure with other WIs | 0.1 | 100% | 100% |  | 100%
TBD | Y | 38.521-2 Rx | 7.3A.3.1 | EIS spherical coverage for CA (2DL CA) | New clause for Inter-band CA | Apple, CAICT | RAN5#95 (May-22) | R5-221357, R5-223751, R5-224248 | Align spec structure with other Wis MUs, TTs, test configs are FFS Some aspects of beam peak search procedures for CA are FFS | 0.1 | 80% (+5%) | 80% (+5%) |  | 80%
TBD | Y | 38.521-2 Rx | 7.3A.3.2 | EIS spherical coverage for CA (3DL CA) | New clause for Inter-band CA | Apple | RAN5#95 (May-22) | R5-221357, R5-233559 | Content added. Some aspects for FFS | 0.1 | 80% (+30%) | 80% (+30%) |  | 80%
TBD | Y | 38.521-2 Rx | 7.3A.3.3 | EIS spherical coverage for CA (4DL CA) | New clause for Inter-band CA | Apple | RAN5#95 (May-22) | R5-221357, R5-233559 | Content added. Some aspects for FFS | 0.1 | 80% (+30%) | 80% (+30%) |  | 80%
TBD | Y | 38.521-2 Rx | 7.3A.3.4 | EIS spherical coverage for CA (5DL CA) | New clause for Inter-band CA | Apple | RAN5#95 (May-22) |  | No need for this clause in Rel-16 WI | 0.1 | 100% (+50%) | 100% (+50%) |  | 100%
TBD | Y | 38.521-2 Rx | 7.3A.3.5 | EIS spherical coverage for CA (6DL CA) | New clause for Inter-band CA | Apple | RAN5#95 (May-22) |  | No need for this clause in Rel-16 WI | 0.1 | 100% (+50%) | 100% (+50%) |  | 100%
TBD | Y | 38.521-2 Rx | 7.3A.3.6 | EIS spherical coverage for CA (7DL CA) | New clause for Inter-band CA | Apple | RAN5#95 (May-22) |  | No need for this clause in Rel-16 WI | 0.1 | 100% (+50%) | 100% (+50%) |  | 100%
TBD | Y | 38.521-2 Rx | 7.3A.3.7 | EIS spherical coverage for CA (8DL CA) | New clause for Inter-band CA | Apple | RAN5#95 (May-22) |  | No need for this clause in Rel-16 WI | 0.1 | 100% (+50%) | 100% (+50%) |  | 100%
|  | 38.521-2 Rx | 7.4A | Maximum input level for CA | Existing sub-clause header
TBD |  | 38.521-2 Rx | 7.4A.0 | Minimum requirements | Requirement updates | Nokia | RAN5#93 (Nov-21) |  |  | 0.1 | 100% | 100% |  | 100%
TBD | Y | 38.521-2 Rx | 7.4A.0.3 | Maximum input level for Inter-band CA | New clause for Inter-band CA | Apple, Nokia | RAN5#95 (May-22) | R5-215976 | RAN4 WI introduced new clause added. Align spec structure with other Wis. Check if need to include DL into clause 7.4A heading. Correct 7.4A.0.3 heading | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Rx | 7.4A.1 | Maximum input level for CA (2DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Nokia, Keysight | RAN5#94 (Feb-22) | R5-223752 R5-227782 R5-231660 R5-231852, R5-233561 | MU and TT are FFS. UL power level configuration is TBD Relaxation of DL power 256 QAM is FFS Intra- and inter-band testing is FFS Modify test freq for intra-band NC CA New test procedures for inter-band DL CA | 0.1 | 100% (+10%) | 100% (+10%) |  | 100%
TBD |  | 38.521-2 Rx | 7.4A.2 | Maximum input level for CA (3DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  | Clause structure complete. FFSs in editors notes | 0.1 | 80% (+80%) | 80% (+80%) |  | 80%
TBD |  | 38.521-2 Rx | 7.4A.3 | Maximum input level for CA (4DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  | Clause structure complete. FFSs in editors notes | 0.1 | 80% (+80%) | 80% (+80%) |  | 80%
TBD |  | 38.521-2 Rx | 7.4A.4 | Maximum input level for CA (5DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  | Clause structure complete. FFSs in editors notes | 0.1 | 80% (+80%) | 80% (+80%) |  | 80%
TBD |  | 38.521-2 Rx | 7.4A.5 | Maximum input level for CA (6DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  | Clause structure complete. FFSs in editors notes | 0.1 | 80% (+80%) | 80% (+80%) |  | 80%
TBD |  | 38.521-2 Rx | 7.4A.6 | Maximum input level for CA (7DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  | Clause structure complete. FFSs in editors notes | 0.1 | 80% (+80%) | 80% (+80%) |  | 80%
TBD |  | 38.521-2 Rx | 7.4A.7 | Maximum input level for CA (8DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) | R5-233561 | Clause structure complete. FFSs in editors notes | 0.1 | 80% (+80%) | 80% (+80%) |  | 80%
TBD |  | 38.521-2 Rx | 7.5A | Adjacent channel selectivity for CA | Existing sub-clause header |  | RAN5#93 (Nov-21) |  | Check if need to include DL into clause 7.5A heading.
TBD |  | 38.521-2 Rx | 7.5A.0 | Minimum requirements | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  | Already updated for NC CA. | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Rx | 7.5A.0.1 | Adjacent channel selectivity for Intra-band contiguous CA | Placeholder for Intra-band contiguous CA | Apple, Nokia | RAN5#94 (Feb-22) | R5-215977 | Align sub-clause structure with Rel-15 WP. Sub-clause currently not in spec | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Rx | 7.5A.0.2 | Adjacent channel selectivity for Intra-band non-contiguous CA | Placeholder for Intra-band non-contiguous CA | Apple, Nokia | RAN5#94 (Feb-22) | R5-215977 | Align sub-clause structure with Rel-15 WP. Sub-clause currently not in spec | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Rx | 7.5A.0.3 | Adjacent channel selectivity for Inter-band CA | Include inter-band CA | Apple, Nokia | RAN5#94 (Feb-22) | R5-215977 | Align sub-clause structure with Rel-15 WP. Sub-clause currently not in spec | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Rx | 7.5A.1 | Adjacent channel selectivity for CA (2DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  | Belongs to “5GS_NR_LTE-UEConTest” Work Item. Not to be specified under this WI. To be done under maintenance | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Rx | 7.5A.2 | Adjacent channel selectivity for CA (3DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  | Belongs to “5GS_NR_LTE-UEConTest” Work Item. Not to be specified under this WI. To be done under maintenance | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Rx | 7.5A.3 | Adjacent channel selectivity for CA (4DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  | Belongs to “5GS_NR_LTE-UEConTest” Work Item. Not to be specified under this WI. To be done under maintenance | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Rx | 7.5A.4 | Adjacent channel selectivity for CA (5DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  | Belongs to “5GS_NR_LTE-UEConTest” Work Item. Not to be specified under this WI. To be done under maintenance | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Rx | 7.5A.5 | Adjacent channel selectivity for CA (6DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  | Belongs to “5GS_NR_LTE-UEConTest” Work Item. Not to be specified under this WI. To be done under maintenance | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Rx | 7.5A.6 | Adjacent channel selectivity for CA (7DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  | Belongs to “5GS_NR_LTE-UEConTest” Work Item. Not to be specified under this WI. To be done under maintenance | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Rx | 7.5A.7 | Adjacent channel selectivity for CA (8DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  | Belongs to “5GS_NR_LTE-UEConTest” Work Item. Not to be specified under this WI. To be done under maintenance | 0.1 | 100% | 100% |  | 100%
|  | 38.521-2 Rx | 7.6A | Blocking characteristics for CA | Existing sub-clause header |  |  |  | Check if need to include DL into clause 7.6A heading.
TBD |  | 38.521-2 Rx | 7.6A.1 | General | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  |  | 0.1 | 100% | 100% |  | 100%
|  | 38.521-2 Rx | 7.6A.2 | In-band blocking for CA | Existing sub-clause header |  | RAN5#94 (Feb-22)
TBD |  | 38.521-2 Rx | 7.6A.2.0 | Minimum requirements | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) |  | Align sub-clause structure with Rel-15 WP. | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Rx | 7.6A.2.0.1 | In-band blocking for Intra-band contiguous CA | Placeholder for Intra-band contiguous CA | Apple, Nokia | RAN5#94 (Feb-22) | R5-215978 | Align sub-clause structure with Rel-15 WP. | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Rx | 7.6A.2.0.2 | In-band blocking for Intra-band non-contiguous CA | Placeholder for Intra-band non-contiguous CA | Apple, Nokia | RAN5#94 (Feb-22) | R5-215978 | Align sub-clause structure with Rel-15 WP. | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Rx | 7.6A.2.0.3 | In-band blocking for Inter-band CA | Include inter-band CA | Apple, Nokia | RAN5#94 (Feb-22) | R5-215978 | Align sub-clause structure with Rel-15 WP. | 0.1 | 100% | 100% |  | 100%
TBD |  | 38.521-2 Rx | 7.6A.2.1 | In-band blocking for CA (2DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple, Keysight | RAN5#94 (Feb-22) | R5-227772 R5-231852 | Align sub-clause structure with Rel-15 WP. New test procedure for inter-band DL CA Clause structure complete. FFSs in editors notes | 0.1 | 80% | 80% |  | 80%
TBD |  | 38.521-2 Rx | 7.6A.2.2 | In-band blocking for CA (3DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) | R5-227772 | Align sub-clause structure with Rel-15 WP. Clause structure complete. FFSs in editors notes | 0.1 | 50% | 50% |  | 50%
TBD |  | 38.521-2 Rx | 7.6A.2.3 | In-band blocking for CA (4DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) | R5-227772 | Align sub-clause structure with Rel-15 WP. Clause structure complete. FFSs in editors notes | 0.1 | 50% | 50% |  | 50%
TBD |  | 38.521-2 Rx | 7.6A.2.4 | In-band blocking for CA (5DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) | R5-227772 | Align sub-clause structure with Rel-15 WP. Clause structure complete. FFSs in editors notes | 0.1 | 50% | 50% |  | 50%
TBD |  | 38.521-2 Rx | 7.6A.2.5 | In-band blocking for CA (6DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) | R5-227772 | Align sub-clause structure with Rel-15 WP. Clause structure complete. FFSs in editors notes | 0.1 | 50% | 50% |  | 50%
TBD |  | 38.521-2 Rx | 7.6A.2.6 | In-band blocking for CA (7DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) | R5-227772 | Align sub-clause structure with Rel-15 WP. Clause structure complete. FFSs in editors notes | 0.1 | 50% | 50% |  | 50%
TBD |  | 38.521-2 Rx | 7.6A.2.7 | In-band blocking for CA (8DL CA) | DL Intra-band CA BW enhancement. New frequency separation classes introduced for up to 2400 MHz separation, Addition of Inter-band CA requirements | Apple | RAN5#94 (Feb-22) | R5-227772 | Align sub-clause structure with Rel-15 WP. Clause structure complete. FFSs in editors notes | 0.1 | 50% | 50% |  | 50%
TS 38.521-3: EN-DC FR2 RF test cases - necessary updates
|  | 38.521-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD | Y | 38.521-3 | Annex F | Measurement uncertainties and Test Tolerances | Define measurement uncertainties and test tolerances for the new EN-DC test case | Keysight | RAN5#97 (Nov-22) | R5-225662, R5-226941, R5-226994 | For the new EN-DC test case proposed in R5-224074 equal to equivalent standalone test case. | 0.1 | 100% | 100% |  | 100%
TBD | Y | 38.521-3 | 6.2B.2.4_2 | UE Maximum Output Power reduction enhancements for Inter-Band EN-DC including FR2 (1 NR CC) | Define a new test case | Keysight | RAN5#97 (Nov-22) | R5-226939 | Clause numbering checked | 1 | 100% | 100% |  | 100%
TBD | Y | 38.521-3 | 6.2B.4.1.4_1 | Configured Output Power with Power Boost for Inter-Band EN-DC including FR2 (1 NR CC) | Define a new test case to enable testing of Rel-16 FR2 RF Enhancements related to Power Boost for EN-DC. | Keysight | RAN5#97 (Nov-22) | R5-225661. R5-233190 |  | 1 | 100% | 100% |  | 100%
TBD | Y | 38.521-3 | 6.4B.2.4.1_2 | Error Vector Magnitude with Power Boost for inter-band EN-DC including FR2 (1 NR CC) | Define a new test case | Keysight | RAN5#97 (Nov-22) | R5-226886 | Clause numbering checked | 1 | 100% | 100% |  | 100%
TBD | Y | 38.521-3 | 6.5B.2.4.1_2 | Spectrum emissions mask with Power Boost for Inter-band EN-DC including FR2 (1 NR CC) | Define a new test case | Keysight | RAN5#97 (Nov-22) | R5-226887 | Clause numbering checked | 1 | 100% | 100% |  | 100%
TBD | Y | 38.521-3 | 6.5B.3.4.1_2 | General Spurious Emissions with Power Boost for Inter-band including FR2 (1 NR CC) | Define a new test case | Keysight | RAN5#97 (Nov-22) | R5-226888 | Clause numbering checked | 1 | 100% | 100% |  | 100%
TBD | Y | 38.521-3 | 6.5B.3.4.2_2 | Spurious emission band UE co-existence with Power Boost for Inter-band including FR2 (1 NR CC) | Define a new test case | Keysight | RAN5#97 (Nov-22) | R5-226889 | Clause numbering checked | 1 | 100% | 100% |  | 100%
TBD | Y | 38.521-3 | 6.5B.4.4 _1 | Additional Spurious Emissions with Power Boost for Inter-band including FR2 (1 NR CC) | Define a new test case | Keysight, CAICT | RAN5#97 (Nov-22) | R5-226890 R5-230570 | Check clause numbering | 1 | 100% | 100% |  | 100%
TBD | Y | 38.521-3 | 6.6B.5 | Enhanced Beam Correspondence for Inter-band EN-DC within FR2 (2 CCs) | WP adds a new SA test in TS 38.521-2. Add equivalent EN-DC Rel.16 Enhanced Beam correspondence test. | Apple, CAICT | RAN5#97 (Nov-22) | R5-217720 R5-225031, R5-226297, R5-227952, R5-230571 | The associated standalone test 6.6.2 in TS 38.521-2 [9] is incomplete. | 1 | 100% | 100% |  | 100%
TS 38.522: Applicability for RF FR2 test cases
TBD |  | 38.522 | 4,1,2 | FR2 standalone conformance test cases | Add test case applicability statements for the test cases introduced for 38.521-2. | Nokia, Keysight, Apple | RAN5#97 (Nov-22) | R5-215981, R5-217729, R5-218370, R5-221891, R5-223753, R5-226942, R5-227383, | Include new TCs | 0.1 | 100% | 100% |  | 100%
TR 38.903: Test Tolerances analysis RRM and RF test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.903 | Annex B | Acceptable uncertainty of test system for test cases defined in TS 38.521-2 for radiative testing | TT analysis for FR2 RF Test cases | Keysight | RAN5#97 (Nov-22) | R5-221629, R5-221657, R5-225663, | MU for Beam Correspondence MU for power boost Enh Beam Correspondence - EIRP TBD | 0.2 | 50% | 50% |  | 50%
TR 38.905: Test Point analysis receiver and transmitter test cases
|  | 38.905 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.905 | 4.2 | Test point analysis for FR2 test cases in TS 38.521-2 | TP analysis for FR2 RF Test cases | Keysight | RAN5#97 (Nov-22) | R5-225745 R5-227909 | Power boost config TX pwr, EVM, SEM | 0.2 | 50% | 50% |  | 50%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.