3GPP TSG-RAN Meeting #100	   RP-231295

Taipei, 12th – 14th June 2023

Agenda Item:	9.2.3

Source:	Rapporteur (Ericsson)

Title:	SI work plan for Study on self-evaluation towards the IMT-2020 submission of the 3GPP Satellite Radio Interface Technology

Document for:	Information

# 1	Introduction

This document provides a work plan for the Rel-18 study item on Self-Evaluation towards the 3GPP submission of a IMT-2020 Satellite Radio Interface Technology [1].

The deadline for the submission to ITU is December 31st 2023.

# 2	SI objective

The objectives are listed below [1]:

Detailed objectives of this study item include: - Complete all required submission templates as defined in Report ITU-R M.2514 [RAN ITU-R Ad-Hoc] - Provide self-evaluation results against technical performance requirements for eMBB-s as defined in Report ITU-R M.2514 [RAN ITU-R Ad-Hoc, RAN1, RAN2], including - Peak data rate - Peak spectral efficiency - User experienced data rate - 5th percentile user spectral efficiency - Average spectral efficiency - Area traffic capacity - Latency, including user plane latency and control plane latency - Energy efficiency, including both network and device - Mobility - Mobility interruption time - Provide self-evaluation results against technical performance requirements for mMTC-s as defined in Report ITU-R M.2514 [RAN ITU-R Ad-Hoc, RAN1, RAN2], including - Connection density - Provide self-evaluation results against technical performance requirements for HRC-s as defined in Report ITU-R M.2514 [RAN ITU-R Ad-Hoc, RAN1, RAN2], including - Reliability - Provide self-evaluation results for other requirements (including bandwidth) as defined in Report ITU-R M.2514 [RAN ITU-R Ad-Hoc, RAN1, RAN2, RAN4]

# 3	WI work plan

## 3.1	April 2023

RAN1#112bis-e

- Initial discussion and agreement on evaluation assumptions

## 3.2	May 2023

RAN1#113

- Final agreement on evaluation assumptions

RAN2#122

- Discussion and agreement on evaluation assumptions for RAN2 related performance requirements, e.g. latency and mobility interruption time.

## 3.3	June 2023

RAN#100

- Initial submission and review of TR skeleton, initial text proposals (eval assumptions), tech description and other templates

## 3.4	August 2023

RAN1#114

- Collection and discussion of evaluation results

RAN2#123

- Initial collection and analysis of RAN2 related evaluation results

## 3.5	September 2023

RAN#101

- Finalization of RIT vs SRIT submission

- Finalization of description templates

- Initial submission and review of compliance templates

- Further TR updates (descriptions, initial eval analysis/results, e.g. for inspection-based TPRs, etc.)

## 3.6	October 2023

RAN1#114bis

- Discussion of evaluation results

- Initial drafting of TPs for TR

RAN2#123bis

- Discussion of evaluation results

- Initial drafting of TPs for TR

RAN4#108bis

- Review of RAN4 related parts(e.g. description of spectrum bands for the compliance template)

## 3.7	November 2023

RAN1#115

- Finalization of RAN1 input to the self-evaluation

RAN2#124

- Finalization of RAN2 input to the self-evaluation

RAN4#109

- Finalization of RAN4 input to the self-evaluation

## 3.8	December 2023

RAN#102

- Finalization of self-evaluation report/templates and necessary submission inputs to ITU-R

# References

RP-230736, “New SID: Study on Self-Evaluation towards IMT-2020 Satellite Radio Interface Submission”, RAN#99