## Time_budget_request
|  |  |  | 1 TU = ~2h; RD: RRM/demodulation | [5 empty] | RAN | R1 | R2 | R3 | R4RF | R4RD | RAN | R1 | R2 | R3 | R4RF | R4RD | R1 | R2 | R3 | R4RF | R4RD | RAN
leading WG | RAT | WI code | WI or SI | Title | latest WID/SID | rapporteur | target | sum TUs | comment | 100 Jun.23 | 114 | 123 | 121 | 108 | 108 | 101 Sep.23 | 114bis | 123bis | 121bis | 108bis | 108bis | 115 | 124 | 122 | 109 | 109 | 102 Dec.23
R4 | NR | FS_SimBC | SI | Study on simplification of band combination specification for NR and LTE |  | ZTE | Dec.23 |  | REL-18 |  |  |  |  | 0.5 | [5 empty] | 0.25 |  |  |  |  | 0.25
| NR |  |  | allocated above | [5 empty] | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0
| NR |  |  | Legacy | [7 empty] | 13 | [5 empty] | 12.75 |  |  |  |  | 13.25
| NR |  |  | TEI and other not planned issues | [7 empty] | 1 | 0.5 |  |  |  |  | 1 | 0.5 |  |  |  | 1 | 0.5
| NR |  |  | Reserve | [6 empty] | 3 | 2.5 | [5 empty] | 3.5 |  |  |  |  | 3.5
| NR |  |  | total used capacity | [5 empty] | 0 | 3 | 16.5 | 0.5 | 0.5 | 0 | 0 | 0 | 17.25 | 0.5 | 0.25 | 0 | 0 | 17.75 | 0.5 | 0.25 | 0 | 0
| NR |  |  | available capacity | [7 empty] | 40 | 12 | 24.5 | 20.5 |  |  | 40 | 12 | 24.5 | 20.5 |  | 40 | 12 | 24.5 | 20.5
| NR |  |  | remaining/exceeded capacity | [5 empty] | 0 | -3 | 23.5 | 11.5 | 24 | 20.5 | 0 | 0 | 22.75 | 11.5 | 24.25 | 20.5 | 0 | 22.25 | 11.5 | 24.25 | 20.5 | 0
| LTE |  |  | allocated above
| LTE |  |  | Legacy
| LTE |  |  | TEI and other not planned issues
| LTE |  |  | Reserve
| LTE |  |  | total used capcaity
| LTE |  |  | available capacity
| LTE |  |  | remaining/exceeded capacity
| UTRA |  |  | allocated above
| UTRAN |  |  | Legacy
| UTRAN |  |  | TEI and other not planned issues
| UTRAN |  |  | Reserve
| UTRAN |  |  | total used capacity
| UTRAN |  |  | available capacity
| UTRAN |  |  | remaining/exceeded capacity
| GERAN |  |  | allocated above
| GERAN |  |  | Legacy
| GERAN |  |  | TEI and other not planned issues
| GERAN |  |  | Reserve
| GERAN |  |  | total used capacity
| GERAN |  |  | available capacity
| GERAN |  |  | remaining/exceeded capacity
R3 |  |  |  | RAN3 overall Status